## Imp_plan
ACTIVITIES | Partner in charge | Participating partners | Output | Phase 1 – Focus on the interregional learning process | [29 empty] | Phase 2 – monitoring of the action plan implementation
|  |  |  | 1st reporting period | [5 empty] | 2nd reporting period | [5 empty] | 3rd reporting period | [5 empty] | 4th reporting period | [5 empty] | 5th reporting period | [5 empty] | 6th reporting period | [11 empty] | 7th reporting period
|  |  |  | 2016 | [5 empty] | 2016 |  |  | 2017 |  |  | 2017 | [5 empty] | 2017 |  |  | 2018 |  |  | 2018 | [5 empty] | 2018 |  |  | 2019 | [8 empty] | 2019 |  |  | 2020
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
|  |  |  | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Febr | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Febr | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Febr | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Febr | Mar | Apr | May | June | July | Aug | Sept
Component 1 -PROJECT MANAGEMENT AND COORDINATION | LP
Contractualisation and start-up
Subsidy Contract | LP | All | 1 SC signed | bar: 2016 1 Apr
Partnership Agreement | LP | All | 1 PA signed | bar: 2016 1 Apr to 2016 2 May
Setting up PMTs (Project Management Teams) | LP | All | 6 PMT set up | bar: 2016 1 Apr
Appointment FLC | LP | All | 6 FLC appointed | bar: 2016 1 Apr to 2016 3 June
Financial and Project Management Guide (FPMG) | LP | All | 1 guide | bar: 2016 1 Apr to 2016 2 May
Rules of Procedures for the SG | LP | All | 1 RoP adopted | bar: 2016 1 Apr to 2016 2 May
Kick-off meeting | LP | All | 1 meeting | bar: 2016 2 May
Project Management and coordination
Daily project management | LP | All | n.a.
Steering Group meeting linked with TWG meeting | LP | All | 7 meetings (=5+2) | bar: 2016 6 Sept; 2017 11 Febr; 2017 20 Nov; 2018 26 May; 2018 30 Sept; 2019 38 May; 2019 44 Nov
Reporting
Internal financial monitoring/budget revision | LP | All | 3 revisions | bar: 2016 9 Dec to 2017 10 Jan; 2017 21 Dec to 2018 22 Jan
Preparation of partner level progress report | LP | All | 8 partner reports / partner | bar: 2016 6 Sept to 2016 9 Dec; 2017 12 Mar to 2017 15 June; 2017 18 Sept to 2017 21 Dec; 2018 24 Mar to 2018 27 June; 2018 30 Sept to 2018 33 Dec; 2019 42 Sept to 2019 45 Dec; 2020 52 July to 2020 54 Sept
Delivery of progress report to JTS | LP | All | 8 progress report | bar: 2017 10 Jan; 2017 16 July; 2018 22 Jan; 2018 28 July; 2019 34 Jan; 2020 46 Jan; 2020 54 Sept
Delivery of final report to JTS | LP | All | 1 final report | bar: 2020 54 Sept
Component 2 -COMMUNICATION | PP4-VPR
Planning and start-up
Communication and knowledge sharing strategy | PP5-VPR | All | 1 project level stategy | bar: 2016 2 May to 2016 4 July
Launching event | LP | All | 1 event | bar: 2016 6 Sept
Briefing brochure linked to the Launching event about the project and the topic adressed | PP5-VPR | All | 1 brochure (English and local editions) | bar: 2016 5 Aug to 2016 6 Sept
Poster (obligatory) | PP5-VPR | All | poster prepared for each partner | bar: 2016 5 Aug to 2016 6 Sept
Website and social media
Launching of website and regular update of the website | PP5-VPR | All | 1 website regularly updated
Social media presence | PP5-VPR | All | regular update
Paticipation in other events
INTERREG Europe events (annual programme events + Policy learning platform events) | PP5-VPR, LP- VRW | n.a. | 8 event | bar: 2016 6 Sept; 2017 11 Febr; 2017 17 Aug; 2018 23 Febr; 2018 29 Aug
Dissemnation at transnational events (presenter or exhibitioner) | PP5-VPR | All | 2 events / semester | bar: 2016 6 Sept; 2017 10 Jan; 2018 22 Jan; 2018 28 July
Dissemnation at national events (presenter or exhibitioner) | PP5-VPR | All | 2 events / partner region | bar: 2016 3 June; 2016 8 Nov; 2017 15 June; 2017 20 Nov; 2018 27 June
Communication materials/tools
Press releases | PP5-VPR | TWG meeting/event organisers | 7 press releases linked to the project meetings/events | bar: 2016 6 Sept; 2017 11 Febr; 2017 20 Nov; 2018 26 May; 2018 30 Sept; 2019 38 May; 2020 51 June
Newsletters on project level | PP5-VPR | All | 5 newsletters (English) | bar: 2016 6 Sept; 2017 11 Febr; 2017 20 Nov; 2018 26 May; 2018 30 Sept
Project video | PP5-VPR | All | 1 English project video | bar: 2018 29 Aug to 2018 30 Sept
Policy learning Synthesis report | LP- VRW, PP5-VPR | All | 1 Synthesis for dissemination | bar: 2018 29 Aug to 2018 30 Sept
Dissemination materials on exchanged experience targeting regions outside the partnership | PP4-VPR | All | 3 materials | bar: 2018 29 Aug to 2018 30 Sept
Mid term event | PP4-VPR | All partners | 1 event | bar: 2018 30 Sept
Final event | PP2- TCC | All partners | 1 event | bar: 2019 44 Nov
Visualisation materials for institutional, stakeholder meetings | PP5- VPR | LP, PP2, PP3, PP4, PP5 | 3 materials per region | bar: 2016 5 Aug to 2018 30 Sept
Component 3 -INTERREGIONAL POLICY LEARNING
Interregional thematic organisation
Setting up Thematic Working Group (TWG) | LP | All partners | 1 TWG established | bar: 2016 2 May
TWG Rules of procedure | LP | All partners | 1 Rules of Procedures | bar: 2016 2 May
TWG meetings linked to thematic implementation | LP | All partners | 7 meetings (5+2) | bar: 2016 6 Sept; 2017 11 Febr; 2017 20 Nov; 2018 26 May; 2018 30 Sept; 2019 38 May; 2019 44 Nov
Stakeholder involvement and organisational learning
Setting up stakeholder & institutional learning groups | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 1 group /policy instrument | bar: 2016 5 Aug to 2016 6 Sept
Interactive training on stakeholder involvement/institutional learning for the Regional Managers | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 1 training | bar: 2016 6 Sept
Methodology for regional Roadmaps | PP2- TCC | All partners | 1 methodology | bar: 2016 6 Sept
regional Roadmaps (on the institutional/stakeholder involvement process) elaborated and quality controled | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 1 regional roadmap/policy instrument | bar: 2016 7 Oct
Regional Opening meeting for stakeholders (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 1 meeting / stakeholder group | bar: 2016 6 Sept
Meetings with stakeholder groups and Institutional learning groups / involvement in action plan implementation + Synergy Sessions with Institutional departments | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 45 SIG meetings on projet level (5 policy instruments = 5 SIGs) | bar: 2016 6 Sept to 2018 30 Sept; 2020 54 Sept
Phase 1 closing stakeholder session (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 1 meeting / stakeholder group | bar: 2018 30 Sept
Synergy session for personnel of partner organisations | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 3 sessions / per partner | bar: 2016 8 Nov; 2017 18 Sept; 2018 25 Apr; 2018 30 Sept
Thematic coordination of stakeholder involvement | PP2- TCC | LP- VRW | n.a.
Analysis
Joint methodology for regional State of Arts | PP4 - PD | All partners | 1 methodology | bar: 2016 5 Aug to 2016 6 Sept
Regional State of Arts (including good practice inventory + list of ingredients for change) | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 | 1 analysis-desk research / policy instrument | bar: 2016 6 Sept to 2016 9 Dec
Project level menu of good practices | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 | 1 good practice collection | bar: 2016 8 Nov to 2017 10 Jan
Thematic coordination of analysis phase | PP4 - PD | LP- VRW | n.a. | bar: 2016 2 May to 2016 9 Dec
Knowledge exchange (good practice transfer)
Guidelines (including matching learning needs with good practices)/methodology and templates for knowledge sharing | LP- VRW | All partners | 1 guide | bar: 2017 10 Jan to 2017 12 Mar
3 Transnational Exchange Session meetings of 3 days length (for individual staff members of partners + appr. 3 stakeholders per partner region) | LP- VRW | All partners | 3 good practice transfer meetings | bar: 2017 13 Apr to 2017 18 Sept
Summary reports on the Exchange Sessions | LP- VRW | All partners | 1 report/policy instrument | bar: 2017 13 Apr to 2017 19 Oct
Thematic coordination of knowledge exchange | LP- VRW | n.a. | n.a. | bar: 2016 9 Dec to 2017 20 Nov
Action plan drafting
Project level Guideline and joint training on action plan development | PP3 - MCM | All partners | 1 guide, 1 training | bar: 2017 20 Nov to 2017 21 Dec
Detailed Action Plan methodology on regional level/workplan | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 1 Action plan methodology / policy instrument (5) | bar: 2018 22 Jan
Elaboration of Action Plans / policy instrument | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 1 action plan / policy instrument (5) | bar: 2018 23 Febr to 2018 28 July
Cross- reading exercise | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 1 procedure | bar: 2018 27 June to 2018 28 July
Final quality control of Action Plans | PP3 - MCM | n.a. | 1 quality control process / action plan | bar: 2018 28 July to 2018 29 Aug
Consistency check of Action Plans on regional level | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 1 procedure / action plan | bar: 2018 28 July to 2018 29 Aug
Thematic coordination of action planning | PP3 - MCM | LP- VRW | n.a. | bar: 2017 19 Oct to 2018 30 Sept
Action plan implementation follow-up(24 months)
Monitoring of the implementation of the action plans | LP- VRW | LP + PP6,PP2,PP3,PP4, PP5 | 1 monitoring procedure / policy instrument | bar: 2018 31 Oct to 2020 54 Sept
Summary on the level of achievements / policy instrument | LP- VRW | LP + PP6,PP2,PP3,PP4, PP5 | 1 report / policy instrument | bar: 2020 50 May to 2020 52 July
Note on J59: Zács Emőke: 1 SIG meeting (Opening SIG meeting)
Note on K59: Zács Emőke: 2 SIG meetings will be organised in Semester 2

## TOTAL
TOTAL |  |  |  | Country -->
DAILY FEE |  | 0 |  |  | Travel cost 1 person 2 nights |  |  | 600 | ERDF | 0.75
[5 empty] | Travel cost 1 person 3 nights |  |  | 800
1365338
Action | ACTIVITIES | Partner in charge | Participating
|  |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL
|  |  |  | days | total
| PREPARATION | LP
| Project proposal preparation |  |  |  | 0 | 0 | 0 | 15000 | 0 | 15000 | OK
| TOTAL |  |  |  | 0 | 0 | 0 | 15000 | 0 | 15000 | OK
| PROJECT MANAGEMENT AND COORDINATION | LP | [8 empty] | OK
| Contractualisation and start-up | [9 empty] | OK
| Subsidy Contract | LP | All |  | 442 | 66.3 | 0 | 0 | 0 | 508.3 | OK
| Partnership Agreement | LP | All |  | 2116 | 317.4 | 0 | 0 | 0 | 2433.4 | OK
| Appointment FLC | LP | All |  | 2464 | 369.6 | 0 | 0 | 0 | 2833.6 | OK
| Management and financial handbook | LP | All |  | 1895 | 284.25 | 0 | 0 | 0 | 2179.25 | OK
| Rules of Procedures for the PR | LP | All |  | 442 | 66.3 | 0 | 0 | 0 | 508.3 | OK
| Rules of Procedures for the SG | LP | All |  | 442 | 66.3 | 0 | 0 | 0 | 508.3 | OK
| Kick-off meeting | LP | All |  | 12888 | 1933.2 | 4800 | 6000 | 0 | 25621.2 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Project Management and coordination | [9 empty] | OK
| Daily project management | LP | All |  | 48010 | 7201.5 | 0 | 80000 | 3000 | 138211.5 | OK
| Steering Group meeting linked with thematic meeting | LP | All |  | 31295 | 4694.25 | 20400 | 10600 | 0 | 66989.25 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Reporting | [9 empty] | OK
| Internal financial monitoring/budget revision | LP | All |  | 14718 | 2207.7 | 0 | 0 | 0 | 16925.7 | OK
| Preparation of partner level progress report | LP | All |  | 41745 | 6261.75 | 0 | 24550 | 0 | 72556.75 | OK
| Delivery of progress report to JTS | LP | All |  | 15917 | 2387.55 | 0 | 65000 | 0 | 83304.55 | OK
| Delivery of final report to JTS | LP | All |  | 4232 | 634.8 | 0 | 0 | 0 | 4866.8 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 176606 | 26490.9 | 25200 | 186150 | 3000 | 417446.9 | OK
| COMMUNICATION | [9 empty] | OK
| Planning and start-up | [9 empty] | OK
| Communication and knowledge sharing strategy | PP5-VPR | All |  | 2637 | 395.55 | 0 | 0 | 0 | 3032.55 | OK
| Launching event | LP | All |  | 10023 | 1503.45 | 2400 | 12000 | 0 | 25926.45 | OK
| Briefing brochure linked to the Launching event about the project and the topic adressed | PP5-VPR | All |  | 7214 | 1082.1 | 0 | 13000 | 0 | 21296.1 | OK
| Poster (obligatory) | PP5-VPR | All |  | 3424 | 513.6 | 0 | 1800 | 0 | 5737.6 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Website and social media | [9 empty] | OK
| Launching of website and regular update of the website | PP5-VPR | All |  | 14032 | 2104.8 | 0 | 0 | 0 | 16136.8 | OK
| Social media presence | PP5-VPR | All |  | 11018 | 1652.7 | 0 | 0 | 0 | 12670.7 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Paticipation in other events | [9 empty] | OK
| INTERREG Europe events | PP5-VPR, LP- VRW | n.a. |  | 4755 | 713.25 | 4800 | 0 | 0 | 10268.25 | OK
| Dissemination at transnational events (presenter or exhibitioner) | PP5-VPR | All |  | 3711 | 556.65 | 5400 | 0 | 0 | 9667.65 | OK
| Dissemination at national events (presenter or exhibitioner) | PP5-VPR | All |  | 4068 | 610.2 | 3000 | 0 | 0 | 7678.2 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Communication materials/tools | [9 empty] | OK
| Press releases | PP5-VPR | TWG meeting/event organisers |  | 6322 | 948.3 | 0 | 0 | 0 | 7270.3 | OK
| Newsletters on project level | PP5-VPR | All |  | 8060 | 1209 | 0 | 2000 | 0 | 11269 | OK
| Project video | PP5-VPR | All |  | 5186 | 777.9 | 0 | 4000 | 0 | 9963.9 | OK
| Policy learning Synthesis report | LP- VRW, PP5-VPR | All |  | 6606 | 990.9 | 0 | 0 | 0 | 7596.9 | OK
| Dissemination materials on exchanged experience targeting regions outside the partnership | PP4-VPR | All |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Mid term event | PP4-VPR | All partners |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Final event | PP2- TCC | All partners |  | 10061 | 1509.15 | 3000 | 12000 | 0 | 26570.15 | OK
| Visualisation materials for institutional, stakeholder meetings | PP5- VPR | LP, PP2, PP3, PP4, PP5 |  | 12145 | 1821.75 | 0 | 15000 | 0 | 28966.75 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 109262 | 16389.3 | 18600 | 59800 | 0 | 204051.3 | OK
| INTERREGIONAL POLICY LEARNING | [9 empty] | OK
| Interregional thematic organisation | [9 empty] | OK
| Setting up Thematic Working Group (TWG) | LP | All partners |  | 2464 | 369.6 | 0 | 30000 | 0 | 32833.6 | OK
| TWG Rules of procedure | LP | All partners |  | 884 | 132.6 | 0 | 0 | 0 | 1016.6 | OK
| TWG meetings linked to thematic implementation | LP | All partners |  | 31541 | 4731.15 | 20400 | 6600 | 0 | 63272.15 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Stakeholder involvement and organisational learning | [9 empty] | OK
| Setting up stakeholder & institutional learning groups | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 |  | 6269 | 940.35 | 0 | 0 | 0 | 7209.35 | OK
| Interactive training on stakeholder involvement/institutional learning for the Regional Managers | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 |  | 7216 | 1082.4 | 0 | 0 | 0 | 8298.4 | OK
| Methodology for regional Roadmaps | PP2- TCC | All partners |  | 3806 | 570.9 | 0 | 0 | 0 | 4376.9 | OK
| regional Roadmaps (on the institutional/stakeholder involvement process) elaborated and quality controled | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 |  | 19410 | 2911.5 | 0 | 0 | 0 | 22321.5 | OK
| Regional Opening meeting for stakeholders (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 |  | 15730 | 2359.5 | 0 | 10800 | 0 | 28889.5 | OK
| Meetings with stakeholder groups and Institutional learning groups / involvement in action plan implementation + Synergy Sessions with Institutional departments | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 |  | 52625 | 7893.75 | 0 | 20050 | 0 | 80568.75 | OK
| Phase 1 closing stakeholder session (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 |  | 18480 | 2772 | 0 | 8800 | 0 | 30052 | OK
| Synergy session for personnel of partner organisations | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 |  | 17712 | 2656.8 | 0 | 0 | 0 | 20368.8 | OK
| Thematic coordination of stakeholder involvement | PP2- TCC | LP- VRW |  | 7930 | 1189.5 | 0 | 0 | 0 | 9119.5 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Analysis | [9 empty] | OK
| Joint methodology for regional State of Arts | PP4 - PD | All partners |  | 2662 | 399.3 | 0 | 0 | 0 | 3061.3 | OK
| Regional State of Arts (including good practice inventory + list of ingredients for change) | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 |  | 39090 | 5863.5 | 0 | 10000 | 0 | 54953.5 | OK
| Transnational audit visits to each region by experts delegated by 2 other partners | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Project level menu of good practices | PP4 - PD | LP- VRW |  | 5962 | 894.3 | 0 | 0 | 0 | 6856.3 | OK
| Thematic coordination of analysis phase | PP4 - PD | LP- VRW |  | 4810 | 721.5 | 0 | 12000 | 0 | 17531.5 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Knowledge exchange (good practice transfer) | [9 empty] | OK
| Guidelines (including matching learning needs with good practices)/methodology and templates for knowledge sharing | LP- VRW | All partners |  | 3957 | 593.55 | 0 | 0 | 0 | 4550.55 | OK
| 3 Transnational Exchange Session meetings of 3 days length (for individual staff members of partners + appr. 3 stakeholders per partner region) | LP- VRW | All partners |  | 57475 | 8621.25 | 22400 | 39800 | 0 | 128296.25 | OK
| Summary reports on the Exchange Sessions | LP- VRW | All partners |  | 8375 | 1256.25 | 0 | 0 | 0 | 9631.25 | OK
| Thematic coordination of knowledge exchange | LP- VRW | n.a. |  | 4420 | 663 | 0 | 0 | 0 | 5083 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Action plan drafting | [9 empty] | OK
| Project level Guideline and joint training on action plan development | PP3 - MCM | All partners |  | 11006 | 1650.9 | 0 | 0 | 0 | 12656.9 | OK
| Detailed Action Plan methodology on regional level/workplan | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Elaboration of Action Plans / policy instrument | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 |  | 39090 | 5863.5 | 0 | 85000 | 0 | 129953.5 | OK
| Cross- reading exercise | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 |  | 6610 | 991.5 | 0 | 0 | 0 | 7601.5 | OK
| Final quality control of Action Plans | PP3 - MCM | n.a. |  | 3789 | 568.35 | 0 | 0 | 0 | 4357.35 | OK
| Consistency check of Action Plans on regional level | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 |  | 3146 | 471.9 | 0 | 0 | 0 | 3617.9 | OK
| Thematic coordination of action planning | PP3 - MCM | LP- VRW |  | 6210 | 931.25 | 0 | 0 | 0 | 7141.25 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Action plan implementation follow-up(24 months) |  |  |  |  | 0 |  |  |  |  | OK
| Monitoring of the implementation of the action plans | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 |  | 15786 | 2367.8 | 0 | 0 | 0 | 18153.8 | OK
| Summary on the level of achievements / policy instrument | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 |  | 6146 | 920.9 | 0 | 0 | 0 | 7066.9 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 402601 | 60388.8 | 42800 | 223050 | 0 | 728839.8 | OK
| TOTAL |  |  |  | 688469 | 103269 | 86600 | 484000 | 3000 | 1365338 | OK
[5 empty] | OK | OK | OK | OK | OK | OK | OK
| Application Form budget |  |  |  | Staff | Overhead | T & A | External expertise | Equip. | TOTAL |  | ERDF | 1160537.3
|  |  | TOTAL |  | 688469 | 103269 | 86600 | 484000 | 3000 | 1365338 |  | Co-finance | 204800.7
[12 empty] | TOTAL | 1365338
| Application Form budget - Spending Forecast | Period | Budget | % | Rounded |  | Application Form budget - External expertise | Type of cost |  | Budget |  |  | OK
|  | Preparation | 15000 | 1.099% | 15000 |  |  | FLC cost |  | 24550
|  | Semester 1 | 137340.0994 | 10.06% | 137341 |  |  | Project/financial/comm. management |  | 145000
|  | Semester 2 | 223983.6939 | 16.4% | 223984 |  |  | Meetings: partner meeting |  | 34200
|  | Semester 3 | 264810.5889 | 19.4% | 264810 |  |  | Meetings: dissemination event |  | 24000
|  | Semester 4 | 289698.1564 | 21.22% | 289698 |  |  |  |  | 0
|  | Semester 5 | 270596.4364 | 19.82% | 270597 |  |  | Meetings: stakeholder group |  | 39650
|  | Semester 6 | 33385.27 | 2.445% | 33386 |  |  | Travel & acc. cost: non staff |  | 28800
|  | Semester 7 | 27324.7024 | 2.001% | 27324 |  |  | Publication and dissemination costs |  | 35800
|  | Semester 8 | 36918.02 | 2.704% | 36918 |  |  | External support for the exc. of experience |  | 137000
|  | Semester 9 | 66281.0324 | 4.855% | 66280 |  |  | Other |  | 15000
|  |  | 0 | 0 |  |  |  | TOTAL |  | 484000
|  | TOTAL | 1365338 | 1 | 1365338 |  |  |  |  | OK
|  |  | OK |  | OK
| % check tables | Budget lines | % |  |  |  | Application Form budget - Equipment | Type of cost |  | Budget
|  | Staff | 50.42% |  |  |  |  | Office eqiupment |  | 3000
|  | Overhead | 7.564% |  |  |  |  | Other
|  | T & A | 6.343% |  |  |  |  | TOTAL |  | 3000
|  | Ext. expertise | 35.45% | [6 empty] | OK
|  | Eqipment | 0.2197%
|  | TOTAL | 100% |  |  |  | % check partnership | Partner | Budget | %
[8 empty] | LP - VRW (NL) | 449994 | 32.96% |  | 576071
|  | CP | % |  |  |  |  | PP1 - TCC (IE) | 258825 | 18.96% |  | 707093
|  | Management CP | 31.67% |  |  |  |  | PP2 - MMC (IT) | 215200 | 15.76% |  | 131022
|  | Communication CP | 14.95% |  |  |  |  | PP3 - Pons D. (SK) | 153732 | 11.26%
|  | Thematic CP | 53.38% |  |  |  |  | PP4 - VPR (LV) | 161510 | 11.83%
|  | TOTAL | 100% |  |  |  |  | PP5 - PSH (NL) | 126077 | 9.234% | 42.19%
[8 empty] | TOTAL | 1365338 | 100%
OK
Original budget
[7 empty] | % check partnership | Partner | Budget | %
[8 empty] | LP - VRW (NL) | 526115 | 33.68%
[8 empty] | PP1 - TCC (IE) | 271432 | 17.38%
[8 empty] | PP2 - MMC (IT) | 227380 | 14.56%
[8 empty] | PP3 - Pons D. (SK) | 167767 | 10.74%
[8 empty] | PP4 - VPR (LV) | 188414 | 12.06%
[8 empty] | PP5 - PSH (NL) | 180978 | 11.59%
[8 empty] | TOTAL | 1562086 | 100%
|  | Austria | 262
|  | Belgium | 278
|  | Czech Republic | 118
|  | Denmark | 280
|  | Estonia | 110
|  | Finland | 232
|  | France | 233
|  | Germany | 253
|  | Greece | 148
|  | Hungary | 121
|  | Ireland | 286
|  | Italy | 200
|  | Netherlands | 275
|  | Poland | 131
|  | Portugal | 137
|  | Slovak Republic | 118
|  | Slovenia | 185
|  | Spain | 202
|  | Sweden | 236
|  | United Kingdom | 238
|  | Bulgaria | 80
|  | Croatia | 100
|  | Cyprus | 120
|  | Latvia | 104
|  | Lithuania | 100
|  | Luxemburg | 324
|  | Malta | 140
|  | Romania | 80
|  | ERDF | 75%
|  | ERDF | 85%

## LP_VRW
LP - VRW |  |  |  | Country --> | [5 empty] | Netherlands |  |  | Semester 1 (month 1-6) | [6 empty] | Semester 2 (month 7-12) | [6 empty] | Semester 3 (month 13-18) | [6 empty] | Semester 4 (month 19-24) | [6 empty] | Semester 5 (month 25-30) | [6 empty] | Semester 6 (month 31-36) | [6 empty] | Semester 7 (month 37-42) | [6 empty] | Semester 8 (month 43-48) | [6 empty] | Semester 9 (month 49-54) | [6 empty] | TOTAL
DAILY FEE |  | 221 |  |  | Travel cost 1 person 2 nights |  |  | 600 | ERDF | 0.85
[5 empty] | Travel cost 1 person 3 nights |  |  | 800
449994
Action | ACTIVITIES | Partner in charge | Participating
|  |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL
|  |  |  | days | total | [7 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total
| PREPARATION | LP
| Project proposal preparation |  |  |  | 0 | 0 |  | 15000 |  | 15000 | OK |  |  | 0 | 0 |  | 15000 |  | 15000 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 15000 | 0 | 15000 | OK
| TOTAL |  |  |  | 0 | 0 | 0 | 15000 | 0 | 15000 | OK |  |  | 0 | 0 | 0 | 15000 | 0 | 15000 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 15000 | 0 | 15000 | OK
| PROJECT MANAGEMENT AND COORDINATION | LP | [8 empty] | OK | [71 empty] | OK
| Contractualisation and start-up | [9 empty] | OK | [71 empty] | OK
| Subsidy Contract | LP | All | 2 | 442 | 66.3 |  |  |  | 508.3 | OK |  |  | 442 | 66.3 |  |  |  | 508.3 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 442 | 66.3 | 0 | 0 | 0 | 508.3 | OK
| Partnership Agreement | LP | All | 5 | 1105 | 165.75 |  |  |  | 1270.75 | OK |  |  | 1105 | 165.75 |  |  |  | 1270.75 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1105 | 165.75 | 0 | 0 | 0 | 1270.75 | OK
| Appointment FLC | LP | All | 2 | 442 | 66.3 |  |  |  | 508.3 | OK |  |  | 442 | 66.3 |  |  |  | 508.3 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 442 | 66.3 | 0 | 0 | 0 | 508.3 | OK
| Management and financial handbook | LP | All | 4 | 884 | 132.6 |  |  |  | 1016.6 | OK |  |  | 884 | 132.6 |  |  |  | 1016.6 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 884 | 132.6 | 0 | 0 | 0 | 1016.6 | OK
| Rules of Procedures for the PR | LP | All | 2 | 442 | 66.3 |  |  |  | 508.3 | OK |  |  | 442 | 66.3 |  |  |  | 508.3 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 442 | 66.3 | 0 | 0 | 0 | 508.3 | OK
| Rules of Procedures for the SG | LP | All | 2 | 442 | 66.3 |  |  |  | 508.3 | OK |  |  | 442 | 66.3 |  |  |  | 508.3 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 442 | 66.3 | 0 | 0 | 0 | 508.3 | OK
| Kick-off meeting | LP | All | 20 | 4800 | 720 |  | 6000 |  | 11520 | OK |  |  | 4800 | 720 | 0 | 6000 |  | 11520 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4800 | 720 | 0 | 6000 | 0 | 11520 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Project Management and coordination | [9 empty] | OK | [71 empty] | OK
| Daily project management | LP | All | 80 | 17680 | 2652 |  | 65000 | 3000 | 88332 | OK |  |  | 2652 | 397.8 |  | 9750 | 3000 | 15799.8 |  | 884 | 132.6 |  | 6500 |  | 7516.6 |  | 5304 | 795.6 |  | 16250 |  | 22349.6 |  | 3536 | 530.4 |  | 13000 |  | 17066.4 |  | 5304 | 795.6 |  | 13000 |  | 19099.6 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 6500 |  | 6500 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 17680 | 2652 | 0 | 65000 | 3000 | 88332 | OK
| Steering Group meeting linked with thematic meeting | LP | All | 40 | 8840 | 1326 | 3600 |  |  | 13766 | OK |  |  | 176.8 | 26.52 | 514.2857 |  |  | 717.6057 |  | 884 | 132.6 | 514.2857 |  |  | 1530.8857 |  | 2652 | 397.8 | 514.2857 |  |  | 3564.0857 |  | 2652 | 397.8 | 514.2857 |  |  | 3564.0857 |  | 1768 | 265.2 | 514.2857 |  |  | 2547.4857 |  |  | 0 |  |  |  | 0 |  | 353.6 | 53.04 | 514.2857 |  |  | 920.9257 |  |  | 0 |  |  |  | 0 |  | 353.6 | 53.04 | 514.2857 |  |  | 920.9257 |  | 8840 | 1326 | 3600 | 0 | 0 | 13766 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Reporting | [9 empty] | OK | [71 empty] | OK
| Internal financial monitoring/budget revision | LP | All | 30 | 6630 | 994.5 |  |  |  | 7624.5 | OK |  |  | 663 | 99.45 |  |  |  | 762.45 |  | 663 | 99.45 |  |  |  | 762.45 |  | 1326 | 198.9 |  |  |  | 1524.9 |  | 2652 | 397.8 |  |  |  | 3049.8 |  | 1326 | 198.9 |  |  |  | 1524.9 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 6630 | 994.5 | 0 | 0 | 0 | 7624.5 | OK
| Preparation of partner level progress report | LP | All | 35 | 7735 | 1160.25 |  | 8400 |  | 17295.25 | OK |  |  |  | 0 |  |  |  | 0 |  | 773.5 | 116.025 |  | 1260 |  | 2149.525 |  | 1160.25 | 174.0375 |  | 1260 |  | 2594.2875 |  | 1547 | 232.05 |  | 1260 |  | 3039.05 |  | 1160.25 | 174.0375 |  | 1260 |  | 2594.2875 |  | 1160.25 | 174.0375 |  | 1260 |  | 2594.2875 |  |  | 0 |  |  |  | 0 |  | 1160.25 | 174.0375 |  | 1260 |  | 2594.2875 |  | 773.5 | 116.025 |  | 840 |  | 1729.525 |  | 7735 | 1160.25 | 0 | 8400 | 0 | 17295.25 | OK
| Delivery of progress report to JTS | LP | All | 40 | 8840 | 1326 |  | 65000 |  | 75166 | OK |  |  |  | 0 |  |  |  | 0 |  | 884 | 132.6 |  | 9750 |  | 10766.6 |  | 1326 | 198.9 |  | 9750 |  | 11274.9 |  | 1768 | 265.2 |  | 9750 |  | 11783.2 |  | 1326 | 198.9 |  | 9750 |  | 11274.9 |  | 1326 | 198.9 |  | 9750 |  | 11274.9 |  |  | 0 |  |  |  | 0 |  | 1326 | 198.9 |  | 9750 |  | 11274.9 |  | 884 | 132.6 |  | 6500 |  | 7516.6 |  | 8840 | 1326 | 0 | 65000 | 0 | 75166 | OK
| Delivery of final report to JTS | LP | All | 10 | 2210 | 331.5 |  |  |  | 2541.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2210 | 331.5 |  |  |  | 2541.5 |  | 2210 | 331.5 | 0 | 0 | 0 | 2541.5 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 60492 | 9073.8 | 3600 | 144400 | 3000 | 220565.8 | OK |  |  | 12048.8 | 1807.32 | 514.2857 | 15750 | 3000 | 33120.4057 |  | 4088.5 | 613.275 | 514.2857 | 17510 | 0 | 22726.0607 |  | 11768.25 | 1765.2375 | 514.2857 | 27260 | 0 | 41307.7732 |  | 12155 | 1823.25 | 514.2857 | 24010 | 0 | 38502.5357 |  | 10884.25 | 1632.6375 | 514.2857 | 24010 | 0 | 37041.1732 |  | 2486.25 | 372.9375 | 0 | 11010 | 0 | 13869.1875 |  | 353.6 | 53.04 | 514.2857 | 6500 | 0 | 7420.9257 |  | 2486.25 | 372.9375 | 0 | 11010 | 0 | 13869.1875 |  | 4221.1 | 633.165 | 514.2857 | 7340 | 0 | 12708.5507 |  | 60492 | 9073.8 | 3600 | 144400 | 3000 | 220565.8 | OK
| COMMUNICATION | [9 empty] | OK | [71 empty] | OK
| Planning and start-up | [9 empty] | OK | [71 empty] | OK
| Communication and knowledge sharing strategy | PP5-VPR | All | 1 | 221 | 33.15 |  |  |  | 254.15 | OK |  |  | 221 | 33.15 |  |  |  | 254.15 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 221 | 33.15 | 0 | 0 | 0 | 254.15 | OK
| Launching event | LP | All | 30 | 6630 | 994.5 |  | 12000 |  | 19624.5 | OK |  |  | 4641 | 696.15 | 0 | 6000 |  | 11337.15 |  | 1989 | 298.35 |  | 6000 |  | 8287.35 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 6630 | 994.5 | 0 | 12000 | 0 | 19624.5 | OK
| Briefing brochure linked to the Launching event about the project and the topic adressed | PP5-VPR | All | 10 | 2210 | 331.5 |  |  |  | 2541.5 | OK |  |  | 1547 | 232.05 |  |  |  | 1779.05 |  | 663 | 99.45 |  | 0 |  | 762.45 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2210 | 331.5 | 0 | 0 | 0 | 2541.5 | OK
| Poster (obligatory) | PP5-VPR | All | 2 | 442 | 66.3 |  | 300 |  | 808.3 | OK |  |  | 442 | 66.3 |  | 300 |  | 808.3 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 442 | 66.3 | 0 | 300 | 0 | 808.3 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Website and social media | [9 empty] | OK | [71 empty] | OK
| Launching of website and regular update of the website | PP5-VPR | All | 20 | 4420 | 663 |  |  |  | 5083 | OK |  |  | 442 | 66.3 |  |  |  | 508.3 |  | 221 | 33.15 |  |  |  | 254.15 |  | 884 | 132.6 |  |  |  | 1016.6 |  | 1105 | 165.75 |  |  |  | 1270.75 |  | 884 | 132.6 |  |  |  | 1016.6 |  | 221 | 33.15 |  |  |  | 254.15 |  | 221 | 33.15 |  |  |  | 254.15 |  | 221 | 33.15 |  |  |  | 254.15 |  | 221 | 33.15 |  |  |  | 254.15 |  | 4420 | 663 | 0 | 0 | 0 | 5083 | OK
| Social media presence | PP5-VPR | All | 20 | 4420 | 663 |  |  |  | 5083 | OK |  |  | 442 | 66.3 |  |  |  | 508.3 |  | 221 | 33.15 |  |  |  | 254.15 |  | 884 | 132.6 |  |  |  | 1016.6 |  | 1105 | 165.75 |  |  |  | 1270.75 |  | 884 | 132.6 |  |  |  | 1016.6 |  | 221 | 33.15 |  |  |  | 254.15 |  | 221 | 33.15 |  |  |  | 254.15 |  | 221 | 33.15 |  |  |  | 254.15 |  | 221 | 33.15 |  |  |  | 254.15 |  | 4420 | 663 | 0 | 0 | 0 | 5083 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Paticipation in other events | [9 empty] | OK | [71 empty] | OK
| INTERREG Europe events | PP5-VPR, LP- VRW | n.a. | 15 | 3315 | 497.25 | 3000 |  |  | 6812.25 | OK |  |  | 331.5 | 49.725 | 300 |  |  | 681.225 |  | 331.5 | 49.725 | 300 |  |  | 681.225 |  | 331.5 | 49.725 | 300 |  |  | 681.225 |  | 331.5 | 49.725 | 300 |  |  | 681.225 |  | 663 | 99.45 | 600 |  |  | 1362.45 |  | 331.5 | 49.725 | 300 |  |  | 681.225 |  | 331.5 | 49.725 | 300 |  |  | 681.225 |  | 331.5 | 49.725 | 300 |  |  | 681.225 |  | 331.5 | 49.725 | 300 |  |  | 681.225 |  | 3315 | 497.25 | 3000 | 0 | 0 | 6812.25 | OK
| Dissemination at transnational events (presenter or exhibitioner) | PP5-VPR | All | 3 | 663 | 99.45 | 1800 |  |  | 2562.45 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 663 | 99.45 | 1800 |  |  | 2562.45 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 663 | 99.45 | 1800 | 0 | 0 | 2562.45 | OK
| Dissemination at national events (presenter or exhibitioner) | PP5-VPR | All | 4 | 884 | 132.6 | 600 |  |  | 1616.6 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 442 | 66.3 | 300 |  |  | 808.3 |  | 442 | 66.3 | 300 |  |  | 808.3 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 884 | 132.6 | 600 | 0 | 0 | 1616.6 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Communication materials/tools | [9 empty] | OK | [71 empty] | OK
| Press releases | PP5-VPR | TWG meeting/event organisers | 4 | 884 | 132.6 |  |  |  | 1016.6 | OK |  |  |  | 0 |  |  |  | 0 |  | 221 | 33.15 |  |  |  | 254.15 |  | 221 | 33.15 |  |  |  | 254.15 |  | 221 | 33.15 |  |  |  | 254.15 |  | 221 | 33.15 |  |  |  | 254.15 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 884 | 132.6 | 0 | 0 | 0 | 1016.6 | OK
| Newsletters on project level | PP5-VPR | All | 5 | 1105 | 165.75 |  |  |  | 1270.75 | OK |  |  |  | 0 |  |  |  | 0 |  | 276.25 | 41.4375 |  | 0 |  | 317.6875 |  | 276.25 | 41.4375 |  |  |  | 317.6875 |  | 276.25 | 41.4375 |  |  |  | 317.6875 |  | 276.25 | 41.4375 |  |  |  | 317.6875 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1105 | 165.75 | 0 | 0 | 0 | 1270.75 | OK
| Project video | PP5-VPR | All | 3 | 663 | 99.45 |  |  |  | 762.45 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 663 | 99.45 |  | 0 |  | 762.45 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 663 | 99.45 | 0 | 0 | 0 | 762.45 | OK
| Policy learning Synthesis report | LP- VRW, PP5-VPR | All | 15 | 3315 | 497.25 |  |  |  | 3812.25 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3315 | 497.25 |  |  |  | 3812.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3315 | 497.25 | 0 | 0 | 0 | 3812.25 | OK
| Dissemination materials on exchanged experience targeting regions outside the partnership | PP4-VPR | All |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Mid term event | PP4-VPR | All partners |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Final event | PP2- TCC | All partners | 6 | 1326 | 198.9 | 600 |  |  | 2124.9 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1326 | 198.9 | 600 | 0 |  | 2124.9 |  | 1326 | 198.9 | 600 | 0 | 0 | 2124.9 | OK
| Visualisation materials for institutional, stakeholder meetings | PP5- VPR | LP, PP2, PP3, PP4, PP5 | 10 | 2210 | 331.5 |  |  |  | 2541.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 1105 | 165.75 |  | 0 |  | 1270.75 |  | 552.5 | 82.875 |  |  |  | 635.375 |  | 552.5 | 82.875 |  |  |  | 635.375 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2210 | 331.5 | 0 | 0 | 0 | 2541.5 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 32708 | 4906.2 | 6000 | 12300 | 0 | 55914.2 | OK |  |  | 8066.5 | 1209.975 | 300 | 6300 | 0 | 15876.475 |  | 3922.75 | 588.4125 | 300 | 6000 | 0 | 10811.1625 |  | 3701.75 | 555.2625 | 300 | 0 | 0 | 4557.0125 |  | 4696.25 | 704.4375 | 2400 | 0 | 0 | 7800.6875 |  | 7900.75 | 1185.1125 | 900 | 0 | 0 | 9985.8625 |  | 773.5 | 116.025 | 300 | 0 | 0 | 1189.525 |  | 773.5 | 116.025 | 300 | 0 | 0 | 1189.525 |  | 773.5 | 116.025 | 300 | 0 | 0 | 1189.525 |  | 2099.5 | 314.925 | 900 | 0 | 0 | 3314.425 |  | 32708 | 4906.2 | 6000 | 12300 | 0 | 55914.2 | OK
| INTERREGIONAL POLICY LEARNING | [9 empty] | OK | [71 empty] | OK
| Interregional thematic organisation | [9 empty] | OK | [71 empty] | OK
| Setting up Thematic Working Group (TWG) | LP | All partners | 2 | 442 | 66.3 |  | 30000 |  | 30508.3 | OK |  |  | 442 | 66.3 |  | 6000 |  | 6508.3 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 6000 |  | 6000 |  |  | 0 |  | 6000 |  | 6000 |  |  | 0 |  | 6000 |  | 6000 |  |  | 0 |  | 3000 |  | 3000 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 3000 |  | 3000 |  |  | 0 |  |  |  | 0 |  | 442 | 66.3 | 0 | 30000 | 0 | 30508.3 | OK
| TWG Rules of procedure | LP | All partners | 4 | 884 | 132.6 |  |  |  | 1016.6 | OK |  |  | 884 | 132.6 |  |  |  | 1016.6 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 884 | 132.6 | 0 | 0 | 0 | 1016.6 | OK
| TWG meetings linked to thematic implementation | LP | All partners | 30 | 6630 | 994.5 | 3600 |  |  | 11224.5 | OK |  |  | 132.6 | 19.89 | 514.2857 |  |  | 666.7757 |  | 663 | 99.45 | 514.2857 |  |  | 1276.7357 |  | 1989 | 298.35 | 514.2857 |  |  | 2801.6357 |  | 1989 | 298.35 | 514.2857 |  |  | 2801.6357 |  | 1326 | 198.9 | 514.2857 |  |  | 2039.1857 |  |  | 0 |  |  |  | 0 |  | 265.2 | 39.78 | 514.2857 |  |  | 819.2657 |  |  | 0 |  |  |  | 0 |  | 265.2 | 39.78 | 514.2857 |  |  | 819.2657 |  | 6630 | 994.5 | 3600 | 0 | 0 | 11224.5 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Stakeholder involvement and organisational learning | [9 empty] | OK | [71 empty] | OK
| Setting up stakeholder & institutional learning groups | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 4 | 884 | 132.6 |  |  |  | 1016.6 | OK |  |  | 618.8 | 92.82 |  |  |  | 711.62 |  | 265.2 | 39.78 |  |  |  | 304.98 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 884 | 132.6 | 0 | 0 | 0 | 1016.6 | OK
| Interactive training on stakeholder involvement/institutional learning for the Regional Managers | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 4 | 884 | 132.6 |  |  |  | 1016.6 | OK |  |  | 442 | 66.3 |  |  |  | 508.3 |  | 442 | 66.3 |  |  |  | 508.3 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 884 | 132.6 | 0 | 0 | 0 | 1016.6 | OK
| Methodology for regional Roadmaps | PP2- TCC | All partners | 1 | 221 | 33.15 |  |  |  | 254.15 | OK |  |  | 221 | 33.15 |  |  |  | 254.15 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 221 | 33.15 | 0 | 0 | 0 | 254.15 | OK
| regional Roadmaps (on the institutional/stakeholder involvement process) elaborated and quality controled | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 3315 | 497.25 |  |  |  | 3812.25 | OK |  |  | 994.5 | 149.175 |  |  |  | 1143.675 |  | 2320.5 | 348.075 |  |  |  | 2668.575 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3315 | 497.25 | 0 | 0 | 0 | 3812.25 | OK
| Regional Opening meeting for stakeholders (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 3315 | 497.25 |  | 4000 |  | 7812.25 | OK |  |  | 994.5 | 149.175 |  |  |  | 1143.675 |  | 2320.5 | 348.075 | 0 | 4000 |  | 6668.575 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3315 | 497.25 | 0 | 4000 | 0 | 7812.25 | OK
| Meetings with stakeholder groups and Institutional learning groups / involvement in action plan implementation + Synergy Sessions with Institutional departments | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 40 | 8840 | 1326 |  | 4500 |  | 14666 | OK |  |  |  | 0 |  |  |  | 0 |  | 884 | 132.6 |  | 450 |  | 1466.6 |  | 2210 | 331.5 |  | 1125 |  | 3666.5 |  | 3536 | 530.4 |  | 1800 |  | 5866.4 |  | 2210 | 331.5 |  | 1125 |  | 3666.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 8840 | 1326 | 0 | 4500 | 0 | 14666 | OK
| Phase 1 closing stakeholder session (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 3315 | 497.25 |  |  |  | 3812.25 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3315 | 497.25 | 0 | 0 |  | 3812.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3315 | 497.25 | 0 | 0 | 0 | 3812.25 | OK
| Synergy session for personnel of partner organisations | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 9 | 1989 | 298.35 |  |  |  | 2287.35 | OK |  |  |  | 0 |  |  |  | 0 |  | 497.25 | 74.5875 |  |  |  | 571.8375 |  | 497.25 | 74.5875 |  |  |  | 571.8375 |  | 497.25 | 74.5875 |  |  |  | 571.8375 |  | 497.25 | 74.5875 |  |  |  | 571.8375 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1989 | 298.35 | 0 | 0 | 0 | 2287.35 | OK
| Thematic coordination of stakeholder involvement | PP2- TCC | LP- VRW | 10 | 2210 | 331.5 |  |  |  | 2541.5 | OK |  |  |  | 0 |  |  |  | 0 |  | 221 | 33.15 |  |  |  | 254.15 |  | 663 | 99.45 |  |  |  | 762.45 |  | 663 | 99.45 |  |  |  | 762.45 |  | 663 | 99.45 |  |  |  | 762.45 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2210 | 331.5 | 0 | 0 | 0 | 2541.5 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Analysis | [9 empty] | OK | [71 empty] | OK
| Joint methodology for regional State of Arts | PP4 - PD | All partners | 1 | 221 | 33.15 |  |  |  | 254.15 | OK |  |  |  | 0 |  |  |  | 0 |  | 221 | 33.15 |  |  |  | 254.15 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 221 | 33.15 | 0 | 0 | 0 | 254.15 | OK
| Regional State of Arts (including good practice inventory + list of ingredients for change) | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 | 25 | 5525 | 828.75 |  |  |  | 6353.75 | OK |  |  |  | 0 |  |  |  | 0 |  | 5525 | 828.75 | 0 | 0 |  | 6353.75 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 5525 | 828.75 | 0 | 0 | 0 | 6353.75 | OK
| Transnational audit visits to each region by experts delegated by 2 other partners | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Project level menu of good practices | PP4 - PD | LP- VRW | 3 | 663 | 99.45 |  |  |  | 762.45 | OK |  |  |  | 0 |  |  |  | 0 |  | 663 | 99.45 |  |  |  | 762.45 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 663 | 99.45 | 0 | 0 | 0 | 762.45 | OK
| Thematic coordination of analysis phase | PP4 - PD | LP- VRW | 10 | 2210 | 331.5 |  |  |  | 2541.5 | OK |  |  |  | 0 |  |  |  | 0 |  | 2210 | 331.5 | 0 | 0 |  | 2541.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2210 | 331.5 | 0 | 0 | 0 | 2541.5 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Knowledge exchange (good practice transfer) | [9 empty] | OK | [71 empty] | OK
| Guidelines (including matching learning needs with good practices)/methodology and templates for knowledge sharing | LP- VRW | All partners | 10 | 2210 | 331.5 |  |  |  | 2541.5 | OK |  |  |  | 0 |  |  |  | 0 |  | 2210 | 331.5 |  |  |  | 2541.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2210 | 331.5 | 0 | 0 | 0 | 2541.5 | OK
| 3 Transnational Exchange Session meetings of 3 days length (for individual staff members of partners + appr. 3 stakeholders per partner region) | LP- VRW | All partners | 50 | 11050 | 1657.5 | 3200 | 2400 |  | 18307.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 7735 | 1160.25 | 2240 | 1680 |  | 12815.25 |  | 3315 | 497.25 | 960 | 720 |  | 5492.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 11050 | 1657.5 | 3200 | 2400 | 0 | 18307.5 | OK
| Summary reports on the Exchange Sessions | LP- VRW | All partners | 20 | 4420 | 663 |  |  |  | 5083 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3094 | 464.1 |  |  |  | 3558.1 |  | 1326 | 198.9 |  |  |  | 1524.9 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4420 | 663 | 0 | 0 | 0 | 5083 | OK
| Thematic coordination of knowledge exchange | LP- VRW | n.a. | 20 | 4420 | 663 |  |  |  | 5083 | OK |  |  |  | 0 |  |  |  | 0 |  | 884 | 132.6 |  |  |  | 1016.6 |  | 2652 | 397.8 |  |  |  | 3049.8 |  | 884 | 132.6 |  |  |  | 1016.6 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4420 | 663 | 0 | 0 | 0 | 5083 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Action plan drafting | [9 empty] | OK | [71 empty] | OK
| Project level Guideline and joint training on action plan development | PP3 - MCM | All partners | 8 | 1768 | 265.2 |  |  |  | 2033.2 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1768 | 265.2 |  |  |  | 2033.2 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1768 | 265.2 | 0 | 0 | 0 | 2033.2 | OK
| Detailed Action Plan methodology on regional level/workplan | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 0 | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Elaboration of Action Plans / policy instrument | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 25 | 5525 | 828.75 |  | 15000 |  | 21353.75 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2762.5 | 414.375 |  | 7500 |  | 10676.875 |  | 2762.5 | 414.375 |  | 7500 |  | 10676.875 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 5525 | 828.75 | 0 | 15000 | 0 | 21353.75 | OK
| Cross- reading exercise | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 5 | 1105 | 165.75 |  |  |  | 1270.75 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1105 | 165.75 |  |  |  | 1270.75 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1105 | 165.75 | 0 | 0 | 0 | 1270.75 | OK
| Final quality control of Action Plans | PP3 - MCM | n.a. | 2 | 442 | 66.3 |  |  |  | 508.3 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 442 | 66.3 |  |  |  | 508.3 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 442 | 66.3 | 0 | 0 | 0 | 508.3 | OK
| Consistency check of Action Plans on regional level | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 3 | 663 | 99.45 |  |  |  | 762.45 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 663 | 99.45 |  |  |  | 762.45 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 663 | 99.45 | 0 | 0 | 0 | 762.45 | OK
| Thematic coordination of action planning | PP3 - MCM | LP- VRW | 10 | 2210 | 331.25 |  |  |  | 2541.25 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1105 | 165.75 |  |  |  | 1270.75 |  | 1105 | 165.5 |  |  |  | 1270.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2210 | 331.25 | 0 | 0 | 0 | 2541.25 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Action plan implementation follow-up(24 months) |  |  |  |  | 0 |  |  |  |  | OK |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 |  |  |  |  | OK
| Monitoring of the implementation of the action plans | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 24 | 5304 | 795.6 |  |  |  | 6099.6 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1326 | 198.9 |  |  |  | 1524.9 |  | 1326 | 198.9 |  |  |  | 1524.9 |  | 1326 | 198.9 |  |  |  | 1524.9 |  | 1326 | 198.9 |  |  |  | 1524.9 |  | 5304 | 795.6 | 0 | 0 | 0 | 6099.6 | OK
| Summary on the level of achievements / policy instrument | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 12 | 2652 | 397.5 |  |  |  | 3049.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1326 | 198.6 |  |  |  | 1524.6 |  | 1326 | 198.9 |  |  |  | 1524.9 |  | 2652 | 397.5 | 0 | 0 | 0 | 3049.5 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[11 empty] | OK | [71 empty] | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 83317 | 12497 | 6800 | 55900 | 0 | 158514 | OK |  |  | 4729.4 | 709.41 | 514.2857 | 6000 | 0 | 11953.0957 |  | 19326.45 | 2898.9675 | 514.2857 | 4450 | 0 | 27189.7032 |  | 18840.25 | 2826.0375 | 2754.2857 | 8805 | 0 | 33225.5732 |  | 17845.75 | 2676.8625 | 1474.2857 | 16020 | 0 | 38016.8982 |  | 14088.75 | 2113.0625 | 514.2857 | 14625 | 0 | 31341.0982 |  | 1326 | 198.9 | 0 | 3000 | 0 | 4524.9 |  | 1591.2 | 238.68 | 514.2857 | 0 | 0 | 2344.1657 |  | 2652 | 397.5 | 0 | 3000 | 0 | 6049.5 |  | 2917.2 | 437.58 | 514.2857 | 0 | 0 | 3869.0657 |  | 83317 | 12497 | 6800 | 55900 | 0 | 158514 | OK
| TOTAL |  |  |  | 176517 | 26477 | 16400 | 227600 | 3000 | 449994 | OK |  |  | 24844.7 | 3726.705 | 1328.5714 | 43050 | 3000 | 60949.9764 |  | 27337.7 | 4100.655 | 1328.5714 | 27960 | 0 | 60726.9264 |  | 34310.25 | 5146.5375 | 3568.5714 | 36065 | 0 | 79090.3589 |  | 34697 | 5204.55 | 4388.5714 | 40030 | 0 | 84320.1214 |  | 32873.75 | 4930.8125 | 1928.5714 | 38635 | 0 | 78368.1339 |  | 4585.75 | 687.8625 | 300 | 14010 | 0 | 19583.6125 |  | 2718.3 | 407.745 | 1328.5714 | 6500 | 0 | 10954.6164 |  | 5911.75 | 886.4625 | 300 | 14010 | 0 | 21108.2125 |  | 9237.8 | 1385.67 | 1928.5714 | 7340 | 0 | 19892.0414 |  | 176517 | 26477 | 16400 | 227600 | 3000 | 449994 | OK
[5 empty] | OK | OK | OK | OK | OK | OK | OK |  |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK
| Application Form budget |  |  |  | Staff | Overhead | T & A | External expertise | Equip. | TOTAL |  | ERDF | 382494.9
|  |  | LP - VRW |  | 176517 | 26477 | 16400 | 227600 | 3000 | 449994 |  | Co-finance | 67499.1
[12 empty] | TOTAL | 449994
| Application Form budget - Spending Forecast | Period | Budget | % | Rounded |  | Application Form budget - External expertise | Type of cost |  | Budget |  |  | OK
|  | Preparation | 15000 | 3.333% | 15000 |  |  | FLC cost |  | 8400
|  | Semester 1 | 60949.9764 | 13.54% | 60950 |  |  | Project/financial/comm. management |  | 130000
|  | Semester 2 | 60726.9264 | 13.5% | 60727 |  |  | Meetings: partner meeting |  | 6000
|  | Semester 3 | 79090.3589 | 17.58% | 79090 |  |  | Meetings: dissemination event |  | 12000
|  | Semester 4 | 84320.1214 | 18.74% | 84320 |  |  |  |  | 0
|  | Semester 5 | 78368.1339 | 17.42% | 78368 |  |  | Meetings: stakeholder group |  | 8500
|  | Semester 6 | 19583.6125 | 4.352% | 19584 |  |  | Travel & acc. cost: non staff |  | 2400
|  | Semester 7 | 10954.6164 | 2.434% | 10955 |  |  | Publication and dissemination costs |  | 300
|  | Semester 8 | 21108.2125 | 4.691% | 21108 |  |  | External support for the exc. of experience |  | 45000
|  | Semester 9 | 19892.0414 | 4.421% | 19892 |  |  | Other |  | 15000
|  |  |  | 0 |  |  |  | TOTAL |  | 227600
|  | TOTAL | 449994 | 1 | 449994 |  |  |  |  | OK
|  |  | OK |  | OK
| % check tables | Budget lines | % |  |  |  | Application Form budget - Equipment | Type of cost |  | Budget
|  | Staff | 39.23% |  |  |  |  | Office eqiupment |  | 3000
|  | Overhead | 5.884% |  |  |  |  | Other
|  | T & A | 3.644% |  |  |  |  | TOTAL |  | 3000
|  | Ext. expertise | 50.58% | [6 empty] | OK
|  | Eqipment | 0.6667%
|  | TOTAL | 100%
|  | CP | %
|  | Management CP | 52.35%
|  | Communication CP | 12.43%
|  | Thematic CP | 35.23%
|  | TOTAL | 100%
|  | Austria | 262
|  | Belgium | 278
|  | Czech Republic | 118
|  | Denmark | 280
|  | Estonia | 110
|  | Finland | 232
|  | France | 233
|  | Germany | 253
|  | Greece | 148
|  | Hungary | 121
|  | Ireland | 286
|  | Italy | 200
|  | Netherlands | 275
|  | Poland | 131
|  | Portugal | 137
|  | Slovak Republic | 118
|  | Slovenia | 185
|  | Spain | 202
|  | Sweden | 236
|  | United Kingdom | 238
|  | Bulgaria | 80
|  | Croatia | 100
|  | Cyprus | 120
|  | Latvia | 104
|  | Lithuania | 100
|  | Luxemburg | 324
|  | Malta | 140
|  | Romania | 80
|  | ERDF | 75%
|  | ERDF | 85%
Note on I20: Tóth Gábor: Organisation of the kick-off meeting to be held in month 2
Note on I23: Tóth Gábor: Day-today project and financial mamagement, reporting, support for the meetings
Note on I28: Tóth Gábor: FLC cost
Note on I29: Tóth Gábor: Day-today project and financial mamagement, reporting, support for the meetings
Note on I36: Tóth Gábor: Organisation of the Launching conference, SG and TWG meeting to be held at month 6
Note on I38: Tóth Gábor: Printing cost of the poster
Note on I56: Tóth Gábor: Non-staff stakeholder travel (2 person)
Note on I64: Tóth Gábor: Support for the overall thematic coordination of the project
Note on I74: Tóth Gábor: Cost for organisieng the meeting (incuding networking activities)
Note on I75: Tóth Gábor: Organisation cost
Note on I84: Tóth Gábor: Organisation cost for hosting the visit
Note on I91: Tóth Gábor: Non-staff stakeholder travel (3 person)
Note on I99: Tóth Gábor: External support for the preparation of the Action Plan

## PP2_TCC
PP2 - TCC |  |  |  | Country --> | [5 empty] | Ireland |  |  | Semester 1 (month 1-6) | [6 empty] | Semester 2 (month 7-12) | [6 empty] | Semester 3 (month 13-18) | [6 empty] | Semester 4 (month 19-24) | [6 empty] | Semester 5 (month 25-30) | [6 empty] | Semester 6 (month 31-36) | [6 empty] | Semester 7 (month 37-42) | [6 empty] | Semester 8 (month 43-48) | [6 empty] | Semester 9 (month 49-54) | [6 empty] | TOTAL
DAILY FEE |  | 286 |  |  | Travel cost 1 person 2 nights |  |  | 600 | ERDF | 0.85
[5 empty] | Travel cost 1 person 3 nights |  |  | 800
258825
Action | ACTIVITIES | Partner in charge | Participating
|  |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL
|  |  |  | days | total | [7 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total
| PREPARATION | LP
| Project proposal preparation |  |  |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | OK |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| PROJECT MANAGEMENT AND COORDINATION | LP | [8 empty] | OK | [71 empty] | OK
| Contractualisation and start-up | [9 empty] | OK | [71 empty] | OK
| Subsidy Contract | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Partnership Agreement | LP | All | 1 | 286 | 42.9 |  |  |  | 328.9 | OK |  |  | 286 | 42.9 |  |  |  | 328.9 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 286 | 42.9 | 0 | 0 | 0 | 328.9 | OK
| Appointment FLC | LP | All | 2 | 572 | 85.8 |  |  |  | 657.8 | OK |  |  | 572 | 85.8 |  |  |  | 657.8 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 572 | 85.8 | 0 | 0 | 0 | 657.8 | OK
| Management and financial handbook | LP | All | 1 | 286 | 42.9 |  |  |  | 328.9 | OK |  |  | 286 | 42.9 |  |  |  | 328.9 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 286 | 42.9 | 0 | 0 | 0 | 328.9 | OK
| Rules of Procedures for the PR | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Rules of Procedures for the SG | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Kick-off meeting | LP | All | 8 | 2288 | 343.2 | 1200 |  |  | 3831.2 | OK |  |  | 2288 | 343.2 | 1200 | 0 |  | 3831.2 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2288 | 343.2 | 1200 | 0 | 0 | 3831.2 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Project Management and coordination | [9 empty] | OK | [71 empty] | OK
| Daily project management | LP | All | 30 | 8580 | 1287 |  |  |  | 9867 | OK |  |  | 1287 | 193.05 |  | 0 | 0 | 1480.05 |  | 429 | 64.35 |  | 0 |  | 493.35 |  | 2574 | 386.1 |  | 0 |  | 2960.1 |  | 1716 | 257.4 |  | 0 |  | 1973.4 |  | 2574 | 386.1 |  | 0 |  | 2960.1 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 8580 | 1287 | 0 | 0 | 0 | 9867 | OK
| Steering Group meeting linked with thematic meeting | LP | All | 30 | 8580 | 1287 | 3000 | 4000 |  | 16867 | OK |  |  | 171.6 | 25.74 | 428.5714 |  |  | 625.9114 |  | 858 | 128.7 | 428.5714 | 4000 |  | 5415.2714 |  | 2574 | 386.1 | 428.5714 |  |  | 3388.6714 |  | 2574 | 386.1 | 428.5714 |  |  | 3388.6714 |  | 1716 | 257.4 | 428.5714 |  |  | 2401.9714 |  |  | 0 |  |  |  | 0 |  | 343.2 | 51.48 | 428.5714 |  |  | 823.2514 |  |  | 0 |  |  |  | 0 |  | 343.2 | 51.48 | 428.5714 |  |  | 823.2514 |  | 8580 | 1287 | 3000 | 4000 | 0 | 16867 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Reporting | [9 empty] | OK | [71 empty] | OK
| Internal financial monitoring/budget revision | LP | All | 8 | 2288 | 343.2 |  |  |  | 2631.2 | OK |  |  | 228.8 | 34.32 |  |  |  | 263.12 |  | 228.8 | 34.32 |  |  |  | 263.12 |  | 457.6 | 68.64 |  |  |  | 526.24 |  | 915.2 | 137.28 |  |  |  | 1052.48 |  | 457.6 | 68.64 |  |  |  | 526.24 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2288 | 343.2 | 0 | 0 | 0 | 2631.2 | OK
| Preparation of partner level progress report | LP | All | 35 | 10010 | 1501.5 |  | 4250 |  | 15761.5 | OK |  |  |  | 0 |  |  |  | 0 |  | 1001 | 150.15 |  | 637.5 |  | 1788.65 |  | 1501.5 | 225.225 |  | 637.5 |  | 2364.225 |  | 2002 | 300.3 |  | 637.5 |  | 2939.8 |  | 1501.5 | 225.225 |  | 637.5 |  | 2364.225 |  | 1501.5 | 225.225 |  | 637.5 |  | 2364.225 |  |  | 0 |  |  |  | 0 |  | 1501.5 | 225.225 |  | 637.5 |  | 2364.225 |  | 1001 | 150.15 |  | 425 |  | 1576.15 |  | 10010 | 1501.5 | 0 | 4250 | 0 | 15761.5 | OK
| Delivery of progress report to JTS | LP | All | 7 | 2002 | 300.3 |  |  |  | 2302.3 | OK |  |  |  | 0 |  |  |  | 0 |  | 200.2 | 30.03 |  | 0 |  | 230.23 |  | 300.3 | 45.045 |  | 0 |  | 345.345 |  | 400.4 | 60.06 |  | 0 |  | 460.46 |  | 300.3 | 45.045 |  | 0 |  | 345.345 |  | 300.3 | 45.045 |  | 0 |  | 345.345 |  |  | 0 |  |  |  | 0 |  | 300.3 | 45.045 |  | 0 |  | 345.345 |  | 200.2 | 30.03 |  | 0 |  | 230.23 |  | 2002 | 300.3 | 0 | 0 | 0 | 2302.3 | OK
| Delivery of final report to JTS | LP | All | 2 | 572 | 85.8 |  |  |  | 657.8 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 572 | 85.8 |  |  |  | 657.8 |  | 572 | 85.8 | 0 | 0 | 0 | 657.8 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 35464 | 5319.6 | 4200 | 8250 | 0 | 53233.6 | OK |  |  | 5119.4 | 767.91 | 1628.5714 | 0 | 0 | 7515.8814 |  | 2717 | 407.55 | 428.5714 | 4637.5 | 0 | 8190.6214 |  | 7407.4 | 1111.11 | 428.5714 | 637.5 | 0 | 9584.5814 |  | 7607.6 | 1141.14 | 428.5714 | 637.5 | 0 | 9814.8114 |  | 6549.4 | 982.41 | 428.5714 | 637.5 | 0 | 8597.8814 |  | 1801.8 | 270.27 | 0 | 637.5 | 0 | 2709.57 |  | 343.2 | 51.48 | 428.5714 | 0 | 0 | 823.2514 |  | 1801.8 | 270.27 | 0 | 637.5 | 0 | 2709.57 |  | 2116.4 | 317.46 | 428.5714 | 425 | 0 | 3287.4314 |  | 35464 | 5319.6 | 4200 | 8250 | 0 | 53233.6 | OK
| COMMUNICATION | [9 empty] | OK | [71 empty] | OK
| Planning and start-up | [9 empty] | OK | [71 empty] | OK
| Communication and knowledge sharing strategy | PP5-VPR | All | 1 | 286 | 42.9 |  |  |  | 328.9 | OK |  |  | 286 | 42.9 |  |  |  | 328.9 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 286 | 42.9 | 0 | 0 | 0 | 328.9 | OK
| Launching event | LP | All | 3 | 858 | 128.7 | 600 |  |  | 1586.7 | OK |  |  | 600.6 | 90.09 | 600 | 0 |  | 1290.69 |  | 257.4 | 38.61 |  | 0 |  | 296.01 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 858 | 128.7 | 600 | 0 | 0 | 1586.7 | OK
| Briefing brochure linked to the Launching event about the project and the topic adressed | PP5-VPR | All | 4 | 1144 | 171.6 |  | 1000 |  | 2315.6 | OK |  |  | 800.8 | 120.12 |  |  |  | 920.92 |  | 343.2 | 51.48 |  | 1000 |  | 1394.68 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1144 | 171.6 | 0 | 1000 | 0 | 2315.6 | OK
| Poster (obligatory) | PP5-VPR | All | 2 | 572 | 85.8 |  | 300 |  | 957.8 | OK |  |  | 572 | 85.8 |  | 300 |  | 957.8 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 572 | 85.8 | 0 | 300 | 0 | 957.8 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Website and social media | [9 empty] | OK | [71 empty] | OK
| Launching of website and regular update of the website | PP5-VPR | All | 7 | 2002 | 300.3 |  |  |  | 2302.3 | OK |  |  | 200.2 | 30.03 |  |  |  | 230.23 |  | 100.1 | 15.015 |  |  |  | 115.115 |  | 400.4 | 60.06 |  |  |  | 460.46 |  | 500.5 | 75.075 |  |  |  | 575.575 |  | 400.4 | 60.06 |  |  |  | 460.46 |  | 100.1 | 15.015 |  |  |  | 115.115 |  | 100.1 | 15.015 |  |  |  | 115.115 |  | 100.1 | 15.015 |  |  |  | 115.115 |  | 100.1 | 15.015 |  |  |  | 115.115 |  | 2002 | 300.3 | 0 | 0 | 0 | 2302.3 | OK
| Social media presence | PP5-VPR | All | 3 | 858 | 128.7 |  |  |  | 986.7 | OK |  |  | 85.8 | 12.87 |  |  |  | 98.67 |  | 42.9 | 6.435 |  |  |  | 49.335 |  | 171.6 | 25.74 |  |  |  | 197.34 |  | 214.5 | 32.175 |  |  |  | 246.675 |  | 171.6 | 25.74 |  |  |  | 197.34 |  | 42.9 | 6.435 |  |  |  | 49.335 |  | 42.9 | 6.435 |  |  |  | 49.335 |  | 42.9 | 6.435 |  |  |  | 49.335 |  | 42.9 | 6.435 |  |  |  | 49.335 |  | 858 | 128.7 | 0 | 0 | 0 | 986.7 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Paticipation in other events | [9 empty] | OK | [71 empty] | OK
| INTERREG Europe events | PP5-VPR, LP- VRW | n.a. |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Dissemination at transnational events (presenter or exhibitioner) | PP5-VPR | All | 3 | 858 | 128.7 | 600 |  |  | 1586.7 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 858 | 128.7 | 600 |  |  | 1586.7 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 858 | 128.7 | 600 | 0 | 0 | 1586.7 | OK
| Dissemination at national events (presenter or exhibitioner) | PP5-VPR | All | 4 | 1144 | 171.6 | 600 |  |  | 1915.6 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 572 | 85.8 | 300 |  |  | 957.8 |  | 572 | 85.8 | 300 |  |  | 957.8 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1144 | 171.6 | 600 | 0 | 0 | 1915.6 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Communication materials/tools | [9 empty] | OK | [71 empty] | OK
| Press releases | PP5-VPR | TWG meeting/event organisers | 8 | 2288 | 343.2 |  |  |  | 2631.2 | OK |  |  |  | 0 |  |  |  | 0 |  | 572 | 85.8 |  |  |  | 657.8 |  | 572 | 85.8 |  |  |  | 657.8 |  | 572 | 85.8 |  |  |  | 657.8 |  | 572 | 85.8 |  |  |  | 657.8 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2288 | 343.2 | 0 | 0 | 0 | 2631.2 | OK
| Newsletters on project level | PP5-VPR | All | 5 | 1430 | 214.5 |  |  |  | 1644.5 | OK |  |  |  | 0 |  |  |  | 0 |  | 357.5 | 53.625 |  | 0 |  | 411.125 |  | 357.5 | 53.625 |  |  |  | 411.125 |  | 357.5 | 53.625 |  |  |  | 411.125 |  | 357.5 | 53.625 |  |  |  | 411.125 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1430 | 214.5 | 0 | 0 | 0 | 1644.5 | OK
| Project video | PP5-VPR | All | 3 | 858 | 128.7 |  |  |  | 986.7 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 858 | 128.7 |  | 0 |  | 986.7 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 858 | 128.7 | 0 | 0 | 0 | 986.7 | OK
| Policy learning Synthesis report | LP- VRW, PP5-VPR | All | 1 | 286 | 42.9 |  |  |  | 328.9 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 286 | 42.9 |  |  |  | 328.9 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 286 | 42.9 | 0 | 0 | 0 | 328.9 | OK
| Dissemination materials on exchanged experience targeting regions outside the partnership | PP4-VPR | All |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Mid term event | PP4-VPR | All partners |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Final event | PP2- TCC | All partners | 20 | 5720 | 858 |  | 12000 |  | 18578 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 5720 | 858 | 0 | 12000 |  | 18578 |  | 5720 | 858 | 0 | 12000 | 0 | 18578 | OK
| Visualisation materials for institutional, stakeholder meetings | PP5- VPR | LP, PP2, PP3, PP4, PP5 | 10 | 2860 | 429 |  | 3000 |  | 6289 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 1500 |  | 1500 |  | 1430 | 214.5 |  | 1500 |  | 3144.5 |  | 715 | 107.25 |  |  |  | 822.25 |  | 715 | 107.25 |  |  |  | 822.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2860 | 429 | 0 | 3000 | 0 | 6289 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 21164 | 3174.6 | 1800 | 16300 | 0 | 42438.6 | OK |  |  | 2545.4 | 381.81 | 600 | 300 | 0 | 3827.21 |  | 1673.1 | 250.965 | 0 | 2500 | 0 | 4424.065 |  | 2931.5 | 439.725 | 0 | 1500 | 0 | 4871.225 |  | 3789.5 | 568.425 | 900 | 0 | 0 | 5257.925 |  | 3932.5 | 589.875 | 300 | 0 | 0 | 4822.375 |  | 143 | 21.45 | 0 | 0 | 0 | 164.45 |  | 143 | 21.45 | 0 | 0 | 0 | 164.45 |  | 143 | 21.45 | 0 | 0 | 0 | 164.45 |  | 5863 | 879.45 | 0 | 12000 | 0 | 18742.45 |  | 21164 | 3174.6 | 1800 | 16300 | 0 | 42438.6 | OK
| INTERREGIONAL POLICY LEARNING | [9 empty] | OK | [71 empty] | OK
| Interregional thematic organisation | [9 empty] | OK | [71 empty] | OK
| Setting up Thematic Working Group (TWG) | LP | All partners | 2 | 572 | 85.8 |  |  |  | 657.8 | OK |  |  | 572 | 85.8 |  |  |  | 657.8 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 572 | 85.8 | 0 | 0 | 0 | 657.8 | OK
| TWG Rules of procedure | LP | All partners |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TWG meetings linked to thematic implementation | LP | All partners | 21 | 6006 | 900.9 | 3000 |  |  | 9906.9 | OK |  |  | 120.12 | 18.018 | 428.5714 |  |  | 566.7094 |  | 600.6 | 90.09 | 428.5714 |  |  | 1119.2614 |  | 1801.8 | 270.27 | 428.5714 |  |  | 2500.6414 |  | 1801.8 | 270.27 | 428.5714 |  |  | 2500.6414 |  | 1201.2 | 180.18 | 428.5714 |  |  | 1809.9514 |  |  | 0 |  |  |  | 0 |  | 240.24 | 36.036 | 428.5714 |  |  | 704.8474 |  |  | 0 |  |  |  | 0 |  | 240.24 | 36.036 | 428.5714 |  |  | 704.8474 |  | 6006 | 900.9 | 3000 | 0 | 0 | 9906.9 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Stakeholder involvement and organisational learning | [9 empty] | OK | [71 empty] | OK
| Setting up stakeholder & institutional learning groups | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 10 | 2860 | 429 |  |  |  | 3289 | OK |  |  | 2002 | 300.3 |  |  |  | 2302.3 |  | 858 | 128.7 |  |  |  | 986.7 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2860 | 429 | 0 | 0 | 0 | 3289 | OK
| Interactive training on stakeholder involvement/institutional learning for the Regional Managers | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 12 | 3432 | 514.8 |  |  |  | 3946.8 | OK |  |  | 1716 | 257.4 |  |  |  | 1973.4 |  | 1716 | 257.4 |  |  |  | 1973.4 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3432 | 514.8 | 0 | 0 | 0 | 3946.8 | OK
| Methodology for regional Roadmaps | PP2- TCC | All partners | 10 | 2860 | 429 |  |  |  | 3289 | OK |  |  | 2860 | 429 |  |  |  | 3289 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2860 | 429 | 0 | 0 | 0 | 3289 | OK
| regional Roadmaps (on the institutional/stakeholder involvement process) elaborated and quality controled | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 20 | 5720 | 858 |  |  |  | 6578 | OK |  |  | 1716 | 257.4 |  |  |  | 1973.4 |  | 4004 | 600.6 |  |  |  | 4604.6 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 5720 | 858 | 0 | 0 | 0 | 6578 | OK
| Regional Opening meeting for stakeholders (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 4290 | 643.5 |  | 2000 |  | 6933.5 | OK |  |  | 1287 | 193.05 |  |  |  | 1480.05 |  | 3003 | 450.45 | 0 | 2000 |  | 5453.45 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4290 | 643.5 | 0 | 2000 | 0 | 6933.5 | OK
| Meetings with stakeholder groups and Institutional learning groups / involvement in action plan implementation + Synergy Sessions with Institutional departments | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 60 | 17160 | 2574 |  | 4500 |  | 24234 | OK |  |  |  | 0 |  |  |  | 0 |  | 1716 | 257.4 |  | 450 |  | 2423.4 |  | 4290 | 643.5 |  | 1125 |  | 6058.5 |  | 6864 | 1029.6 |  | 1800 |  | 9693.6 |  | 4290 | 643.5 |  | 1125 |  | 6058.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 17160 | 2574 | 0 | 4500 | 0 | 24234 | OK
| Phase 1 closing stakeholder session (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 4290 | 643.5 |  | 2000 |  | 6933.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4290 | 643.5 | 0 | 2000 |  | 6933.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4290 | 643.5 | 0 | 2000 | 0 | 6933.5 | OK
| Synergy session for personnel of partner organisations | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 18 | 5148 | 772.2 |  |  |  | 5920.2 | OK |  |  |  | 0 |  |  |  | 0 |  | 1287 | 193.05 |  |  |  | 1480.05 |  | 1287 | 193.05 |  |  |  | 1480.05 |  | 1287 | 193.05 |  |  |  | 1480.05 |  | 1287 | 193.05 |  |  |  | 1480.05 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 5148 | 772.2 | 0 | 0 | 0 | 5920.2 | OK
| Thematic coordination of stakeholder involvement | PP2- TCC | LP- VRW | 20 | 5720 | 858 |  |  |  | 6578 | OK |  |  |  | 0 |  |  |  | 0 |  | 572 | 85.8 |  |  |  | 657.8 |  | 1716 | 257.4 |  |  |  | 1973.4 |  | 1716 | 257.4 |  |  |  | 1973.4 |  | 1716 | 257.4 |  |  |  | 1973.4 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 5720 | 858 | 0 | 0 | 0 | 6578 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Analysis | [9 empty] | OK | [71 empty] | OK
| Joint methodology for regional State of Arts | PP4 - PD | All partners | 1 | 286 | 42.9 |  |  |  | 328.9 | OK |  |  |  | 0 |  |  |  | 0 |  | 286 | 42.9 |  |  |  | 328.9 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 286 | 42.9 | 0 | 0 | 0 | 328.9 | OK
| Regional State of Arts (including good practice inventory + list of ingredients for change) | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 | 40 | 11440 | 1716 |  |  |  | 13156 | OK |  |  |  | 0 |  |  |  | 0 |  | 11440 | 1716 | 0 | 0 |  | 13156 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 11440 | 1716 | 0 | 0 | 0 | 13156 | OK
| Transnational audit visits to each region by experts delegated by 2 other partners | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Project level menu of good practices | PP4 - PD | LP- VRW | 4 | 1144 | 171.6 |  |  |  | 1315.6 | OK |  |  |  | 0 |  |  |  | 0 |  | 1144 | 171.6 |  |  |  | 1315.6 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1144 | 171.6 | 0 | 0 | 0 | 1315.6 | OK
| Thematic coordination of analysis phase | PP4 - PD | LP- VRW |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Knowledge exchange (good practice transfer) | [9 empty] | OK | [71 empty] | OK
| Guidelines (including matching learning needs with good practices)/methodology and templates for knowledge sharing | LP- VRW | All partners | 2 | 572 | 85.8 |  |  |  | 657.8 | OK |  |  |  | 0 |  |  |  | 0 |  | 572 | 85.8 |  |  |  | 657.8 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 572 | 85.8 | 0 | 0 | 0 | 657.8 | OK
| 3 Transnational Exchange Session meetings of 3 days length (for individual staff members of partners + appr. 3 stakeholders per partner region) | LP- VRW | All partners | 50 | 14300 | 2145 | 3200 | 8800 |  | 28445 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 10010 | 1501.5 | 2240 | 6160 |  | 19911.5 |  | 4290 | 643.5 | 960 | 2640 |  | 8533.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 14300 | 2145 | 3200 | 8800 | 0 | 28445 | OK
| Summary reports on the Exchange Sessions | LP- VRW | All partners | 5 | 1430 | 214.5 |  |  |  | 1644.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1001 | 150.15 |  |  |  | 1151.15 |  | 429 | 64.35 |  |  |  | 493.35 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1430 | 214.5 | 0 | 0 | 0 | 1644.5 | OK
| Thematic coordination of knowledge exchange | LP- VRW | n.a. |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Action plan drafting | [9 empty] | OK | [71 empty] | OK
| Project level Guideline and joint training on action plan development | PP3 - MCM | All partners | 8 | 2288 | 343.2 |  |  |  | 2631.2 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2288 | 343.2 |  |  |  | 2631.2 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2288 | 343.2 | 0 | 0 | 0 | 2631.2 | OK
| Detailed Action Plan methodology on regional level/workplan | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 0 | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Elaboration of Action Plans / policy instrument | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 40 | 11440 | 1716 |  | 15000 |  | 28156 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 5720 | 858 |  | 7500 |  | 14078 |  | 5720 | 858 |  | 7500 |  | 14078 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 11440 | 1716 | 0 | 15000 | 0 | 28156 | OK
| Cross- reading exercise | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 5 | 1430 | 214.5 |  |  |  | 1644.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1430 | 214.5 |  |  |  | 1644.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1430 | 214.5 | 0 | 0 | 0 | 1644.5 | OK
| Final quality control of Action Plans | PP3 - MCM | n.a. | 2 | 572 | 85.8 |  |  |  | 657.8 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 572 | 85.8 |  |  |  | 657.8 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 572 | 85.8 | 0 | 0 | 0 | 657.8 | OK
| Consistency check of Action Plans on regional level | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 3 | 858 | 128.7 |  |  |  | 986.7 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 858 | 128.7 |  |  |  | 986.7 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 858 | 128.7 | 0 | 0 | 0 | 986.7 | OK
| Thematic coordination of action planning | PP3 - MCM | LP- VRW |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Action plan implementation follow-up(24 months) |  |  |  |  | 0 |  |  |  |  | OK |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 |  |  |  |  | OK
| Monitoring of the implementation of the action plans | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 12 | 3432 | 514.7 |  |  |  | 3946.7 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 858 | 128.6 |  |  |  | 986.6 |  | 858 | 128.7 |  |  |  | 986.7 |  | 858 | 128.7 |  |  |  | 986.7 |  | 858 | 128.7 |  |  |  | 986.7 |  | 3432 | 514.7 | 0 | 0 | 0 | 3946.7 | OK
| Summary on the level of achievements / policy instrument | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 4 | 1144 | 171.4 |  |  |  | 1315.4 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 572 | 85.8 |  |  |  | 657.8 |  | 572 | 85.6 |  |  |  | 657.6 |  | 1144 | 171.4 | 0 | 0 | 0 | 1315.4 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[11 empty] | OK | [71 empty] | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 108394 | 16258.8 | 6200 | 32300 | 0 | 163152.8 | OK |  |  | 10273.12 | 1540.968 | 428.5714 | 0 | 0 | 12242.6594 |  | 27198.6 | 4079.79 | 428.5714 | 2450 | 0 | 34156.9614 |  | 20105.8 | 3015.87 | 2668.5714 | 7285 | 0 | 33075.2414 |  | 24395.8 | 3659.37 | 1388.5714 | 11940 | 0 | 41383.7414 |  | 21364.2 | 3204.63 | 428.5714 | 10625 | 0 | 35622.4014 |  | 858 | 128.6 | 0 | 0 | 0 | 986.6 |  | 1098.24 | 164.736 | 428.5714 | 0 | 0 | 1691.5474 |  | 1430 | 214.5 | 0 | 0 | 0 | 1644.5 |  | 1670.24 | 250.336 | 428.5714 | 0 | 0 | 2349.1474 |  | 108394 | 16258.8 | 6200 | 32300 | 0 | 163152.8 | OK
| TOTAL |  |  |  | 165022 | 24753 | 12200 | 56850 | 0 | 258825 | OK |  |  | 17937.92 | 2690.688 | 2657.1429 | 300 | 0 | 23585.7509 |  | 31588.7 | 4738.305 | 857.1429 | 9587.5 | 0 | 46771.6479 |  | 30444.7 | 4566.705 | 3097.1429 | 9422.5 | 0 | 47531.0479 |  | 35792.9 | 5368.935 | 2717.1429 | 12577.5 | 0 | 56456.4779 |  | 31846.1 | 4776.915 | 1157.1429 | 11262.5 | 0 | 49042.6579 |  | 2802.8 | 420.32 | 0 | 637.5 | 0 | 3860.62 |  | 1584.44 | 237.666 | 857.1429 | 0 | 0 | 2679.2489 |  | 3374.8 | 506.22 | 0 | 637.5 | 0 | 4518.52 |  | 9649.64 | 1447.246 | 857.1429 | 12425 | 0 | 24379.0289 |  | 165022 | 24753 | 12200 | 56850 | 0 | 258825 | OK
[5 empty] | OK | OK | OK | OK | OK | OK | OK |  |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK
| Application Form budget |  |  |  | Staff | Overhead | T & A | External expertise | Equip. | TOTAL |  | ERDF | 220001.25
|  |  | PP2 - TCC |  | 165022 | 24753 | 12200 | 56850 | 0 | 258825 |  | Co-finance | 38823.75
[12 empty] | TOTAL | 258825
| Application Form budget - Spending Forecast | Period | Budget | % | Rounded |  | Application Form budget - External expertise | Type of cost |  | Budget |  |  | OK
|  | Preparation | 0 | 0% | 0 |  |  | FLC cost |  | 4250
|  | Semester 1 | 23585.7509 | 9.113% | 23586 |  |  | Project/financial/comm. management
|  | Semester 2 | 46771.6479 | 18.07% | 46772 |  |  | Meetings: partner meeting |  | 8000
|  | Semester 3 | 47531.0479 | 18.36% | 47531 |  |  | Meetings: dissemination event |  | 12000
|  | Semester 4 | 56456.4779 | 21.81% | 56456 |  |  |  |  | 0
|  | Semester 5 | 49042.6579 | 18.95% | 49043 |  |  | Meetings: stakeholder group |  | 8500
|  | Semester 6 | 3860.62 | 1.492% | 3861 |  |  | Travel & acc. cost: non staff |  | 4800
|  | Semester 7 | 2679.2489 | 1.035% | 2679 |  |  | Publication and dissemination costs |  | 4300
|  | Semester 8 | 4518.52 | 1.746% | 4519 |  |  | External support for the exc. of experience |  | 15000
|  | Semester 9 | 24379.0289 | 9.419% | 24378 |  |  | Other
|  |  |  | 0 |  |  |  | TOTAL |  | 56850
|  | TOTAL | 258825 | 1 | 258825 |  |  |  |  | OK
|  |  | OK |  | OK
| % check tables | Budget lines | % |  |  |  | Application Form budget - Equipment | Type of cost |  | Budget
|  | Staff | 63.76% |  |  |  |  | Office eqiupment
|  | Overhead | 9.564% |  |  |  |  | Other
|  | T & A | 4.714% |  |  |  |  | TOTAL |  | 0
|  | Ext. expertise | 21.96% | [6 empty] | OK
|  | Eqipment | 0%
|  | TOTAL | 100%
|  | CP | %
|  | Management CP | 20.57%
|  | Communication CP | 16.4%
|  | Thematic CP | 63.04%
|  | TOTAL | 100%
|  | Austria | 262
|  | Belgium | 278
|  | Czech Republic | 118
|  | Denmark | 280
|  | Estonia | 110
|  | Finland | 232
|  | France | 233
|  | Germany | 253
|  | Greece | 148
|  | Hungary | 121
|  | Ireland | 286
|  | Italy | 200
|  | Netherlands | 275
|  | Poland | 131
|  | Portugal | 137
|  | Slovak Republic | 118
|  | Slovenia | 185
|  | Spain | 202
|  | Sweden | 236
|  | United Kingdom | 238
|  | Bulgaria | 80
|  | Croatia | 100
|  | Cyprus | 120
|  | Latvia | 104
|  | Lithuania | 100
|  | Luxemburg | 324
|  | Malta | 140
|  | Romania | 80
|  | ERDF | 75%
|  | ERDF | 85%
Note on I24: Tóth Gábor: Organisation of the SG and TWG meeting to be held in month 11
Note on I28: Tóth Gábor: FLC cost
Note on I37: Tóth Gábor: Printing of the briefing brouchure
Note on I38: Tóth Gábor: Printing cost of the poster
Note on I55: Tóth Gábor: Printing cost
Note on I56: Tóth Gábor: Non-staff stakeholder travel (2 person)
Note on I57: Tóth Gábor: Organisation of the Final conference, SG and TWG meeting to be held at month 51
Note on I58: Tóth Gábor: Design and printing cost
Note on I74: Tóth Gábor: Cost for organisieng the meeting (incuding networking activities)
Note on I75: Tóth Gábor: Organisation cost
Note on I76: Tóth Gábor: Cost for organisieng the meeting (incuding networking activities)
Note on I84: Tóth Gábor: Organisation cost for hosting the visit
Note on I91: Tóth Gábor: Non-staff stakeholder travel (3 person): 4800 EUR Organisation of 1 Transnational exchange session: 4000 EUR
Note on I99: Tóth Gábor: External support for the preparation of the Action Plan

## PP3_MCM
PP3 - MCM |  |  |  | Country --> | [5 empty] | Italy |  |  | Semester 1 (month 1-6) | [6 empty] | Semester 2 (month 7-12) | [6 empty] | Semester 3 (month 13-18) | [6 empty] | Semester 4 (month 19-24) | [6 empty] | Semester 5 (month 25-30) | [6 empty] | Semester 6 (month 31-36) | [6 empty] | Semester 7 (month 37-42) | [6 empty] | Semester 8 (month 43-48) | [6 empty] | Semester 9 (month 49-54) | [6 empty] | TOTAL
DAILY FEE |  | 200 |  |  | Travel cost 1 person 2 nights |  |  | 600 | ERDF | 0.85
[5 empty] | Travel cost 1 person 3 nights |  |  | 800
215200
Action | ACTIVITIES | Partner in charge | Participating
|  |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL
|  |  |  | days | total | [7 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total
| PREPARATION | LP
| Project proposal preparation |  |  |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | OK |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| PROJECT MANAGEMENT AND COORDINATION | LP | [8 empty] | OK | [71 empty] | OK
| Contractualisation and start-up | [9 empty] | OK | [71 empty] | OK
| Subsidy Contract | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Partnership Agreement | LP | All | 1 | 200 | 30 |  |  |  | 230 | OK |  |  | 200 | 30 |  |  |  | 230 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 200 | 30 | 0 | 0 | 0 | 230 | OK
| Appointment FLC | LP | All | 2 | 400 | 60 |  |  |  | 460 | OK |  |  | 400 | 60 |  |  |  | 460 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 400 | 60 | 0 | 0 | 0 | 460 | OK
| Management and financial handbook | LP | All | 1 | 200 | 30 |  |  |  | 230 | OK |  |  | 200 | 30 |  |  |  | 230 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 200 | 30 | 0 | 0 | 0 | 230 | OK
| Rules of Procedures for the PR | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Rules of Procedures for the SG | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Kick-off meeting | LP | All | 8 | 1600 | 240 | 1200 |  |  | 3040 | OK |  |  | 1600 | 240 | 1200 | 0 |  | 3040 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1600 | 240 | 1200 | 0 | 0 | 3040 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Project Management and coordination | [9 empty] | OK | [71 empty] | OK
| Daily project management | LP | All | 30 | 6000 | 900 |  |  |  | 6900 | OK |  |  | 900 | 135 |  | 0 | 0 | 1035 |  | 300 | 45 |  | 0 |  | 345 |  | 1800 | 270 |  | 0 |  | 2070 |  | 1200 | 180 |  | 0 |  | 1380 |  | 1800 | 270 |  | 0 |  | 2070 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 6000 | 900 | 0 | 0 | 0 | 6900 | OK
| Steering Group meeting linked with thematic meeting | LP | All | 30 | 6000 | 900 | 3000 | 3600 |  | 13500 | OK |  |  | 120 | 18 | 428.5714 |  |  | 566.5714 |  | 600 | 90 | 428.5714 |  |  | 1118.5714 |  | 1800 | 270 | 428.5714 |  |  | 2498.5714 |  | 1800 | 270 | 428.5714 | 3600 |  | 6098.5714 |  | 1200 | 180 | 428.5714 |  |  | 1808.5714 |  |  | 0 |  |  |  | 0 |  | 240 | 36 | 428.5714 |  |  | 704.5714 |  |  | 0 |  |  |  | 0 |  | 240 | 36 | 428.5714 |  |  | 704.5714 |  | 6000 | 900 | 3000 | 3600 | 0 | 13500 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Reporting | [9 empty] | OK | [71 empty] | OK
| Internal financial monitoring/budget revision | LP | All | 8 | 1600 | 240 |  |  |  | 1840 | OK |  |  | 160 | 24 |  |  |  | 184 |  | 160 | 24 |  |  |  | 184 |  | 320 | 48 |  |  |  | 368 |  | 640 | 96 |  |  |  | 736 |  | 320 | 48 |  |  |  | 368 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1600 | 240 | 0 | 0 | 0 | 1840 | OK
| Preparation of partner level progress report | LP | All | 35 | 7000 | 1050 |  | 3500 |  | 11550 | OK |  |  |  | 0 |  |  |  | 0 |  | 700 | 105 |  | 525 |  | 1330 |  | 1050 | 157.5 |  | 525 |  | 1732.5 |  | 1400 | 210 |  | 525 |  | 2135 |  | 1050 | 157.5 |  | 525 |  | 1732.5 |  | 1050 | 157.5 |  | 525 |  | 1732.5 |  |  | 0 |  |  |  | 0 |  | 1050 | 157.5 |  | 525 |  | 1732.5 |  | 700 | 105 |  | 350 |  | 1155 |  | 7000 | 1050 | 0 | 3500 | 0 | 11550 | OK
| Delivery of progress report to JTS | LP | All | 7 | 1400 | 210 |  |  |  | 1610 | OK |  |  |  | 0 |  |  |  | 0 |  | 140 | 21 |  | 0 |  | 161 |  | 210 | 31.5 |  | 0 |  | 241.5 |  | 280 | 42 |  | 0 |  | 322 |  | 210 | 31.5 |  | 0 |  | 241.5 |  | 210 | 31.5 |  | 0 |  | 241.5 |  |  | 0 |  |  |  | 0 |  | 210 | 31.5 |  | 0 |  | 241.5 |  | 140 | 21 |  | 0 |  | 161 |  | 1400 | 210 | 0 | 0 | 0 | 1610 | OK
| Delivery of final report to JTS | LP | All | 2 | 400 | 60 |  |  |  | 460 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 400 | 60 |  |  |  | 460 |  | 400 | 60 | 0 | 0 | 0 | 460 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 24800 | 3720 | 4200 | 7100 | 0 | 39820 | OK |  |  | 3580 | 537 | 1628.5714 | 0 | 0 | 5745.5714 |  | 1900 | 285 | 428.5714 | 525 | 0 | 3138.5714 |  | 5180 | 777 | 428.5714 | 525 | 0 | 6910.5714 |  | 5320 | 798 | 428.5714 | 4125 | 0 | 10671.5714 |  | 4580 | 687 | 428.5714 | 525 | 0 | 6220.5714 |  | 1260 | 189 | 0 | 525 | 0 | 1974 |  | 240 | 36 | 428.5714 | 0 | 0 | 704.5714 |  | 1260 | 189 | 0 | 525 | 0 | 1974 |  | 1480 | 222 | 428.5714 | 350 | 0 | 2480.5714 |  | 24800 | 3720 | 4200 | 7100 | 0 | 39820 | OK
| COMMUNICATION | [9 empty] | OK | [71 empty] | OK
| Planning and start-up | [9 empty] | OK | [71 empty] | OK
| Communication and knowledge sharing strategy | PP5-VPR | All | 1 | 200 | 30 |  |  |  | 230 | OK |  |  | 200 | 30 |  |  |  | 230 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 200 | 30 | 0 | 0 | 0 | 230 | OK
| Launching event | LP | All | 3 | 600 | 90 | 600 |  |  | 1290 | OK |  |  | 420 | 63 | 600 | 0 |  | 1083 |  | 180 | 27 |  | 0 |  | 207 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 600 | 90 | 600 | 0 | 0 | 1290 | OK
| Briefing brochure linked to the Launching event about the project and the topic adressed | PP5-VPR | All | 4 | 800 | 120 |  | 2000 |  | 2920 | OK |  |  | 560 | 84 |  |  |  | 644 |  | 240 | 36 |  | 2000 |  | 2276 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 800 | 120 | 0 | 2000 | 0 | 2920 | OK
| Poster (obligatory) | PP5-VPR | All | 2 | 400 | 60 |  | 300 |  | 760 | OK |  |  | 400 | 60 |  | 300 |  | 760 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 400 | 60 | 0 | 300 | 0 | 760 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Website and social media | [9 empty] | OK | [71 empty] | OK
| Launching of website and regular update of the website | PP5-VPR | All | 7 | 1400 | 210 |  |  |  | 1610 | OK |  |  | 140 | 21 |  |  |  | 161 |  | 70 | 10.5 |  |  |  | 80.5 |  | 280 | 42 |  |  |  | 322 |  | 350 | 52.5 |  |  |  | 402.5 |  | 280 | 42 |  |  |  | 322 |  | 70 | 10.5 |  |  |  | 80.5 |  | 70 | 10.5 |  |  |  | 80.5 |  | 70 | 10.5 |  |  |  | 80.5 |  | 70 | 10.5 |  |  |  | 80.5 |  | 1400 | 210 | 0 | 0 | 0 | 1610 | OK
| Social media presence | PP5-VPR | All | 3 | 600 | 90 |  |  |  | 690 | OK |  |  | 60 | 9 |  |  |  | 69 |  | 30 | 4.5 |  |  |  | 34.5 |  | 120 | 18 |  |  |  | 138 |  | 150 | 22.5 |  |  |  | 172.5 |  | 120 | 18 |  |  |  | 138 |  | 30 | 4.5 |  |  |  | 34.5 |  | 30 | 4.5 |  |  |  | 34.5 |  | 30 | 4.5 |  |  |  | 34.5 |  | 30 | 4.5 |  |  |  | 34.5 |  | 600 | 90 | 0 | 0 | 0 | 690 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Paticipation in other events | [9 empty] | OK | [71 empty] | OK
| INTERREG Europe events | PP5-VPR, LP- VRW | n.a. |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Dissemination at transnational events (presenter or exhibitioner) | PP5-VPR | All | 3 | 600 | 90 | 600 |  |  | 1290 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 600 | 90 | 600 |  |  | 1290 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 600 | 90 | 600 | 0 | 0 | 1290 | OK
| Dissemination at national events (presenter or exhibitioner) | PP5-VPR | All | 4 | 800 | 120 | 600 |  |  | 1520 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 400 | 60 | 300 |  |  | 760 |  | 400 | 60 | 300 |  |  | 760 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 800 | 120 | 600 | 0 | 0 | 1520 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Communication materials/tools | [9 empty] | OK | [71 empty] | OK
| Press releases | PP5-VPR | TWG meeting/event organisers | 8 | 1600 | 240 |  |  |  | 1840 | OK |  |  |  | 0 |  |  |  | 0 |  | 400 | 60 |  |  |  | 460 |  | 400 | 60 |  |  |  | 460 |  | 400 | 60 |  |  |  | 460 |  | 400 | 60 |  |  |  | 460 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1600 | 240 | 0 | 0 | 0 | 1840 | OK
| Newsletters on project level | PP5-VPR | All | 5 | 1000 | 150 |  |  |  | 1150 | OK |  |  |  | 0 |  |  |  | 0 |  | 250 | 37.5 |  | 0 |  | 287.5 |  | 250 | 37.5 |  |  |  | 287.5 |  | 250 | 37.5 |  |  |  | 287.5 |  | 250 | 37.5 |  |  |  | 287.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1000 | 150 | 0 | 0 | 0 | 1150 | OK
| Project video | PP5-VPR | All | 3 | 600 | 90 |  |  |  | 690 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 600 | 90 |  | 0 |  | 690 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 600 | 90 | 0 | 0 | 0 | 690 | OK
| Policy learning Synthesis report | LP- VRW, PP5-VPR | All | 1 | 200 | 30 |  |  |  | 230 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 200 | 30 |  |  |  | 230 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 200 | 30 | 0 | 0 | 0 | 230 | OK
| Dissemination materials on exchanged experience targeting regions outside the partnership | PP4-VPR | All |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Mid term event | PP4-VPR | All partners |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Final event | PP2- TCC | All partners | 3 | 600 | 90 | 600 |  |  | 1290 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 600 | 90 | 600 | 0 |  | 1290 |  | 600 | 90 | 600 | 0 | 0 | 1290 | OK
| Visualisation materials for institutional, stakeholder meetings | PP5- VPR | LP, PP2, PP3, PP4, PP5 | 10 | 2000 | 300 |  | 3000 |  | 5300 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 1500 |  | 1500 |  | 1000 | 150 |  | 1500 |  | 2650 |  | 500 | 75 |  |  |  | 575 |  | 500 | 75 |  |  |  | 575 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2000 | 300 | 0 | 3000 | 0 | 5300 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 11400 | 1710 | 2400 | 5300 | 0 | 20810 | OK |  |  | 1780 | 267 | 600 | 300 | 0 | 2947 |  | 1170 | 175.5 | 0 | 3500 | 0 | 4845.5 |  | 2050 | 307.5 | 0 | 1500 | 0 | 3857.5 |  | 2650 | 397.5 | 900 | 0 | 0 | 3947.5 |  | 2750 | 412.5 | 300 | 0 | 0 | 3462.5 |  | 100 | 15 | 0 | 0 | 0 | 115 |  | 100 | 15 | 0 | 0 | 0 | 115 |  | 100 | 15 | 0 | 0 | 0 | 115 |  | 700 | 105 | 600 | 0 | 0 | 1405 |  | 11400 | 1710 | 2400 | 5300 | 0 | 20810 | OK
| INTERREGIONAL POLICY LEARNING | [9 empty] | OK | [71 empty] | OK
| Interregional thematic organisation | [9 empty] | OK | [71 empty] | OK
| Setting up Thematic Working Group (TWG) | LP | All partners | 2 | 400 | 60 |  |  |  | 460 | OK |  |  | 400 | 60 |  |  |  | 460 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 400 | 60 | 0 | 0 | 0 | 460 | OK
| TWG Rules of procedure | LP | All partners |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TWG meetings linked to thematic implementation | LP | All partners | 31 | 6200 | 930 | 3000 | 3600 |  | 13730 | OK |  |  | 124 | 18.6 | 428.5714 |  |  | 571.1714 |  | 620 | 93 | 428.5714 |  |  | 1141.5714 |  | 1860 | 279 | 428.5714 |  |  | 2567.5714 |  | 1860 | 279 | 428.5714 |  |  | 2567.5714 |  | 1240 | 186 | 428.5714 |  |  | 1854.5714 |  |  | 0 |  |  |  | 0 |  | 248 | 37.2 | 428.5714 | 3600 |  | 4313.7714 |  |  | 0 |  |  |  | 0 |  | 248 | 37.2 | 428.5714 |  |  | 713.7714 |  | 6200 | 930 | 3000 | 3600 | 0 | 13730 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Stakeholder involvement and organisational learning | [9 empty] | OK | [71 empty] | OK
| Setting up stakeholder & institutional learning groups | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 5 | 1000 | 150 |  |  |  | 1150 | OK |  |  | 700 | 105 |  |  |  | 805 |  | 300 | 45 |  |  |  | 345 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1000 | 150 | 0 | 0 | 0 | 1150 | OK
| Interactive training on stakeholder involvement/institutional learning for the Regional Managers | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 4 | 800 | 120 |  |  |  | 920 | OK |  |  | 400 | 60 |  |  |  | 460 |  | 400 | 60 |  |  |  | 460 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 800 | 120 | 0 | 0 | 0 | 920 | OK
| Methodology for regional Roadmaps | PP2- TCC | All partners | 1 | 200 | 30 |  |  |  | 230 | OK |  |  | 200 | 30 |  |  |  | 230 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 200 | 30 | 0 | 0 | 0 | 230 | OK
| regional Roadmaps (on the institutional/stakeholder involvement process) elaborated and quality controled | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 20 | 4000 | 600 |  |  |  | 4600 | OK |  |  | 1200 | 180 |  |  |  | 1380 |  | 2800 | 420 |  |  |  | 3220 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4000 | 600 | 0 | 0 | 0 | 4600 | OK
| Regional Opening meeting for stakeholders (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 3000 | 450 |  | 1800 |  | 5250 | OK |  |  | 900 | 135 |  |  |  | 1035 |  | 2100 | 315 | 0 | 1800 |  | 4215 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3000 | 450 | 0 | 1800 | 0 | 5250 | OK
| Meetings with stakeholder groups and Institutional learning groups / involvement in action plan implementation + Synergy Sessions with Institutional departments | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 50 | 10000 | 1500 |  | 4050 |  | 15550 | OK |  |  |  | 0 |  |  |  | 0 |  | 1000 | 150 |  | 405 |  | 1555 |  | 2500 | 375 |  | 1012.5 |  | 3887.5 |  | 4000 | 600 |  | 1620 |  | 6220 |  | 2500 | 375 |  | 1012.5 |  | 3887.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 10000 | 1500 | 0 | 4050 | 0 | 15550 | OK
| Phase 1 closing stakeholder session (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 3000 | 450 |  | 1800 |  | 5250 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3000 | 450 | 0 | 1800 |  | 5250 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3000 | 450 | 0 | 1800 | 0 | 5250 | OK
| Synergy session for personnel of partner organisations | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 18 | 3600 | 540 |  |  |  | 4140 | OK |  |  |  | 0 |  |  |  | 0 |  | 900 | 135 |  |  |  | 1035 |  | 900 | 135 |  |  |  | 1035 |  | 900 | 135 |  |  |  | 1035 |  | 900 | 135 |  |  |  | 1035 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3600 | 540 | 0 | 0 | 0 | 4140 | OK
| Thematic coordination of stakeholder involvement | PP2- TCC | LP- VRW |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Analysis | [9 empty] | OK | [71 empty] | OK
| Joint methodology for regional State of Arts | PP4 - PD | All partners | 1 | 200 | 30 |  |  |  | 230 | OK |  |  |  | 0 |  |  |  | 0 |  | 200 | 30 |  |  |  | 230 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 200 | 30 | 0 | 0 | 0 | 230 | OK
| Regional State of Arts (including good practice inventory + list of ingredients for change) | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 | 40 | 8000 | 1200 |  | 10000 |  | 19200 | OK |  |  |  | 0 |  |  |  | 0 |  | 8000 | 1200 | 0 | 0 |  | 9200 |  |  | 0 |  | 10000 |  | 10000 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 8000 | 1200 | 0 | 10000 | 0 | 19200 | OK
| Transnational audit visits to each region by experts delegated by 2 other partners | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Project level menu of good practices | PP4 - PD | LP- VRW | 4 | 800 | 120 |  |  |  | 920 | OK |  |  |  | 0 |  |  |  | 0 |  | 800 | 120 |  |  |  | 920 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 800 | 120 | 0 | 0 | 0 | 920 | OK
| Thematic coordination of analysis phase | PP4 - PD | LP- VRW |  | 0 | 0 |  | 5000 |  | 5000 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  | 5000 |  | 5000 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 5000 | 0 | 5000 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Knowledge exchange (good practice transfer) | [9 empty] | OK | [71 empty] | OK
| Guidelines (including matching learning needs with good practices)/methodology and templates for knowledge sharing | LP- VRW | All partners | 2 | 400 | 60 |  |  |  | 460 | OK |  |  |  | 0 |  |  |  | 0 |  | 400 | 60 |  |  |  | 460 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 400 | 60 | 0 | 0 | 0 | 460 | OK
| 3 Transnational Exchange Session meetings of 3 days length (for individual staff members of partners + appr. 3 stakeholders per partner region) | LP- VRW | All partners | 50 | 10000 | 1500 | 4800 | 7200 |  | 23500 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 7000 | 1050 | 3360 | 5040 |  | 16450 |  | 3000 | 450 | 1440 | 2160 |  | 7050 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 10000 | 1500 | 4800 | 7200 | 0 | 23500 | OK
| Summary reports on the Exchange Sessions | LP- VRW | All partners | 5 | 1000 | 150 |  |  |  | 1150 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 700 | 105 |  |  |  | 805 |  | 300 | 45 |  |  |  | 345 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1000 | 150 | 0 | 0 | 0 | 1150 | OK
| Thematic coordination of knowledge exchange | LP- VRW | n.a. |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Action plan drafting | [9 empty] | OK | [71 empty] | OK
| Project level Guideline and joint training on action plan development | PP3 - MCM | All partners | 22 | 4400 | 660 |  |  |  | 5060 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4400 | 660 |  |  |  | 5060 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4400 | 660 | 0 | 0 | 0 | 5060 | OK
| Detailed Action Plan methodology on regional level/workplan | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 0 | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Elaboration of Action Plans / policy instrument | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 40 | 8000 | 1200 |  | 25000 |  | 34200 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4000 | 600 |  | 12500 |  | 17100 |  | 4000 | 600 |  | 12500 |  | 17100 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 8000 | 1200 | 0 | 25000 | 0 | 34200 | OK
| Cross- reading exercise | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 10 | 2000 | 300 |  |  |  | 2300 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2000 | 300 |  |  |  | 2300 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2000 | 300 | 0 | 0 | 0 | 2300 | OK
| Final quality control of Action Plans | PP3 - MCM | n.a. | 10 | 2000 | 300 |  |  |  | 2300 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2000 | 300 |  |  |  | 2300 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2000 | 300 | 0 | 0 | 0 | 2300 | OK
| Consistency check of Action Plans on regional level | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 3 | 600 | 90 |  |  |  | 690 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 600 | 90 |  |  |  | 690 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 600 | 90 | 0 | 0 | 0 | 690 | OK
| Thematic coordination of action planning | PP3 - MCM | LP- VRW | 20 | 4000 | 600 |  |  |  | 4600 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2000 | 300 |  |  |  | 2300 |  | 2000 | 300 |  |  |  | 2300 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4000 | 600 | 0 | 0 | 0 | 4600 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Action plan implementation follow-up(24 months) |  |  |  |  | 0 |  |  |  |  | OK |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 |  |  |  |  | OK
| Monitoring of the implementation of the action plans | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 12 | 2400 | 360 |  |  |  | 2760 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 600 | 90 |  |  |  | 690 |  | 600 | 90 |  |  |  | 690 |  | 600 | 90 |  |  |  | 690 |  | 600 | 90 |  |  |  | 690 |  | 2400 | 360 | 0 | 0 | 0 | 2760 | OK
| Summary on the level of achievements / policy instrument | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 4 | 800 | 120 |  |  |  | 920 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 400 | 60 |  |  |  | 460 |  | 400 | 60 |  |  |  | 460 |  | 800 | 120 | 0 | 0 | 0 | 920 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[11 empty] | OK | [71 empty] | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 76800 | 11520 | 7800 | 58450 | 0 | 154570 | OK |  |  | 3924 | 588.6 | 428.5714 | 0 | 0 | 4941.1714 |  | 17520 | 2628 | 428.5714 | 2205 | 0 | 22781.5714 |  | 12960 | 1944 | 3788.5714 | 21052.5 | 0 | 39745.0714 |  | 20460 | 3069 | 1868.5714 | 16280 | 0 | 41677.5714 |  | 18240 | 2736 | 428.5714 | 15312.5 | 0 | 36717.0714 |  | 600 | 90 | 0 | 0 | 0 | 690 |  | 848 | 127.2 | 428.5714 | 3600 | 0 | 5003.7714 |  | 1000 | 150 | 0 | 0 | 0 | 1150 |  | 1248 | 187.2 | 428.5714 | 0 | 0 | 1863.7714 |  | 76800 | 11520 | 7800 | 58450 | 0 | 154570 | OK
| TOTAL |  |  |  | 113000 | 16950 | 14400 | 70850 | 0 | 215200 | OK |  |  | 9284 | 1392.6 | 2657.1429 | 300 | 0 | 13633.7429 |  | 20590 | 3088.5 | 857.1429 | 6230 | 0 | 30765.6429 |  | 20190 | 3028.5 | 4217.1429 | 23077.5 | 0 | 50513.1429 |  | 28430 | 4264.5 | 3197.1429 | 20405 | 0 | 56296.6429 |  | 25570 | 3835.5 | 1157.1429 | 15837.5 | 0 | 46400.1429 |  | 1960 | 294 | 0 | 525 | 0 | 2779 |  | 1188 | 178.2 | 857.1429 | 3600 | 0 | 5823.3429 |  | 2360 | 354 | 0 | 525 | 0 | 3239 |  | 3428 | 514.2 | 1457.1429 | 350 | 0 | 5749.3429 |  | 113000 | 16950 | 14400 | 70850 | 0 | 215200 | OK
[5 empty] | OK | OK | OK | OK | OK | OK | OK |  |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK
| Application Form budget |  |  |  | Staff | Overhead | T & A | External expertise | Equip. | TOTAL |  | ERDF | 182920
|  |  | PP3 - MCM |  | 113000 | 16950 | 14400 | 70850 | 0 | 215200 |  | Co-finance | 32280
[12 empty] | TOTAL | 215200
| Application Form budget - Spending Forecast | Period | Budget | % | Rounded |  | Application Form budget - External expertise | Type of cost |  | Budget |  |  | OK
|  | Preparation | 0 | 0% | 0 |  |  | FLC cost |  | 3500
|  | Semester 1 | 13633.7429 | 6.335% | 13634 |  |  | Project/financial/comm. management
|  | Semester 2 | 30765.6429 | 14.3% | 30766 |  |  | Meetings: partner meeting |  | 7200
|  | Semester 3 | 50513.1429 | 23.47% | 50513 |  |  | Meetings: dissemination event
|  | Semester 4 | 56296.6429 | 26.16% | 56297 |  |  |  |  | 0
|  | Semester 5 | 46400.1429 | 21.56% | 46400 |  |  | Meetings: stakeholder group |  | 7650
|  | Semester 6 | 2779 | 1.291% | 2779 |  |  | Travel & acc. cost: non staff |  | 7200
|  | Semester 7 | 5823.3429 | 2.706% | 5823 |  |  | Publication and dissemination costs |  | 5300
|  | Semester 8 | 3239 | 1.505% | 3239 |  |  | External support for the exc. of experience |  | 40000
|  | Semester 9 | 5749.3429 | 2.672% | 5749 |  |  | Other
|  |  |  | 0 |  |  |  | TOTAL |  | 70850
|  | TOTAL | 215200 | 1 | 215200 |  |  |  |  | OK
|  |  | OK |  | OK
| % check tables | Budget lines | % |  |  |  | Application Form budget - Equipment | Type of cost |  | Budget
|  | Staff | 52.51% |  |  |  |  | Office eqiupment
|  | Overhead | 7.876% |  |  |  |  | Other
|  | T & A | 6.691% |  |  |  |  | TOTAL |  | 0
|  | Ext. expertise | 32.92% | [6 empty] | OK
|  | Eqipment | 0%
|  | TOTAL | 100%
|  | CP | %
|  | Management CP | 18.5%
|  | Communication CP | 9.67%
|  | Thematic CP | 71.83%
|  | TOTAL | 100%
|  | Austria | 262
|  | Belgium | 278
|  | Czech Republic | 118
|  | Denmark | 280
|  | Estonia | 110
|  | Finland | 232
|  | France | 233
|  | Germany | 253
|  | Greece | 148
|  | Hungary | 121
|  | Ireland | 286
|  | Italy | 200
|  | Netherlands | 275
|  | Poland | 131
|  | Portugal | 137
|  | Slovak Republic | 118
|  | Slovenia | 185
|  | Spain | 202
|  | Sweden | 236
|  | United Kingdom | 238
|  | Bulgaria | 80
|  | Croatia | 100
|  | Cyprus | 120
|  | Latvia | 104
|  | Lithuania | 100
|  | Luxemburg | 324
|  | Malta | 140
|  | Romania | 80
|  | ERDF | 75%
|  | ERDF | 85%
Note on I24: Tóth Gábor: Organisation of the SG and TWG meeting to be held in month 20
Note on I28: Tóth Gábor: FLC cost
Note on I37: Tóth Gábor: Translation and printing of the briefing brouchure
Note on I38: Tóth Gábor: Printing cost of the poster
Note on I55: Tóth Gábor: Printing cost
Note on I56: Tóth Gábor: Non-staff stakeholder travel (2 person)
Note on I58: Tóth Gábor: Design and printing cost
Note on I66: Tóth Gábor: Organisation of the SG and TWG meeting to be held in month 38
Note on I74: Tóth Gábor: Cost for organisieng the meeting (incuding networking activities)
Note on I75: Tóth Gábor: Organisation cost
Note on I76: Tóth Gábor: Cost for organisieng the meeting (incuding networking activities)
Note on I84: Tóth Gábor: Organisation cost for hosting the visit
Note on I91: Tóth Gábor: Non-staff stakeholder travel (3 person)
Note on I99: Tóth Gábor: External support for the preparation of the Action Plan

## PP4_Pons_Danubii
PP4 - Pons Danubii |  |  |  | Country --> | [5 empty] | Slovak Republic |  |  | Semester 1 (month 1-6) | [6 empty] | Semester 2 (month 7-12) | [6 empty] | Semester 3 (month 13-18) | [6 empty] | Semester 4 (month 19-24) | [6 empty] | Semester 5 (month 25-30) | [6 empty] | Semester 6 (month 31-36) | [6 empty] | Semester 7 (month 37-42) | [6 empty] | Semester 8 (month 43-48) | [6 empty] | Semester 9 (month 49-54) | [6 empty] | TOTAL
DAILY FEE |  | 130 |  |  | Travel cost 1 person 2 nights |  |  | 600 | ERDF | 0.85
[5 empty] | Travel cost 1 person 3 nights |  |  | 800
153732
Action | ACTIVITIES | Partner in charge | Participating
|  |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL
|  |  |  | days | total | [7 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total
| PREPARATION | LP
| Project proposal preparation |  |  |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | OK |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| PROJECT MANAGEMENT AND COORDINATION | LP | [8 empty] | OK | [71 empty] | OK
| Contractualisation and start-up | [9 empty] | OK | [71 empty] | OK
| Subsidy Contract | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Partnership Agreement | LP | All | 1 | 130 | 19.5 |  |  |  | 149.5 | OK |  |  | 130 | 19.5 |  |  |  | 149.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 130 | 19.5 | 0 | 0 | 0 | 149.5 | OK
| Appointment FLC | LP | All | 2 | 260 | 39 |  |  |  | 299 | OK |  |  | 260 | 39 |  |  |  | 299 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 260 | 39 | 0 | 0 | 0 | 299 | OK
| Management and financial handbook | LP | All | 1 | 130 | 19.5 |  |  |  | 149.5 | OK |  |  | 130 | 19.5 |  |  |  | 149.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 130 | 19.5 | 0 | 0 | 0 | 149.5 | OK
| Rules of Procedures for the PR | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Rules of Procedures for the SG | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Kick-off meeting | LP | All | 8 | 1040 | 156 | 1200 |  |  | 2396 | OK |  |  | 1040 | 156 | 1200 | 0 |  | 2396 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1040 | 156 | 1200 | 0 | 0 | 2396 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Project Management and coordination | [9 empty] | OK | [71 empty] | OK
| Daily project management | LP | All | 30 | 3900 | 585 |  | 15000 |  | 19485 | OK |  |  | 585 | 87.75 |  | 2250 | 0 | 2922.75 |  | 195 | 29.25 |  | 1500 |  | 1724.25 |  | 1170 | 175.5 |  | 3750 |  | 5095.5 |  | 780 | 117 |  | 3000 |  | 3897 |  | 1170 | 175.5 |  | 3000 |  | 4345.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 1500 |  | 1500 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3900 | 585 | 0 | 15000 | 0 | 19485 | OK
| Steering Group meeting linked with thematic meeting | LP | All | 15 | 1950 | 292.5 | 3600 | 3000 |  | 8842.5 | OK |  |  | 39 | 5.85 | 514.2857 |  |  | 559.1357 |  | 195 | 29.25 | 514.2857 |  |  | 738.5357 |  | 585 | 87.75 | 514.2857 |  |  | 1187.0357 |  | 585 | 87.75 | 514.2857 |  |  | 1187.0357 |  | 390 | 58.5 | 514.2857 | 3000 |  | 3962.7857 |  |  | 0 |  |  |  | 0 |  | 78 | 11.7 | 514.2857 |  |  | 603.9857 |  |  | 0 |  |  |  | 0 |  | 78 | 11.7 | 514.2857 |  |  | 603.9857 |  | 1950 | 292.5 | 3600 | 3000 | 0 | 8842.5 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Reporting | [9 empty] | OK | [71 empty] | OK
| Internal financial monitoring/budget revision | LP | All | 8 | 1040 | 156 |  |  |  | 1196 | OK |  |  | 104 | 15.6 |  |  |  | 119.6 |  | 104 | 15.6 |  |  |  | 119.6 |  | 208 | 31.2 |  |  |  | 239.2 |  | 416 | 62.4 |  |  |  | 478.4 |  | 208 | 31.2 |  |  |  | 239.2 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1040 | 156 | 0 | 0 | 0 | 1196 | OK
| Preparation of partner level progress report | LP | All | 35 | 4550 | 682.5 |  |  |  | 5232.5 | OK |  |  |  | 0 |  |  |  | 0 |  | 455 | 68.25 |  | 0 |  | 523.25 |  | 682.5 | 102.375 |  | 0 |  | 784.875 |  | 910 | 136.5 |  | 0 |  | 1046.5 |  | 682.5 | 102.375 |  | 0 |  | 784.875 |  | 682.5 | 102.375 |  | 0 |  | 784.875 |  |  | 0 |  |  |  | 0 |  | 682.5 | 102.375 |  | 0 |  | 784.875 |  | 455 | 68.25 |  | 0 |  | 523.25 |  | 4550 | 682.5 | 0 | 0 | 0 | 5232.5 | OK
| Delivery of progress report to JTS | LP | All | 7 | 910 | 136.5 |  |  |  | 1046.5 | OK |  |  |  | 0 |  |  |  | 0 |  | 91 | 13.65 |  | 0 |  | 104.65 |  | 136.5 | 20.475 |  | 0 |  | 156.975 |  | 182 | 27.3 |  | 0 |  | 209.3 |  | 136.5 | 20.475 |  | 0 |  | 156.975 |  | 136.5 | 20.475 |  | 0 |  | 156.975 |  |  | 0 |  |  |  | 0 |  | 136.5 | 20.475 |  | 0 |  | 156.975 |  | 91 | 13.65 |  | 0 |  | 104.65 |  | 910 | 136.5 | 0 | 0 | 0 | 1046.5 | OK
| Delivery of final report to JTS | LP | All | 2 | 260 | 39 |  |  |  | 299 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 260 | 39 |  |  |  | 299 |  | 260 | 39 | 0 | 0 | 0 | 299 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 14170 | 2125.5 | 4800 | 18000 | 0 | 39095.5 | OK |  |  | 2288 | 343.2 | 1714.2857 | 2250 | 0 | 6595.4857 |  | 1040 | 156 | 514.2857 | 1500 | 0 | 3210.2857 |  | 2782 | 417.3 | 514.2857 | 3750 | 0 | 7463.5857 |  | 2873 | 430.95 | 514.2857 | 3000 | 0 | 6818.2357 |  | 2587 | 388.05 | 514.2857 | 6000 | 0 | 9489.3357 |  | 819 | 122.85 | 0 | 0 | 0 | 941.85 |  | 78 | 11.7 | 514.2857 | 1500 | 0 | 2103.9857 |  | 819 | 122.85 | 0 | 0 | 0 | 941.85 |  | 884 | 132.6 | 514.2857 | 0 | 0 | 1530.8857 |  | 14170 | 2125.5 | 4800 | 18000 | 0 | 39095.5 | OK
| COMMUNICATION | [9 empty] | OK | [71 empty] | OK
| Planning and start-up | [9 empty] | OK | [71 empty] | OK
| Communication and knowledge sharing strategy | PP5-VPR | All | 1 | 130 | 19.5 |  |  |  | 149.5 | OK |  |  | 130 | 19.5 |  |  |  | 149.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 130 | 19.5 | 0 | 0 | 0 | 149.5 | OK
| Launching event | LP | All | 3 | 390 | 58.5 | 600 |  |  | 1048.5 | OK |  |  | 273 | 40.95 | 600 | 0 |  | 913.95 |  | 117 | 17.55 |  | 0 |  | 134.55 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 390 | 58.5 | 600 | 0 | 0 | 1048.5 | OK
| Briefing brochure linked to the Launching event about the project and the topic adressed | PP5-VPR | All | 4 | 520 | 78 |  | 2000 |  | 2598 | OK |  |  | 364 | 54.6 |  |  |  | 418.6 |  | 156 | 23.4 |  | 2000 |  | 2179.4 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 520 | 78 | 0 | 2000 | 0 | 2598 | OK
| Poster (obligatory) | PP5-VPR | All | 2 | 260 | 39 |  | 300 |  | 599 | OK |  |  | 260 | 39 |  | 300 |  | 599 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 260 | 39 | 0 | 300 | 0 | 599 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Website and social media | [9 empty] | OK | [71 empty] | OK
| Launching of website and regular update of the website | PP5-VPR | All | 7 | 910 | 136.5 |  |  |  | 1046.5 | OK |  |  | 91 | 13.65 |  |  |  | 104.65 |  | 45.5 | 6.825 |  |  |  | 52.325 |  | 182 | 27.3 |  |  |  | 209.3 |  | 227.5 | 34.125 |  |  |  | 261.625 |  | 182 | 27.3 |  |  |  | 209.3 |  | 45.5 | 6.825 |  |  |  | 52.325 |  | 45.5 | 6.825 |  |  |  | 52.325 |  | 45.5 | 6.825 |  |  |  | 52.325 |  | 45.5 | 6.825 |  |  |  | 52.325 |  | 910 | 136.5 | 0 | 0 | 0 | 1046.5 | OK
| Social media presence | PP5-VPR | All | 3 | 390 | 58.5 |  |  |  | 448.5 | OK |  |  | 39 | 5.85 |  |  |  | 44.85 |  | 19.5 | 2.925 |  |  |  | 22.425 |  | 78 | 11.7 |  |  |  | 89.7 |  | 97.5 | 14.625 |  |  |  | 112.125 |  | 78 | 11.7 |  |  |  | 89.7 |  | 19.5 | 2.925 |  |  |  | 22.425 |  | 19.5 | 2.925 |  |  |  | 22.425 |  | 19.5 | 2.925 |  |  |  | 22.425 |  | 19.5 | 2.925 |  |  |  | 22.425 |  | 390 | 58.5 | 0 | 0 | 0 | 448.5 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Paticipation in other events | [9 empty] | OK | [71 empty] | OK
| INTERREG Europe events | PP5-VPR, LP- VRW | n.a. |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Dissemination at transnational events (presenter or exhibitioner) | PP5-VPR | All | 3 | 390 | 58.5 | 600 |  |  | 1048.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 390 | 58.5 | 600 |  |  | 1048.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 390 | 58.5 | 600 | 0 | 0 | 1048.5 | OK
| Dissemination at national events (presenter or exhibitioner) | PP5-VPR | All | 4 | 520 | 78 | 600 |  |  | 1198 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 260 | 39 | 300 |  |  | 599 |  | 260 | 39 | 300 |  |  | 599 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 520 | 78 | 600 | 0 | 0 | 1198 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Communication materials/tools | [9 empty] | OK | [71 empty] | OK
| Press releases | PP5-VPR | TWG meeting/event organisers | 4 | 520 | 78 |  |  |  | 598 | OK |  |  |  | 0 |  |  |  | 0 |  | 130 | 19.5 |  |  |  | 149.5 |  | 130 | 19.5 |  |  |  | 149.5 |  | 130 | 19.5 |  |  |  | 149.5 |  | 130 | 19.5 |  |  |  | 149.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 520 | 78 | 0 | 0 | 0 | 598 | OK
| Newsletters on project level | PP5-VPR | All | 5 | 650 | 97.5 |  |  |  | 747.5 | OK |  |  |  | 0 |  |  |  | 0 |  | 162.5 | 24.375 |  | 0 |  | 186.875 |  | 162.5 | 24.375 |  |  |  | 186.875 |  | 162.5 | 24.375 |  |  |  | 186.875 |  | 162.5 | 24.375 |  |  |  | 186.875 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 650 | 97.5 | 0 | 0 | 0 | 747.5 | OK
| Project video | PP5-VPR | All | 3 | 390 | 58.5 |  |  |  | 448.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 390 | 58.5 |  | 0 |  | 448.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 390 | 58.5 | 0 | 0 | 0 | 448.5 | OK
| Policy learning Synthesis report | LP- VRW, PP5-VPR | All | 1 | 130 | 19.5 |  |  |  | 149.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 130 | 19.5 |  |  |  | 149.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 130 | 19.5 | 0 | 0 | 0 | 149.5 | OK
| Dissemination materials on exchanged experience targeting regions outside the partnership | PP4-VPR | All |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Mid term event | PP4-VPR | All partners |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Final event | PP2- TCC | All partners | 3 | 390 | 58.5 | 600 |  |  | 1048.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 390 | 58.5 | 600 | 0 |  | 1048.5 |  | 390 | 58.5 | 600 | 0 | 0 | 1048.5 | OK
| Visualisation materials for institutional, stakeholder meetings | PP5- VPR | LP, PP2, PP3, PP4, PP5 | 10 | 1300 | 195 |  | 3000 |  | 4495 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 1500 |  | 1500 |  | 650 | 97.5 |  | 1500 |  | 2247.5 |  | 325 | 48.75 |  |  |  | 373.75 |  | 325 | 48.75 |  |  |  | 373.75 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1300 | 195 | 0 | 3000 | 0 | 4495 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 6890 | 1033.5 | 2400 | 5300 | 0 | 15623.5 | OK |  |  | 1157 | 173.55 | 600 | 300 | 0 | 2230.55 |  | 630.5 | 94.575 | 0 | 3500 | 0 | 4225.075 |  | 1202.5 | 180.375 | 0 | 1500 | 0 | 2882.875 |  | 1592.5 | 238.875 | 900 | 0 | 0 | 2731.375 |  | 1657.5 | 248.625 | 300 | 0 | 0 | 2206.125 |  | 65 | 9.75 | 0 | 0 | 0 | 74.75 |  | 65 | 9.75 | 0 | 0 | 0 | 74.75 |  | 65 | 9.75 | 0 | 0 | 0 | 74.75 |  | 455 | 68.25 | 600 | 0 | 0 | 1123.25 |  | 6890 | 1033.5 | 2400 | 5300 | 0 | 15623.5 | OK
| INTERREGIONAL POLICY LEARNING | [9 empty] | OK | [71 empty] | OK
| Interregional thematic organisation | [9 empty] | OK | [71 empty] | OK
| Setting up Thematic Working Group (TWG) | LP | All partners | 2 | 260 | 39 |  |  |  | 299 | OK |  |  | 260 | 39 |  |  |  | 299 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 260 | 39 | 0 | 0 | 0 | 299 | OK
| TWG Rules of procedure | LP | All partners |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TWG meetings linked to thematic implementation | LP | All partners | 21 | 2730 | 409.5 | 3600 |  |  | 6739.5 | OK |  |  | 54.6 | 8.19 | 514.2857 |  |  | 577.0757 |  | 273 | 40.95 | 514.2857 |  |  | 828.2357 |  | 819 | 122.85 | 514.2857 |  |  | 1456.1357 |  | 819 | 122.85 | 514.2857 |  |  | 1456.1357 |  | 546 | 81.9 | 514.2857 |  |  | 1142.1857 |  |  | 0 |  |  |  | 0 |  | 109.2 | 16.38 | 514.2857 |  |  | 639.8657 |  |  | 0 |  |  |  | 0 |  | 109.2 | 16.38 | 514.2857 |  |  | 639.8657 |  | 2730 | 409.5 | 3600 | 0 | 0 | 6739.5 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Stakeholder involvement and organisational learning | [9 empty] | OK | [71 empty] | OK
| Setting up stakeholder & institutional learning groups | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 5 | 650 | 97.5 |  |  |  | 747.5 | OK |  |  | 455 | 68.25 |  |  |  | 523.25 |  | 195 | 29.25 |  |  |  | 224.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 650 | 97.5 | 0 | 0 | 0 | 747.5 | OK
| Interactive training on stakeholder involvement/institutional learning for the Regional Managers | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 4 | 520 | 78 |  |  |  | 598 | OK |  |  | 260 | 39 |  |  |  | 299 |  | 260 | 39 |  |  |  | 299 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 520 | 78 | 0 | 0 | 0 | 598 | OK
| Methodology for regional Roadmaps | PP2- TCC | All partners | 1 | 130 | 19.5 |  |  |  | 149.5 | OK |  |  | 130 | 19.5 |  |  |  | 149.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 130 | 19.5 | 0 | 0 | 0 | 149.5 | OK
| regional Roadmaps (on the institutional/stakeholder involvement process) elaborated and quality controled | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 20 | 2600 | 390 |  |  |  | 2990 | OK |  |  | 780 | 117 |  |  |  | 897 |  | 1820 | 273 |  |  |  | 2093 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2600 | 390 | 0 | 0 | 0 | 2990 | OK
| Regional Opening meeting for stakeholders (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 1950 | 292.5 |  | 1500 |  | 3742.5 | OK |  |  | 585 | 87.75 |  |  |  | 672.75 |  | 1365 | 204.75 | 0 | 1500 |  | 3069.75 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1950 | 292.5 | 0 | 1500 | 0 | 3742.5 | OK
| Meetings with stakeholder groups and Institutional learning groups / involvement in action plan implementation + Synergy Sessions with Institutional departments | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 50 | 6500 | 975 |  | 3500 |  | 10975 | OK |  |  |  | 0 |  |  |  | 0 |  | 650 | 97.5 |  | 350 |  | 1097.5 |  | 1625 | 243.75 |  | 875 |  | 2743.75 |  | 2600 | 390 |  | 1400 |  | 4390 |  | 1625 | 243.75 |  | 875 |  | 2743.75 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 6500 | 975 | 0 | 3500 | 0 | 10975 | OK
| Phase 1 closing stakeholder session (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 1950 | 292.5 |  | 1500 |  | 3742.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1950 | 292.5 | 0 | 1500 |  | 3742.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1950 | 292.5 | 0 | 1500 | 0 | 3742.5 | OK
| Synergy session for personnel of partner organisations | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 18 | 2340 | 351 |  |  |  | 2691 | OK |  |  |  | 0 |  |  |  | 0 |  | 585 | 87.75 |  |  |  | 672.75 |  | 585 | 87.75 |  |  |  | 672.75 |  | 585 | 87.75 |  |  |  | 672.75 |  | 585 | 87.75 |  |  |  | 672.75 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2340 | 351 | 0 | 0 | 0 | 2691 | OK
| Thematic coordination of stakeholder involvement | PP2- TCC | LP- VRW |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Analysis | [9 empty] | OK | [71 empty] | OK
| Joint methodology for regional State of Arts | PP4 - PD | All partners | 12 | 1560 | 234 |  |  |  | 1794 | OK |  |  |  | 0 |  |  |  | 0 |  | 1560 | 234 |  |  |  | 1794 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1560 | 234 | 0 | 0 | 0 | 1794 | OK
| Regional State of Arts (including good practice inventory + list of ingredients for change) | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 | 40 | 5200 | 780 |  |  |  | 5980 | OK |  |  |  | 0 |  |  |  | 0 |  | 5200 | 780 | 0 | 0 |  | 5980 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 5200 | 780 | 0 | 0 | 0 | 5980 | OK
| Transnational audit visits to each region by experts delegated by 2 other partners | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Project level menu of good practices | PP4 - PD | LP- VRW | 20 | 2600 | 390 |  |  |  | 2990 | OK |  |  |  | 0 |  |  |  | 0 |  | 2600 | 390 |  |  |  | 2990 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2600 | 390 | 0 | 0 | 0 | 2990 | OK
| Thematic coordination of analysis phase | PP4 - PD | LP- VRW | 20 | 2600 | 390 |  | 7000 |  | 9990 | OK |  |  |  | 0 |  |  |  | 0 |  | 2600 | 390 | 0 | 7000 |  | 9990 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2600 | 390 | 0 | 7000 | 0 | 9990 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Knowledge exchange (good practice transfer) | [9 empty] | OK | [71 empty] | OK
| Guidelines (including matching learning needs with good practices)/methodology and templates for knowledge sharing | LP- VRW | All partners | 2 | 260 | 39 |  |  |  | 299 | OK |  |  |  | 0 |  |  |  | 0 |  | 260 | 39 |  |  |  | 299 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 260 | 39 | 0 | 0 | 0 | 299 | OK
| 3 Transnational Exchange Session meetings of 3 days length (for individual staff members of partners + appr. 3 stakeholders per partner region) | LP- VRW | All partners | 50 | 6500 | 975 | 3200 | 7800 |  | 18475 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4550 | 682.5 | 2240 | 5460 |  | 12932.5 |  | 1950 | 292.5 | 960 | 2340 |  | 5542.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 6500 | 975 | 3200 | 7800 | 0 | 18475 | OK
| Summary reports on the Exchange Sessions | LP- VRW | All partners | 5 | 650 | 97.5 |  |  |  | 747.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 455 | 68.25 |  |  |  | 523.25 |  | 195 | 29.25 |  |  |  | 224.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 650 | 97.5 | 0 | 0 | 0 | 747.5 | OK
| Thematic coordination of knowledge exchange | LP- VRW | n.a. |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Action plan drafting | [9 empty] | OK | [71 empty] | OK
| Project level Guideline and joint training on action plan development | PP3 - MCM | All partners | 8 | 1040 | 156 |  |  |  | 1196 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1040 | 156 |  |  |  | 1196 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1040 | 156 | 0 | 0 | 0 | 1196 | OK
| Detailed Action Plan methodology on regional level/workplan | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 0 | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Elaboration of Action Plans / policy instrument | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 40 | 5200 | 780 |  | 15000 |  | 20980 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2600 | 390 |  | 7500 |  | 10490 |  | 2600 | 390 |  | 7500 |  | 10490 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 5200 | 780 | 0 | 15000 | 0 | 20980 | OK
| Cross- reading exercise | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 5 | 650 | 97.5 |  |  |  | 747.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 650 | 97.5 |  |  |  | 747.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 650 | 97.5 | 0 | 0 | 0 | 747.5 | OK
| Final quality control of Action Plans | PP3 - MCM | n.a. | 2 | 260 | 39 |  |  |  | 299 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 260 | 39 |  |  |  | 299 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 260 | 39 | 0 | 0 | 0 | 299 | OK
| Consistency check of Action Plans on regional level | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 3 | 390 | 58.5 |  |  |  | 448.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 390 | 58.5 |  |  |  | 448.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 390 | 58.5 | 0 | 0 | 0 | 448.5 | OK
| Thematic coordination of action planning | PP3 - MCM | LP- VRW |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Action plan implementation follow-up(24 months) |  |  |  |  | 0 |  |  |  |  | OK |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 |  |  |  |  | OK
| Monitoring of the implementation of the action plans | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 12 | 1560 | 234 |  |  |  | 1794 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 390 | 59 |  |  |  | 449 |  | 390 | 58.5 |  |  |  | 448.5 |  | 390 | 58.5 |  |  |  | 448.5 |  | 390 | 58.5 |  |  |  | 448.5 |  | 1560 | 234.5 | 0 | 0 | 0 | 1794.5 | ERROR
| Summary on the level of achievements / policy instrument | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 4 | 520 | 78 |  |  |  | 598 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 260 | 39 |  |  |  | 299 |  | 260 | 38.5 |  |  |  | 298.5 |  | 520 | 77.5 | 0 | 0 | 0 | 597.5 | ERROR
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[11 empty] | OK | [71 empty] | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 48620 | 7293 | 6800 | 36300 | 0 | 99013 | OK |  |  | 2524.6 | 378.69 | 514.2857 | 0 | 0 | 3417.5757 |  | 17368 | 2605.2 | 514.2857 | 8850 | 0 | 29337.4857 |  | 8034 | 1205.1 | 2754.2857 | 6335 | 0 | 18328.3857 |  | 9789 | 1468.35 | 1474.2857 | 11240 | 0 | 23971.6357 |  | 8606 | 1290.9 | 514.2857 | 9875 | 0 | 20286.1857 |  | 390 | 59 | 0 | 0 | 0 | 449 |  | 499.2 | 74.88 | 514.2857 | 0 | 0 | 1088.3657 |  | 650 | 97.5 | 0 | 0 | 0 | 747.5 |  | 759.2 | 113.38 | 514.2857 | 0 | 0 | 1386.8657 |  | 48620 | 7293 | 6800 | 36300 | 0 | 99013 | OK
| TOTAL |  |  |  | 69680 | 10452 | 14000 | 59600 | 0 | 153732 | OK |  |  | 5969.6 | 895.44 | 2828.5714 | 2550 | 0 | 12243.6114 |  | 19038.5 | 2855.775 | 1028.5714 | 13850 | 0 | 36772.8464 |  | 12018.5 | 1802.775 | 3268.5714 | 11585 | 0 | 28674.8464 |  | 14254.5 | 2138.175 | 2888.5714 | 14240 | 0 | 33521.2464 |  | 12850.5 | 1927.575 | 1328.5714 | 15875 | 0 | 31981.6464 |  | 1274 | 191.6 | 0 | 0 | 0 | 1465.6 |  | 642.2 | 96.33 | 1028.5714 | 1500 | 0 | 3267.1014 |  | 1534 | 230.1 | 0 | 0 | 0 | 1764.1 |  | 2098.2 | 314.23 | 1628.5714 | 0 | 0 | 4041.0014 |  | 69680 | 10452 | 14000 | 59600 | 0 | 153732 | OK
[5 empty] | OK | OK | OK | OK | OK | OK | OK |  |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK
| Application Form budget |  |  |  | Staff | Overhead | T & A | External expertise | Equip. | TOTAL |  | ERDF | 130672.2
|  |  | PP4 - Pons Danubii |  | 69680 | 10452 | 14000 | 59600 | 0 | 153732 |  | Co-finance | 23059.8
[12 empty] | TOTAL | 153732
| Application Form budget - Spending Forecast | Period | Budget | % | Rounded |  | Application Form budget - External expertise | Type of cost |  | Budget |  |  | OK
|  | Preparation | 0 | 0% | 0 |  |  | FLC cost
|  | Semester 1 | 12243.6114 | 7.964% | 12244 |  |  | Project/financial/comm. management |  | 15000
|  | Semester 2 | 36772.8464 | 23.92% | 36773 |  |  | Meetings: partner meeting |  | 6000
|  | Semester 3 | 28674.8464 | 18.65% | 28675 |  |  | Meetings: dissemination event
|  | Semester 4 | 33521.2464 | 21.8% | 33521 |  |  |  |  | 0
|  | Semester 5 | 31981.6464 | 20.8% | 31982 |  |  | Meetings: stakeholder group |  | 6500
|  | Semester 6 | 1465.6 | 0.9533% | 1466 |  |  | Travel & acc. cost: non staff |  | 4800
|  | Semester 7 | 3267.1014 | 2.125% | 3267 |  |  | Publication and dissemination costs |  | 5300
|  | Semester 8 | 1764.1 | 1.148% | 1764 |  |  | External support for the exc. of experience |  | 22000
|  | Semester 9 | 4041.0014 | 2.629% | 4040 |  |  | Other
|  |  |  | 0 |  |  |  | TOTAL |  | 59600
|  | TOTAL | 153732 | 1 | 153732 |  |  |  |  | OK
|  |  | OK |  | OK
| % check tables | Budget lines | % |  |  |  | Application Form budget - Equipment | Type of cost |  | Budget
|  | Staff | 45.33% |  |  |  |  | Office eqiupment
|  | Overhead | 6.799% |  |  |  |  | Other
|  | T & A | 9.107% |  |  |  |  | TOTAL |  | 0
|  | Ext. expertise | 38.77% | [6 empty] | OK
|  | Eqipment | 0%
|  | TOTAL | 100%
|  | CP | %
|  | Management CP | 25.43%
|  | Communication CP | 10.16%
|  | Thematic CP | 64.41%
|  | TOTAL | 100%
|  | Austria | 262
|  | Belgium | 278
|  | Czech Republic | 118
|  | Denmark | 280
|  | Estonia | 110
|  | Finland | 232
|  | France | 233
|  | Germany | 253
|  | Greece | 148
|  | Hungary | 121
|  | Ireland | 286
|  | Italy | 200
|  | Netherlands | 275
|  | Poland | 131
|  | Portugal | 137
|  | Slovak Republic | 130
|  | Slovenia | 185
|  | Spain | 202
|  | Sweden | 236
|  | United Kingdom | 238
|  | Bulgaria | 80
|  | Croatia | 100
|  | Cyprus | 120
|  | Latvia | 104
|  | Lithuania | 100
|  | Luxemburg | 324
|  | Malta | 140
|  | Romania | 80
|  | ERDF | 75%
|  | ERDF | 85%
Note on I23: Tóth Gábor: Partner level project management support
Note on I24: Tóth Gábor: Organisation of the SG and TWG meeting to be held in month 26
Note on I28: Tóth Gábor: FLC cost
Note on I37: Tóth Gábor: Translation and printing of the briefing brouchure
Note on I38: Tóth Gábor: Printing cost of the poster
Note on I55: Tóth Gábor: Printing cost
Note on I56: Tóth Gábor: Non-staff stakeholder travel (2 person)
Note on I58: Tóth Gábor: Design and printing cost
Note on I74: Tóth Gábor: Cost for organisieng the meeting (incuding networking activities)
Note on I75: Tóth Gábor: Organisation cost
Note on I76: Tóth Gábor: Cost for organisieng the meeting (incuding networking activities)
Note on I84: Tóth Gábor: Organisation cost for hosting the visit
Note on I86: Tóth Gábor: Support for the coordination of the activity and for the preparation of the Regional State of the Art methodology
Note on I91: Tóth Gábor: Non-staff stakeholder travel (3 person): 4800 EUR Organisation of 1 Transnational exchange session: 3000 EUR
Note on I99: Tóth Gábor: External support for the preparation of the Action Plan

## PP5_VPR
PP5 - VPR |  |  |  | Country --> | [5 empty] | Latvia |  |  | Semester 1 (month 1-6) | [6 empty] | Semester 2 (month 7-12) | [6 empty] | Semester 3 (month 13-18) | [6 empty] | Semester 4 (month 19-24) | [6 empty] | Semester 5 (month 25-30) | [6 empty] | Semester 6 (month 31-36) | [6 empty] | Semester 7 (month 37-42) | [6 empty] | Semester 8 (month 43-48) | [6 empty] | Semester 9 (month 49-54) | [6 empty] | TOTAL
DAILY FEE |  | 120 |  |  | Travel cost 1 person 2 nights |  |  | 600 | ERDF | 0.85
[5 empty] | Travel cost 1 person 3 nights |  |  | 800
161510
Action | ACTIVITIES | Partner in charge | Participating
|  |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL
|  |  |  | days | total | [7 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total
| PREPARATION | LP
| Project proposal preparation |  |  |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | OK |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| PROJECT MANAGEMENT AND COORDINATION | LP | [8 empty] | OK | [71 empty] | OK
| Contractualisation and start-up | [9 empty] | OK | [71 empty] | OK
| Subsidy Contract | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Partnership Agreement | LP | All | 1 | 120 | 18 |  |  |  | 138 | OK |  |  | 120 | 18 |  |  |  | 138 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 120 | 18 | 0 | 0 | 0 | 138 | OK
| Appointment FLC | LP | All | 2 | 240 | 36 |  |  |  | 276 | OK |  |  | 240 | 36 |  |  |  | 276 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 240 | 36 | 0 | 0 | 0 | 276 | OK
| Management and financial handbook | LP | All | 1 | 120 | 18 |  |  |  | 138 | OK |  |  | 120 | 18 |  |  |  | 138 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 120 | 18 | 0 | 0 | 0 | 138 | OK
| Rules of Procedures for the PR | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Rules of Procedures for the SG | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Kick-off meeting | LP | All | 8 | 960 | 144 | 1200 |  |  | 2304 | OK |  |  | 960 | 144 | 1200 | 0 |  | 2304 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 960 | 144 | 1200 | 0 | 0 | 2304 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Project Management and coordination | [9 empty] | OK | [71 empty] | OK
| Daily project management | LP | All | 30 | 3600 | 540 |  |  |  | 4140 | OK |  |  | 540 | 81 |  | 0 | 0 | 621 |  | 180 | 27 |  | 0 |  | 207 |  | 1080 | 162 |  | 0 |  | 1242 |  | 720 | 108 |  | 0 |  | 828 |  | 1080 | 162 |  | 0 |  | 1242 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3600 | 540 | 0 | 0 | 0 | 4140 | OK
| Steering Group meeting linked with thematic meeting | LP | All | 15 | 1800 | 270 | 3600 |  |  | 5670 | OK |  |  | 36 | 5.4 | 514.2857 |  |  | 555.6857 |  | 180 | 27 | 514.2857 |  |  | 721.2857 |  | 540 | 81 | 514.2857 |  |  | 1135.2857 |  | 540 | 81 | 514.2857 |  |  | 1135.2857 |  | 360 | 54 | 514.2857 |  |  | 928.2857 |  |  | 0 |  |  |  | 0 |  | 72 | 10.8 | 514.2857 |  |  | 597.0857 |  |  | 0 |  |  |  | 0 |  | 72 | 10.8 | 514.2857 |  |  | 597.0857 |  | 1800 | 270 | 3600 | 0 | 0 | 5670 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Reporting | [9 empty] | OK | [71 empty] | OK
| Internal financial monitoring/budget revision | LP | All | 8 | 960 | 144 |  |  |  | 1104 | OK |  |  | 96 | 14.4 |  |  |  | 110.4 |  | 96 | 14.4 |  |  |  | 110.4 |  | 192 | 28.8 |  |  |  | 220.8 |  | 384 | 57.6 |  |  |  | 441.6 |  | 192 | 28.8 |  |  |  | 220.8 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 960 | 144 | 0 | 0 | 0 | 1104 | OK
| Preparation of partner level progress report | LP | All | 35 | 4200 | 630 |  |  |  | 4830 | OK |  |  |  | 0 |  |  |  | 0 |  | 420 | 63 |  | 0 |  | 483 |  | 630 | 94.5 |  | 0 |  | 724.5 |  | 840 | 126 |  | 0 |  | 966 |  | 630 | 94.5 |  | 0 |  | 724.5 |  | 630 | 94.5 |  | 0 |  | 724.5 |  |  | 0 |  |  |  | 0 |  | 630 | 94.5 |  | 0 |  | 724.5 |  | 420 | 63 |  | 0 |  | 483 |  | 4200 | 630 | 0 | 0 | 0 | 4830 | OK
| Delivery of progress report to JTS | LP | All | 7 | 840 | 126 |  |  |  | 966 | OK |  |  |  | 0 |  |  |  | 0 |  | 84 | 12.6 |  | 0 |  | 96.6 |  | 126 | 18.9 |  | 0 |  | 144.9 |  | 168 | 25.2 |  | 0 |  | 193.2 |  | 126 | 18.9 |  | 0 |  | 144.9 |  | 126 | 18.9 |  | 0 |  | 144.9 |  |  | 0 |  |  |  | 0 |  | 126 | 18.9 |  | 0 |  | 144.9 |  | 84 | 12.6 |  | 0 |  | 96.6 |  | 840 | 126 | 0 | 0 | 0 | 966 | OK
| Delivery of final report to JTS | LP | All | 2 | 240 | 36 |  |  |  | 276 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 240 | 36 |  |  |  | 276 |  | 240 | 36 | 0 | 0 | 0 | 276 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 13080 | 1962 | 4800 | 0 | 0 | 19842 | OK |  |  | 2112 | 316.8 | 1714.2857 | 0 | 0 | 4143.0857 |  | 960 | 144 | 514.2857 | 0 | 0 | 1618.2857 |  | 2568 | 385.2 | 514.2857 | 0 | 0 | 3467.4857 |  | 2652 | 397.8 | 514.2857 | 0 | 0 | 3564.0857 |  | 2388 | 358.2 | 514.2857 | 0 | 0 | 3260.4857 |  | 756 | 113.4 | 0 | 0 | 0 | 869.4 |  | 72 | 10.8 | 514.2857 | 0 | 0 | 597.0857 |  | 756 | 113.4 | 0 | 0 | 0 | 869.4 |  | 816 | 122.4 | 514.2857 | 0 | 0 | 1452.6857 |  | 13080 | 1962 | 4800 | 0 | 0 | 19842 | OK
| COMMUNICATION | [9 empty] | OK | [71 empty] | OK
| Planning and start-up | [9 empty] | OK | [71 empty] | OK
| Communication and knowledge sharing strategy | PP5-VPR | All | 15 | 1800 | 270 |  |  |  | 2070 | OK |  |  | 1800 | 270 |  |  |  | 2070 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1800 | 270 | 0 | 0 | 0 | 2070 | OK
| Launching event | LP | All | 6 | 720 | 108 | 600 |  |  | 1428 | OK |  |  | 504 | 75.6 | 600 | 0 |  | 1179.6 |  | 216 | 32.4 |  | 0 |  | 248.4 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 720 | 108 | 600 | 0 | 0 | 1428 | OK
| Briefing brochure linked to the Launching event about the project and the topic adressed | PP5-VPR | All | 12 | 1440 | 216 |  | 6000 |  | 7656 | OK |  |  | 1008 | 151.2 |  |  |  | 1159.2 |  | 432 | 64.8 |  | 6000 |  | 6496.8 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1440 | 216 | 0 | 6000 | 0 | 7656 | OK
| Poster (obligatory) | PP5-VPR | All | 10 | 1200 | 180 |  | 300 |  | 1680 | OK |  |  | 1200 | 180 |  | 300 |  | 1680 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1200 | 180 | 0 | 300 | 0 | 1680 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Website and social media | [9 empty] | OK | [71 empty] | OK
| Launching of website and regular update of the website | PP5-VPR | All | 35 | 4200 | 630 |  |  |  | 4830 | OK |  |  | 420 | 63 |  |  |  | 483 |  | 210 | 31.5 |  |  |  | 241.5 |  | 840 | 126 |  |  |  | 966 |  | 1050 | 157.5 |  |  |  | 1207.5 |  | 840 | 126 |  |  |  | 966 |  | 210 | 31.5 |  |  |  | 241.5 |  | 210 | 31.5 |  |  |  | 241.5 |  | 210 | 31.5 |  |  |  | 241.5 |  | 210 | 31.5 |  |  |  | 241.5 |  | 4200 | 630 | 0 | 0 | 0 | 4830 | OK
| Social media presence | PP5-VPR | All | 35 | 4200 | 630 |  |  |  | 4830 | OK |  |  | 420 | 63 |  |  |  | 483 |  | 210 | 31.5 |  |  |  | 241.5 |  | 840 | 126 |  |  |  | 966 |  | 1050 | 157.5 |  |  |  | 1207.5 |  | 840 | 126 |  |  |  | 966 |  | 210 | 31.5 |  |  |  | 241.5 |  | 210 | 31.5 |  |  |  | 241.5 |  | 210 | 31.5 |  |  |  | 241.5 |  | 210 | 31.5 |  |  |  | 241.5 |  | 4200 | 630 | 0 | 0 | 0 | 4830 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Paticipation in other events | [9 empty] | OK | [71 empty] | OK
| INTERREG Europe events | PP5-VPR, LP- VRW | n.a. | 12 | 1440 | 216 | 1800 |  |  | 3456 | OK |  |  | 144 | 21.6 | 180 |  |  | 345.6 |  | 144 | 21.6 | 180 |  |  | 345.6 |  | 144 | 21.6 | 180 |  |  | 345.6 |  | 144 | 21.6 | 180 |  |  | 345.6 |  | 288 | 43.2 | 360 |  |  | 691.2 |  | 144 | 21.6 | 180 |  |  | 345.6 |  | 144 | 21.6 | 180 |  |  | 345.6 |  | 144 | 21.6 | 180 |  |  | 345.6 |  | 144 | 21.6 | 180 |  |  | 345.6 |  | 1440 | 216 | 1800 | 0 | 0 | 3456 | OK
| Dissemination at transnational events (presenter or exhibitioner) | PP5-VPR | All | 10 | 1200 | 180 | 1800 |  |  | 3180 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1200 | 180 | 1800 |  |  | 3180 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1200 | 180 | 1800 | 0 | 0 | 3180 | OK
| Dissemination at national events (presenter or exhibitioner) | PP5-VPR | All | 6 | 720 | 108 | 600 |  |  | 1428 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 360 | 54 | 300 |  |  | 714 |  | 360 | 54 | 300 |  |  | 714 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 720 | 108 | 600 | 0 | 0 | 1428 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Communication materials/tools | [9 empty] | OK | [71 empty] | OK
| Press releases | PP5-VPR | TWG meeting/event organisers | 4 | 480 | 72 |  |  |  | 552 | OK |  |  |  | 0 |  |  |  | 0 |  | 120 | 18 |  |  |  | 138 |  | 120 | 18 |  |  |  | 138 |  | 120 | 18 |  |  |  | 138 |  | 120 | 18 |  |  |  | 138 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 480 | 72 | 0 | 0 | 0 | 552 | OK
| Newsletters on project level | PP5-VPR | All | 30 | 3600 | 540 |  | 2000 |  | 6140 | OK |  |  |  | 0 |  |  |  | 0 |  | 900 | 135 |  | 2000 |  | 3035 |  | 900 | 135 |  |  |  | 1035 |  | 900 | 135 |  |  |  | 1035 |  | 900 | 135 |  |  |  | 1035 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 3600 | 540 | 0 | 2000 | 0 | 6140 | OK
| Project video | PP5-VPR | All | 20 | 2400 | 360 |  | 4000 |  | 6760 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2400 | 360 |  | 4000 |  | 6760 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2400 | 360 | 0 | 4000 | 0 | 6760 | OK
| Policy learning Synthesis report | LP- VRW, PP5-VPR | All | 20 | 2400 | 360 |  |  |  | 2760 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2400 | 360 |  |  |  | 2760 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2400 | 360 | 0 | 0 | 0 | 2760 | OK
| Dissemination materials on exchanged experience targeting regions outside the partnership | PP4-VPR | All |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Mid term event | PP4-VPR | All partners |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Final event | PP2- TCC | All partners | 10 | 1200 | 180 | 600 |  |  | 1980 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1200 | 180 | 600 | 0 |  | 1980 |  | 1200 | 180 | 600 | 0 | 0 | 1980 | OK
| Visualisation materials for institutional, stakeholder meetings | PP5- VPR | LP, PP2, PP3, PP4, PP5 | 20 | 2400 | 360 |  | 3000 |  | 5760 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 1500 |  | 1500 |  | 1200 | 180 |  | 1500 |  | 2880 |  | 600 | 90 |  |  |  | 690 |  | 600 | 90 |  |  |  | 690 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2400 | 360 | 0 | 3000 | 0 | 5760 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 29400 | 4410 | 5400 | 15300 | 0 | 54510 | OK |  |  | 5496 | 824.4 | 780 | 300 | 0 | 7400.4 |  | 2232 | 334.8 | 180 | 9500 | 0 | 12246.8 |  | 4044 | 606.6 | 180 | 1500 | 0 | 6330.6 |  | 5424 | 813.6 | 2280 | 0 | 0 | 8517.6 |  | 8748 | 1312.2 | 660 | 4000 | 0 | 14720.2 |  | 564 | 84.6 | 180 | 0 | 0 | 828.6 |  | 564 | 84.6 | 180 | 0 | 0 | 828.6 |  | 564 | 84.6 | 180 | 0 | 0 | 828.6 |  | 1764 | 264.6 | 780 | 0 | 0 | 2808.6 |  | 29400 | 4410 | 5400 | 15300 | 0 | 54510 | OK
| INTERREGIONAL POLICY LEARNING | [9 empty] | OK | [71 empty] | OK
| Interregional thematic organisation | [9 empty] | OK | [71 empty] | OK
| Setting up Thematic Working Group (TWG) | LP | All partners | 2 | 240 | 36 |  |  |  | 276 | OK |  |  | 240 | 36 |  |  |  | 276 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 240 | 36 | 0 | 0 | 0 | 276 | OK
| TWG Rules of procedure | LP | All partners |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TWG meetings linked to thematic implementation | LP | All partners | 35 | 4200 | 630 | 3600 | 3000 |  | 11430 | OK |  |  | 84 | 12.6 | 514.2857 |  |  | 610.8857 |  | 420 | 63 | 514.2857 |  |  | 997.2857 |  | 1260 | 189 | 514.2857 |  |  | 1963.2857 |  | 1260 | 189 | 514.2857 |  |  | 1963.2857 |  | 840 | 126 | 514.2857 | 3000 |  | 4480.2857 |  |  | 0 |  |  |  | 0 |  | 168 | 25.2 | 514.2857 |  |  | 707.4857 |  |  | 0 |  |  |  | 0 |  | 168 | 25.2 | 514.2857 |  |  | 707.4857 |  | 4200 | 630 | 3600 | 3000 | 0 | 11430 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Stakeholder involvement and organisational learning | [9 empty] | OK | [71 empty] | OK
| Setting up stakeholder & institutional learning groups | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 5 | 600 | 90 |  |  |  | 690 | OK |  |  | 420 | 63 |  |  |  | 483 |  | 180 | 27 |  |  |  | 207 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 600 | 90 | 0 | 0 | 0 | 690 | OK
| Interactive training on stakeholder involvement/institutional learning for the Regional Managers | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 4 | 480 | 72 |  |  |  | 552 | OK |  |  | 240 | 36 |  |  |  | 276 |  | 240 | 36 |  |  |  | 276 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 480 | 72 | 0 | 0 | 0 | 552 | OK
| Methodology for regional Roadmaps | PP2- TCC | All partners | 1 | 120 | 18 |  |  |  | 138 | OK |  |  | 120 | 18 |  |  |  | 138 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 120 | 18 | 0 | 0 | 0 | 138 | OK
| regional Roadmaps (on the institutional/stakeholder involvement process) elaborated and quality controled | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 20 | 2400 | 360 |  |  |  | 2760 | OK |  |  | 720 | 108 |  |  |  | 828 |  | 1680 | 252 |  |  |  | 1932 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2400 | 360 | 0 | 0 | 0 | 2760 | OK
| Regional Opening meeting for stakeholders (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 1800 | 270 |  | 1500 |  | 3570 | OK |  |  | 540 | 81 |  |  |  | 621 |  | 1260 | 189 | 0 | 1500 |  | 2949 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1800 | 270 | 0 | 1500 | 0 | 3570 | OK
| Meetings with stakeholder groups and Institutional learning groups / involvement in action plan implementation + Synergy Sessions with Institutional departments | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 50 | 6000 | 900 |  | 3500 |  | 10400 | OK |  |  |  | 0 |  |  |  | 0 |  | 600 | 90 |  | 350 |  | 1040 |  | 1500 | 225 |  | 875 |  | 2600 |  | 2400 | 360 |  | 1400 |  | 4160 |  | 1500 | 225 |  | 875 |  | 2600 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 6000 | 900 | 0 | 3500 | 0 | 10400 | OK
| Phase 1 closing stakeholder session (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 1800 | 270 |  | 1500 |  | 3570 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1800 | 270 | 0 | 1500 |  | 3570 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1800 | 270 | 0 | 1500 | 0 | 3570 | OK
| Synergy session for personnel of partner organisations | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 18 | 2160 | 324 |  |  |  | 2484 | OK |  |  |  | 0 |  |  |  | 0 |  | 540 | 81 |  |  |  | 621 |  | 540 | 81 |  |  |  | 621 |  | 540 | 81 |  |  |  | 621 |  | 540 | 81 |  |  |  | 621 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2160 | 324 | 0 | 0 | 0 | 2484 | OK
| Thematic coordination of stakeholder involvement | PP2- TCC | LP- VRW |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Analysis | [9 empty] | OK | [71 empty] | OK
| Joint methodology for regional State of Arts | PP4 - PD | All partners | 1 | 120 | 18 |  |  |  | 138 | OK |  |  |  | 0 |  |  |  | 0 |  | 120 | 18 |  |  |  | 138 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 120 | 18 | 0 | 0 | 0 | 138 | OK
| Regional State of Arts (including good practice inventory + list of ingredients for change) | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 | 40 | 4800 | 720 |  |  |  | 5520 | OK |  |  |  | 0 |  |  |  | 0 |  | 4800 | 720 | 0 | 0 |  | 5520 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4800 | 720 | 0 | 0 | 0 | 5520 | OK
| Transnational audit visits to each region by experts delegated by 2 other partners | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Project level menu of good practices | PP4 - PD | LP- VRW | 4 | 480 | 72 |  |  |  | 552 | OK |  |  |  | 0 |  |  |  | 0 |  | 480 | 72 |  |  |  | 552 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 480 | 72 | 0 | 0 | 0 | 552 | OK
| Thematic coordination of analysis phase | PP4 - PD | LP- VRW |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Knowledge exchange (good practice transfer) | [9 empty] | OK | [71 empty] | OK
| Guidelines (including matching learning needs with good practices)/methodology and templates for knowledge sharing | LP- VRW | All partners | 2 | 240 | 36 |  |  |  | 276 | OK |  |  |  | 0 |  |  |  | 0 |  | 240 | 36 |  |  |  | 276 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 240 | 36 | 0 | 0 | 0 | 276 | OK
| 3 Transnational Exchange Session meetings of 3 days length (for individual staff members of partners + appr. 3 stakeholders per partner region) | LP- VRW | All partners | 50 | 6000 | 900 | 4800 | 7200 |  | 18900 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4200 | 630 | 3360 | 5040 |  | 13230 |  | 1800 | 270 | 1440 | 2160 |  | 5670 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 6000 | 900 | 4800 | 7200 | 0 | 18900 | OK
| Summary reports on the Exchange Sessions | LP- VRW | All partners | 5 | 600 | 90 |  |  |  | 690 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 420 | 63 |  |  |  | 483 |  | 180 | 27 |  |  |  | 207 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 600 | 90 | 0 | 0 | 0 | 690 | OK
| Thematic coordination of knowledge exchange | LP- VRW | n.a. |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Action plan drafting | [9 empty] | OK | [71 empty] | OK
| Project level Guideline and joint training on action plan development | PP3 - MCM | All partners | 8 | 960 | 144 |  |  |  | 1104 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 960 | 144 |  |  |  | 1104 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 960 | 144 | 0 | 0 | 0 | 1104 | OK
| Detailed Action Plan methodology on regional level/workplan | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 0 | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Elaboration of Action Plans / policy instrument | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 40 | 4800 | 720 |  | 15000 |  | 20520 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2400 | 360 |  | 7500 |  | 10260 |  | 2400 | 360 |  | 7500 |  | 10260 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4800 | 720 | 0 | 15000 | 0 | 20520 | OK
| Cross- reading exercise | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 5 | 600 | 90 |  |  |  | 690 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 600 | 90 |  |  |  | 690 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 600 | 90 | 0 | 0 | 0 | 690 | OK
| Final quality control of Action Plans | PP3 - MCM | n.a. | 2 | 240 | 36 |  |  |  | 276 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 240 | 36 |  |  |  | 276 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 240 | 36 | 0 | 0 | 0 | 276 | OK
| Consistency check of Action Plans on regional level | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 3 | 360 | 54 |  |  |  | 414 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 360 | 54 |  |  |  | 414 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 360 | 54 | 0 | 0 | 0 | 414 | OK
| Thematic coordination of action planning | PP3 - MCM | LP- VRW |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Action plan implementation follow-up(24 months) |  |  |  |  | 0 |  |  |  |  | OK |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 |  |  |  |  | OK
| Monitoring of the implementation of the action plans | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 12 | 1440 | 216 |  |  |  | 1656 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 360 | 54 |  |  |  | 414 |  | 360 | 54 |  |  |  | 414 |  | 360 | 54 |  |  |  | 414 |  | 360 | 54 |  |  |  | 414 |  | 1440 | 216 | 0 | 0 | 0 | 1656 | OK
| Summary on the level of achievements / policy instrument | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 4 | 480 | 72 |  |  |  | 552 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 240 | 36 |  |  |  | 276 |  | 240 | 36 |  |  |  | 276 |  | 480 | 72 | 0 | 0 | 0 | 552 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[11 empty] | OK | [71 empty] | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 40920 | 6138 | 8400 | 31700 | 0 | 87158 | OK |  |  | 2364 | 354.6 | 514.2857 | 0 | 0 | 3232.8857 |  | 10560 | 1584 | 514.2857 | 1850 | 0 | 14508.2857 |  | 7920 | 1188 | 3874.2857 | 5915 | 0 | 18897.2857 |  | 9540 | 1431 | 1954.2857 | 11060 | 0 | 23985.2857 |  | 8280 | 1242 | 514.2857 | 12875 | 0 | 22911.2857 |  | 360 | 54 | 0 | 0 | 0 | 414 |  | 528 | 79.2 | 514.2857 | 0 | 0 | 1121.4857 |  | 600 | 90 | 0 | 0 | 0 | 690 |  | 768 | 115.2 | 514.2857 | 0 | 0 | 1397.4857 |  | 40920 | 6138 | 8400 | 31700 | 0 | 87158 | OK
| TOTAL |  |  |  | 83400 | 12510 | 18600 | 47000 | 0 | 161510 | OK |  |  | 9972 | 1495.8 | 3008.5714 | 300 | 0 | 14776.3714 |  | 13752 | 2062.8 | 1208.5714 | 11350 | 0 | 28373.3714 |  | 14532 | 2179.8 | 4568.5714 | 7415 | 0 | 28695.3714 |  | 17616 | 2642.4 | 4748.5714 | 11060 | 0 | 36066.9714 |  | 19416 | 2912.4 | 1688.5714 | 16875 | 0 | 40891.9714 |  | 1680 | 252 | 180 | 0 | 0 | 2112 |  | 1164 | 174.6 | 1208.5714 | 0 | 0 | 2547.1714 |  | 1920 | 288 | 180 | 0 | 0 | 2388 |  | 3348 | 502.2 | 1808.5714 | 0 | 0 | 5658.7714 |  | 83400 | 12510 | 18600 | 47000 | 0 | 161510 | OK
[5 empty] | OK | OK | OK | OK | OK | OK | OK |  |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK
| Application Form budget |  |  |  | Staff | Overhead | T & A | External expertise | Equip. | TOTAL |  | ERDF | 137283.5
|  |  | PP5 - VPR |  | 83400 | 12510 | 18600 | 47000 | 0 | 161510 |  | Co-finance | 24226.5
[12 empty] | TOTAL | 161510
| Application Form budget - Spending Forecast | Period | Budget | % | Rounded |  | Application Form budget - External expertise | Type of cost |  | Budget |  |  | OK
|  | Preparation | 0 | 0% | 0 |  |  | FLC cost
|  | Semester 1 | 14776.3714 | 9.149% | 14776 |  |  | Project/financial/comm. management
|  | Semester 2 | 28373.3714 | 17.57% | 28373 |  |  | Meetings: partner meeting |  | 3000
|  | Semester 3 | 28695.3714 | 17.77% | 28695 |  |  | Meetings: dissemination event |  | 0
|  | Semester 4 | 36066.9714 | 22.33% | 36067 |  |  |  |  | 0
|  | Semester 5 | 40891.9714 | 25.32% | 40892 |  |  | Meetings: stakeholder group |  | 6500
|  | Semester 6 | 2112 | 1.308% | 2112 |  |  | Travel & acc. cost: non staff |  | 7200
|  | Semester 7 | 2547.1714 | 1.577% | 2547 |  |  | Publication and dissemination costs |  | 15300
|  | Semester 8 | 2388 | 1.479% | 2388 |  |  | External support for the exc. of experience |  | 15000
|  | Semester 9 | 5658.7714 | 3.504% | 5660 |  |  | Other
|  |  |  | 0 |  |  |  | TOTAL |  | 47000
|  | TOTAL | 161510 | 1 | 161510 |  |  |  |  | OK
|  |  | OK |  | OK
| % check tables | Budget lines | % |  |  |  | Application Form budget - Equipment | Type of cost |  | Budget
|  | Staff | 51.64% |  |  |  |  | Office eqiupment
|  | Overhead | 7.746% |  |  |  |  | Other
|  | T & A | 11.52% |  |  |  |  | TOTAL |  | 0
|  | Ext. expertise | 29.1% | [6 empty] | OK
|  | Eqipment | 0%
|  | TOTAL | 100%
|  | CP | %
|  | Management CP | 12.29%
|  | Communication CP | 33.75%
|  | Thematic CP | 53.96%
|  | TOTAL | 100%
|  | Austria | 262
|  | Belgium | 278
|  | Czech Republic | 118
|  | Denmark | 280
|  | Estonia | 110
|  | Finland | 232
|  | France | 233
|  | Germany | 253
|  | Greece | 148
|  | Hungary | 121
|  | Ireland | 286
|  | Italy | 200
|  | Netherlands | 275
|  | Poland | 131
|  | Portugal | 137
|  | Slovak Republic | 118
|  | Slovenia | 185
|  | Spain | 202
|  | Sweden | 236
|  | United Kingdom | 238
|  | Bulgaria | 80
|  | Croatia | 100
|  | Cyprus | 120
|  | Latvia | 120
|  | Lithuania | 100
|  | Luxemburg | 324
|  | Malta | 140
|  | Romania | 80
|  | ERDF | 75%
|  | ERDF | 85%
Note on I28: Tóth Gábor: FLC cost
Note on I37: Tóth Gábor: Design, translation and printing of the briefing brouchure (English and Latvian versions)
Note on I38: Tóth Gábor: Printing cost of the poster
Note on I52: Tóth Gábor: Technical assistance related to the newsletters
Note on I53: Tóth Gábor: Technical assistance related to the project video
Note on I55: Tóth Gábor: Design and printing cost
Note on I56: Tóth Gábor: Organisation of the Mid-term conference, SG and TWG meeting to be held at month 30
Note on I58: Tóth Gábor: Design and printing cost
Note on I66: Tóth Gábor: Organisation of the SG and TWG meeting to be held at month 30
Note on I74: Tóth Gábor: Cost for organisieng the meeting (incuding networking activities)
Note on I75: Tóth Gábor: Organisation cost
Note on I76: Tóth Gábor: Cost for organisieng the meeting (incuding networking activities)
Note on I84: Tóth Gábor: Organisation cost for hosting the visit
Note on I91: Tóth Gábor: Non-staff stakeholder travel (3 person)
Note on I99: Tóth Gábor: External support for the preparation of the Action Plan

## PP6_PZH
PP6 - Province of South Holland |  |  |  | Country --> | [5 empty] | Netherlands |  |  | Semester 1 (month 1-6) | [6 empty] | Semester 2 (month 7-12) | [6 empty] | Semester 3 (month 13-18) | [6 empty] | Semester 4 (month 19-24) | [6 empty] | Semester 5 (month 25-30) | [6 empty] | Semester 6 (month 31-36) | [6 empty] | Semester 7 (month 37-42) | [6 empty] | Semester 8 (month 43-48) | [6 empty] | Semester 9 (month 49-54) | [6 empty] | TOTAL
DAILY FEE |  | 275 |  |  | Travel cost 1 person 2 nights |  |  | 600 | ERDF | 0.85
[5 empty] | Travel cost 1 person 3 nights |  |  | 800
126077
Action | ACTIVITIES | Partner in charge | Participating
|  |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL
|  |  |  | days | total | [7 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total | [5 empty] | days | total
| PREPARATION | LP
| Project proposal preparation |  |  |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | OK |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| PROJECT MANAGEMENT AND COORDINATION | LP | [8 empty] | OK | [71 empty] | OK
| Contractualisation and start-up | [9 empty] | OK | [71 empty] | OK
| Subsidy Contract | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Partnership Agreement | LP | All | 1 | 275 | 41.25 |  |  |  | 316.25 | OK |  |  | 275 | 41.25 |  |  |  | 316.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 | 0 | 0 | 0 | 316.25 | OK
| Appointment FLC | LP | All | 2 | 550 | 82.5 |  |  |  | 632.5 | OK |  |  | 550 | 82.5 |  |  |  | 632.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 550 | 82.5 | 0 | 0 | 0 | 632.5 | OK
| Management and financial handbook | LP | All | 1 | 275 | 41.25 |  |  |  | 316.25 | OK |  |  | 275 | 41.25 |  |  |  | 316.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 | 0 | 0 | 0 | 316.25 | OK
| Rules of Procedures for the PR | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Rules of Procedures for the SG | LP | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Kick-off meeting | LP | All | 8 | 2200 | 330 |  |  |  | 2530 | OK |  |  | 2200 | 330 | 0 | 0 |  | 2530 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2200 | 330 | 0 | 0 | 0 | 2530 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Project Management and coordination | [9 empty] | OK | [71 empty] | OK
| Daily project management | LP | All | 30 | 8250 | 1237.5 |  |  |  | 9487.5 | OK |  |  | 1237.5 | 185.625 |  | 0 | 0 | 1423.125 |  | 412.5 | 61.875 |  | 0 |  | 474.375 |  | 2475 | 371.25 |  | 0 |  | 2846.25 |  | 1650 | 247.5 |  | 0 |  | 1897.5 |  | 2475 | 371.25 |  | 0 |  | 2846.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 8250 | 1237.5 | 0 | 0 | 0 | 9487.5 | OK
| Steering Group meeting linked with thematic meeting | LP | All | 15 | 4125 | 618.75 | 3600 |  |  | 8343.75 | OK |  |  | 82.5 | 12.375 | 514.2857 |  |  | 609.1607 |  | 412.5 | 61.875 | 514.2857 |  |  | 988.6607 |  | 1237.5 | 185.625 | 514.2857 |  |  | 1937.4107 |  | 1237.5 | 185.625 | 514.2857 |  |  | 1937.4107 |  | 825 | 123.75 | 514.2857 |  |  | 1463.0357 |  |  | 0 |  |  |  | 0 |  | 165 | 24.75 | 514.2857 |  |  | 704.0357 |  |  | 0 |  |  |  | 0 |  | 165 | 24.75 | 514.2857 |  |  | 704.0357 |  | 4125 | 618.75 | 3600 | 0 | 0 | 8343.75 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Reporting | [9 empty] | OK | [71 empty] | OK
| Internal financial monitoring/budget revision | LP | All | 8 | 2200 | 330 |  |  |  | 2530 | OK |  |  | 220 | 33 |  |  |  | 253 |  | 440 | 66 |  |  |  | 506 |  | 440 | 66 |  |  |  | 506 |  | 660 | 99 |  |  |  | 759 |  | 440 | 66 |  |  |  | 506 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2200 | 330 | 0 | 0 | 0 | 2530 | OK
| Preparation of partner level progress report | LP | All | 30 | 8250 | 1237.5 |  | 8400 |  | 17887.5 | OK |  |  |  | 0 |  |  |  | 0 |  | 1237.5 | 185.625 |  | 1260 |  | 2683.125 |  | 1237.5 | 185.625 |  | 1260 |  | 2683.125 |  | 1237.5 | 185.625 |  | 1260 |  | 2683.125 |  | 1237.5 | 185.625 |  | 1260 |  | 2683.125 |  | 1237.5 | 185.625 |  | 1260 |  | 2683.125 |  |  | 0 |  |  |  | 0 |  | 1237.5 | 185.625 |  | 1260 |  | 2683.125 |  | 825 | 123.75 |  | 840 |  | 1788.75 |  | 8250 | 1237.5 | 0 | 8400 | 0 | 17887.5 | OK
| Delivery of progress report to JTS | LP | All | 7 | 1925 | 288.75 |  |  |  | 2213.75 | OK |  |  |  | 0 |  |  |  | 0 |  | 288.75 | 43.3125 |  | 0 |  | 332.0625 |  | 288.75 | 43.3125 |  | 0 |  | 332.0625 |  | 288.75 | 43.3125 |  | 0 |  | 332.0625 |  | 288.75 | 43.3125 |  | 0 |  | 332.0625 |  | 288.75 | 43.3125 |  | 0 |  | 332.0625 |  |  | 0 |  |  |  | 0 |  | 288.75 | 43.3125 |  | 0 |  | 332.0625 |  | 192.5 | 28.875 |  | 0 |  | 221.375 |  | 1925 | 288.75 | 0 | 0 | 0 | 2213.75 | OK
| Delivery of final report to JTS | LP | All | 2 | 550 | 82.5 |  |  |  | 632.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 550 | 82.5 |  |  |  | 632.5 |  | 550 | 82.5 | 0 | 0 | 0 | 632.5 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 28600 | 4290 | 3600 | 8400 | 0 | 44890 | OK |  |  | 4840 | 726 | 514.2857 | 0 | 0 | 6080.2857 |  | 2791.25 | 418.6875 | 514.2857 | 1260 | 0 | 4984.2232 |  | 5678.75 | 851.8125 | 514.2857 | 1260 | 0 | 8304.8482 |  | 5073.75 | 761.0625 | 514.2857 | 1260 | 0 | 7609.0982 |  | 5266.25 | 789.9375 | 514.2857 | 1260 | 0 | 7830.4732 |  | 1526.25 | 228.9375 | 0 | 1260 | 0 | 3015.1875 |  | 165 | 24.75 | 514.2857 | 0 | 0 | 704.0357 |  | 1526.25 | 228.9375 | 0 | 1260 | 0 | 3015.1875 |  | 1732.5 | 259.875 | 514.2857 | 840 | 0 | 3346.6607 |  | 28600 | 4290 | 3600 | 8400 | 0 | 44890 | OK
| COMMUNICATION | [9 empty] | OK | [71 empty] | OK
| Planning and start-up | [9 empty] | OK | [71 empty] | OK
| Communication and knowledge sharing strategy | PP5-VPR | All |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Launching event | LP | All | 3 | 825 | 123.75 |  |  |  | 948.75 | OK |  |  | 577.5 | 86.625 | 0 | 0 |  | 664.125 |  | 247.5 | 37.125 |  | 0 |  | 284.625 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 825 | 123.75 | 0 | 0 | 0 | 948.75 | OK
| Briefing brochure linked to the Launching event about the project and the topic adressed | PP5-VPR | All | 4 | 1100 | 165 |  | 2000 |  | 3265 | OK |  |  | 770 | 115.5 |  |  |  | 885.5 |  | 330 | 49.5 |  | 2000 |  | 2379.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1100 | 165 | 0 | 2000 | 0 | 3265 | OK
| Poster (obligatory) | PP5-VPR | All | 2 | 550 | 82.5 |  | 300 |  | 932.5 | OK |  |  | 550 | 82.5 |  | 300 |  | 932.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 550 | 82.5 | 0 | 300 | 0 | 932.5 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Website and social media | [9 empty] | OK | [71 empty] | OK
| Launching of website and regular update of the website | PP5-VPR | All | 4 | 1100 | 165 |  |  |  | 1265 | OK |  |  | 110 | 16.5 |  |  |  | 126.5 |  | 110 | 16.5 |  |  |  | 126.5 |  | 220 | 33 |  |  |  | 253 |  | 220 | 33 |  |  |  | 253 |  | 220 | 33 |  |  |  | 253 |  | 55 | 8.25 |  |  |  | 63.25 |  | 55 | 8.25 |  |  |  | 63.25 |  | 55 | 8.25 |  |  |  | 63.25 |  | 55 | 8.25 |  |  |  | 63.25 |  | 1100 | 165 | 0 | 0 | 0 | 1265 | OK
| Social media presence | PP5-VPR | All | 2 | 550 | 82.5 |  |  |  | 632.5 | OK |  |  | 55 | 8.25 |  |  |  | 63.25 |  | 55 | 8.25 |  |  |  | 63.25 |  | 110 | 16.5 |  |  |  | 126.5 |  | 110 | 16.5 |  |  |  | 126.5 |  | 110 | 16.5 |  |  |  | 126.5 |  | 27.5 | 4.125 |  |  |  | 31.625 |  | 27.5 | 4.125 |  |  |  | 31.625 |  | 27.5 | 4.125 |  |  |  | 31.625 |  | 27.5 | 4.125 |  |  |  | 31.625 |  | 550 | 82.5 | 0 | 0 | 0 | 632.5 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Paticipation in other events | [9 empty] | OK | [71 empty] | OK
| INTERREG Europe events | PP5-VPR, LP- VRW | n.a. |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Dissemination at transnational events (presenter or exhibitioner) | PP5-VPR | All |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Dissemination at national events (presenter or exhibitioner) | PP5-VPR | All |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Communication materials/tools | [9 empty] | OK | [71 empty] | OK
| Press releases | PP5-VPR | TWG meeting/event organisers | 2 | 550 | 82.5 |  |  |  | 632.5 | OK |  |  |  | 0 |  |  |  | 0 |  | 137.5 | 20.625 |  |  |  | 158.125 |  | 137.5 | 20.625 |  |  |  | 158.125 |  | 137.5 | 20.625 |  |  |  | 158.125 |  | 137.5 | 20.625 |  |  |  | 158.125 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 550 | 82.5 | 0 | 0 | 0 | 632.5 | OK
| Newsletters on project level | PP5-VPR | All | 1 | 275 | 41.25 |  |  |  | 316.25 | OK |  |  |  | 0 |  |  |  | 0 |  | 68.75 | 10.3125 |  | 0 |  | 79.0625 |  | 68.75 | 10.3125 |  |  |  | 79.0625 |  | 68.75 | 10.3125 |  |  |  | 79.0625 |  | 68.75 | 10.3125 |  |  |  | 79.0625 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 | 0 | 0 | 0 | 316.25 | OK
| Project video | PP5-VPR | All | 1 | 275 | 41.25 |  |  |  | 316.25 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 |  | 0 |  | 316.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 | 0 | 0 | 0 | 316.25 | OK
| Policy learning Synthesis report | LP- VRW, PP5-VPR | All | 1 | 275 | 41.25 |  |  |  | 316.25 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 |  |  |  | 316.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 | 0 | 0 | 0 | 316.25 | OK
| Dissemination materials on exchanged experience targeting regions outside the partnership | PP4-VPR | All |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Mid term event | PP4-VPR | All partners |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Final event | PP2- TCC | All partners | 3 | 825 | 123.75 | 600 |  |  | 1548.75 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 825 | 123.75 | 600 | 0 |  | 1548.75 |  | 825 | 123.75 | 600 | 0 | 0 | 1548.75 | OK
| Visualisation materials for institutional, stakeholder meetings | PP5- VPR | LP, PP2, PP3, PP4, PP5 | 5 | 1375 | 206.25 |  | 3000 |  | 4581.25 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 1500 |  | 1500 |  | 687.5 | 103.125 |  | 1500 |  | 2290.625 |  | 343.75 | 51.5625 |  |  |  | 395.3125 |  | 343.75 | 51.5625 |  |  |  | 395.3125 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1375 | 206.25 | 0 | 3000 | 0 | 4581.25 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 7700 | 1155 | 600 | 5300 | 0 | 14755 | OK |  |  | 2062.5 | 309.375 | 0 | 300 | 0 | 2671.875 |  | 948.75 | 142.3125 | 0 | 3500 | 0 | 4591.0625 |  | 1223.75 | 183.5625 | 0 | 1500 | 0 | 2907.3125 |  | 880 | 132 | 0 | 0 | 0 | 1012 |  | 1430 | 214.5 | 0 | 0 | 0 | 1644.5 |  | 82.5 | 12.375 | 0 | 0 | 0 | 94.875 |  | 82.5 | 12.375 | 0 | 0 | 0 | 94.875 |  | 82.5 | 12.375 | 0 | 0 | 0 | 94.875 |  | 907.5 | 136.125 | 600 | 0 | 0 | 1643.625 |  | 7700 | 1155 | 600 | 5300 | 0 | 14755 | OK
| INTERREGIONAL POLICY LEARNING | [9 empty] | OK | [71 empty] | OK
| Interregional thematic organisation | [9 empty] | OK | [71 empty] | OK
| Setting up Thematic Working Group (TWG) | LP | All partners | 2 | 550 | 82.5 |  |  |  | 632.5 | OK |  |  | 550 | 82.5 |  |  |  | 632.5 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  | 550 | 82.5 | 0 | 0 | 0 | 632.5 | OK
| TWG Rules of procedure | LP | All partners |  | 0 | 0 |  |  |  | 0 | OK |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TWG meetings linked to thematic implementation | LP | All partners | 21 | 5775 | 866.25 | 3600 |  |  | 10241.25 | OK |  |  | 115.5 | 17.325 | 514.2857 |  |  | 647.1107 |  | 577.5 | 86.625 | 514.2857 |  |  | 1178.4107 |  | 1732.5 | 259.875 | 514.2857 |  |  | 2506.6607 |  | 1732.5 | 259.875 | 514.2857 |  |  | 2506.6607 |  | 1155 | 173.25 | 514.2857 |  |  | 1842.5357 |  |  | 0 |  |  |  | 0 |  | 231 | 34.65 | 514.2857 |  |  | 779.9357 |  |  | 0 |  |  |  | 0 |  | 231 | 34.65 | 514.2857 |  |  | 779.9357 |  | 5775 | 866.25 | 3600 | 0 | 0 | 10241.25 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Stakeholder involvement and organisational learning | [9 empty] | OK | [71 empty] | OK
| Setting up stakeholder & institutional learning groups | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 1 | 275 | 41.25 |  |  |  | 316.25 | OK |  |  | 192.5 | 28.875 |  |  |  | 221.375 |  | 82.5 | 12.375 |  |  |  | 94.875 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 | 0 | 0 | 0 | 316.25 | OK
| Interactive training on stakeholder involvement/institutional learning for the Regional Managers | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 4 | 1100 | 165 |  |  |  | 1265 | OK |  |  | 550 | 82.5 |  |  |  | 632.5 |  | 550 | 82.5 |  |  |  | 632.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1100 | 165 | 0 | 0 | 0 | 1265 | OK
| Methodology for regional Roadmaps | PP2- TCC | All partners | 1 | 275 | 41.25 |  |  |  | 316.25 | OK |  |  | 275 | 41.25 |  |  |  | 316.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 | 0 | 0 | 0 | 316.25 | OK
| regional Roadmaps (on the institutional/stakeholder involvement process) elaborated and quality controled | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 5 | 1375 | 206.25 |  |  |  | 1581.25 | OK |  |  | 412.5 | 61.875 |  |  |  | 474.375 |  | 962.5 | 144.375 |  |  |  | 1106.875 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1375 | 206.25 | 0 | 0 | 0 | 1581.25 | OK
| Regional Opening meeting for stakeholders (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 5 | 1375 | 206.25 |  |  |  | 1581.25 | OK |  |  | 412.5 | 61.875 |  |  |  | 474.375 |  | 962.5 | 144.375 | 0 | 0 |  | 1106.875 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 1375 | 206.25 | 0 | 0 | 0 | 1581.25 | OK
| Meetings with stakeholder groups and Institutional learning groups / involvement in action plan implementation + Synergy Sessions with Institutional departments | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 4125 | 618.75 |  |  |  | 4743.75 | OK |  |  |  | 0 |  |  |  | 0 |  | 412.5 | 61.875 |  | 0 |  | 474.375 |  | 1031.25 | 154.6875 |  | 0 |  | 1185.9375 |  | 1650 | 247.5 |  | 0 |  | 1897.5 |  | 1031.25 | 154.6875 |  | 0 |  | 1185.9375 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4125 | 618.75 | 0 | 0 | 0 | 4743.75 | OK
| Phase 1 closing stakeholder session (including some networking lunch, evening reception, regional seminar) | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 4125 | 618.75 |  | 2000 |  | 6743.75 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4125 | 618.75 | 0 | 2000 |  | 6743.75 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4125 | 618.75 | 0 | 2000 | 0 | 6743.75 | OK
| Synergy session for personnel of partner organisations | PP2- TCC | LP + PP6,PP2,PP3,PP4, PP5 | 9 | 2475 | 371.25 |  |  |  | 2846.25 | OK |  |  |  | 0 |  |  |  | 0 |  | 618.75 | 92.8125 |  |  |  | 711.5625 |  | 618.75 | 92.8125 |  |  |  | 711.5625 |  | 618.75 | 92.8125 |  |  |  | 711.5625 |  | 618.75 | 92.8125 |  |  |  | 711.5625 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2475 | 371.25 | 0 | 0 | 0 | 2846.25 | OK
| Thematic coordination of stakeholder involvement | PP2- TCC | LP- VRW |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Analysis | [9 empty] | OK | [71 empty] | OK
| Joint methodology for regional State of Arts | PP4 - PD | All partners | 1 | 275 | 41.25 |  |  |  | 316.25 | OK |  |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 |  |  |  | 316.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 | 0 | 0 | 0 | 316.25 | OK
| Regional State of Arts (including good practice inventory + list of ingredients for change) | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 4125 | 618.75 |  |  |  | 4743.75 | OK |  |  |  | 0 |  |  |  | 0 |  | 4125 | 618.75 | 0 | 0 |  | 4743.75 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4125 | 618.75 | 0 | 0 | 0 | 4743.75 | OK
| Transnational audit visits to each region by experts delegated by 2 other partners | PP4 - PD | LP + PP6,PP2,PP3,PP4, PP5 |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Project level menu of good practices | PP4 - PD | LP- VRW | 1 | 275 | 41.25 |  |  |  | 316.25 | OK |  |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 |  |  |  | 316.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 | 0 | 0 | 0 | 316.25 | OK
| Thematic coordination of analysis phase | PP4 - PD | LP- VRW |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Knowledge exchange (good practice transfer) | [9 empty] | OK | [71 empty] | OK
| Guidelines (including matching learning needs with good practices)/methodology and templates for knowledge sharing | LP- VRW | All partners | 1 | 275 | 41.25 |  |  |  | 316.25 | OK |  |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 |  |  |  | 316.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 | 0 | 0 | 0 | 316.25 | OK
| 3 Transnational Exchange Session meetings of 3 days length (for individual staff members of partners + appr. 3 stakeholders per partner region) | LP- VRW | All partners | 35 | 9625 | 1443.75 | 3200 | 6400 |  | 20668.75 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 6737.5 | 1010.625 | 2240 | 4480 |  | 14468.125 |  | 2887.5 | 433.125 | 960 | 1920 |  | 6200.625 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 9625 | 1443.75 | 3200 | 6400 | 0 | 20668.75 | OK
| Summary reports on the Exchange Sessions | LP- VRW | All partners | 1 | 275 | 41.25 |  |  |  | 316.25 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 192.5 | 28.875 |  |  |  | 221.375 |  | 82.5 | 12.375 |  |  |  | 94.875 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 | 0 | 0 | 0 | 316.25 | OK
| Thematic coordination of knowledge exchange | LP- VRW | n.a. |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Action plan drafting | [9 empty] | OK | [71 empty] | OK
| Project level Guideline and joint training on action plan development | PP3 - MCM | All partners | 2 | 550 | 82.5 |  |  |  | 632.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 550 | 82.5 |  |  |  | 632.5 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 550 | 82.5 | 0 | 0 | 0 | 632.5 | OK
| Detailed Action Plan methodology on regional level/workplan | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 0 | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Elaboration of Action Plans / policy instrument | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 15 | 4125 | 618.75 |  |  |  | 4743.75 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 2062.5 | 309.375 |  | 0 |  | 2371.875 |  | 2062.5 | 309.375 |  | 0 |  | 2371.875 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 4125 | 618.75 | 0 | 0 | 0 | 4743.75 | OK
| Cross- reading exercise | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 3 | 825 | 123.75 |  |  |  | 948.75 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 825 | 123.75 |  |  |  | 948.75 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 825 | 123.75 | 0 | 0 | 0 | 948.75 | OK
| Final quality control of Action Plans | PP3 - MCM | n.a. | 1 | 275 | 41.25 |  |  |  | 316.25 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 |  |  |  | 316.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 | 0 | 0 | 0 | 316.25 | OK
| Consistency check of Action Plans on regional level | PP3 - MCM | LP + PP6,PP2,PP3,PP4, PP5 | 1 | 275 | 41.25 |  |  |  | 316.25 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 |  |  |  | 316.25 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 41.25 | 0 | 0 | 0 | 316.25 | OK
| Thematic coordination of action planning | PP3 - MCM | LP- VRW |  | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| Action plan implementation follow-up(24 months) |  |  |  |  | 0 |  |  |  |  | OK |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 |  |  |  |  | OK
| Monitoring of the implementation of the action plans | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 6 | 1650 | 247.5 |  |  |  | 1897.5 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 412.5 | 61.875 |  |  |  | 474.375 |  | 412.5 | 61.875 |  |  |  | 474.375 |  | 412.5 | 61.875 |  |  |  | 474.375 |  | 412.5 | 61.875 |  |  |  | 474.375 |  | 1650 | 247.5 | 0 | 0 | 0 | 1897.5 | OK
| Summary on the level of achievements / policy instrument | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 2 | 550 | 82 |  |  |  | 632 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 275 | 40.75 |  |  |  | 315.75 |  | 275 | 41.25 |  |  |  | 316.25 |  | 550 | 82 | 0 | 0 | 0 | 632 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[11 empty] | OK | [71 empty] | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| TOTAL |  |  |  | 44550 | 6682 | 6800 | 8400 | 0 | 66432 | OK |  |  | 2508 | 376.2 | 514.2857 | 0 | 0 | 3398.4857 |  | 9116.25 | 1367.4375 | 514.2857 | 0 | 0 | 10997.9732 |  | 10312.5 | 1546.875 | 2754.2857 | 4480 | 0 | 19093.6607 |  | 9583.75 | 1437.5625 | 1474.2857 | 1920 | 0 | 14415.5982 |  | 10367.5 | 1555.125 | 514.2857 | 2000 | 0 | 14436.9107 |  | 412.5 | 61.875 | 0 | 0 | 0 | 474.375 |  | 643.5 | 96.525 | 514.2857 | 0 | 0 | 1254.3107 |  | 687.5 | 102.625 | 0 | 0 | 0 | 790.125 |  | 918.5 | 137.775 | 514.2857 | 0 | 0 | 1570.5607 |  | 44550 | 6682 | 6800 | 8400 | 0 | 66432 | OK
| TOTAL |  |  |  | 80850 | 12127 | 11000 | 22100 | 0 | 126077 | OK |  |  | 9410.5 | 1411.575 | 1028.5714 | 300 | 0 | 12150.6464 |  | 12856.25 | 1928.4375 | 1028.5714 | 4760 | 0 | 20573.2589 |  | 17215 | 2582.25 | 3268.5714 | 7240 | 0 | 30305.8214 |  | 15537.5 | 2330.625 | 1988.5714 | 3180 | 0 | 23036.6964 |  | 17063.75 | 2559.5625 | 1028.5714 | 3260 | 0 | 23911.8839 |  | 2021.25 | 303.1875 | 0 | 1260 | 0 | 3584.4375 |  | 891 | 133.65 | 1028.5714 | 0 | 0 | 2053.2214 |  | 2296.25 | 343.9375 | 0 | 1260 | 0 | 3900.1875 |  | 3558.5 | 533.775 | 1628.5714 | 840 | 0 | 6560.8464 |  | 80850 | 12127 | 11000 | 22100 | 0 | 126077 | OK
[5 empty] | OK | OK | OK | OK | OK | OK | OK |  |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK
| Application Form budget |  |  |  | Staff | Overhead | T & A | External expertise | Equip. | TOTAL |  | ERDF | 107165.45
|  |  | PP6 - Province of South Holland |  | 80850 | 12127 | 11000 | 22100 | 0 | 126077 |  | Co-finance | 18911.55
[12 empty] | TOTAL | 126077
| Application Form budget - Spending Forecast | Period | Budget | % | Rounded |  | Application Form budget - External expertise | Type of cost |  | Budget |  |  | OK
|  | Preparation | 0 | 0% | 0 |  |  | FLC cost |  | 8400
|  | Semester 1 | 12150.6464 | 9.637% | 12151 |  |  | Project/financial/comm. management
|  | Semester 2 | 20573.2589 | 16.32% | 20573 |  |  | Meetings: partner meeting |  | 4000
|  | Semester 3 | 30305.8214 | 24.04% | 30306 |  |  | Meetings: dissemination event
|  | Semester 4 | 23036.6964 | 18.27% | 23037 |  |  |  |  | 0
|  | Semester 5 | 23911.8839 | 18.97% | 23912 |  |  | Meetings: stakeholder group |  | 2000
|  | Semester 6 | 3584.4375 | 2.843% | 3584 |  |  | Travel & acc. cost: non staff |  | 2400
|  | Semester 7 | 2053.2214 | 1.629% | 2053 |  |  | Publication and dissemination costs |  | 5300
|  | Semester 8 | 3900.1875 | 3.093% | 3900 |  |  | External support for the exc. of experience |  | 0
|  | Semester 9 | 6560.8464 | 5.204% | 6561 |  |  | Other
|  |  |  | 0 |  |  |  | TOTAL |  | 22100
|  | TOTAL | 126077 | 1 | 126077 |  |  |  |  | OK
|  |  | OK |  | OK
| % check tables | Budget lines | % |  |  |  | Application Form budget - Equipment | Type of cost |  | Budget
|  | Staff | 64.13% |  |  |  |  | Office eqiupment
|  | Overhead | 9.619% |  |  |  |  | Other
|  | T & A | 8.725% |  |  |  |  | TOTAL |  | 0
|  | Ext. expertise | 17.53% | [6 empty] | OK
|  | Eqipment | 0%
|  | TOTAL | 100%
|  | CP | %
|  | Management CP | 35.61%
|  | Communication CP | 11.7%
|  | Thematic CP | 52.69%
|  | TOTAL | 100%
|  | Austria | 262
|  | Belgium | 278
|  | Czech Republic | 118
|  | Denmark | 280
|  | Estonia | 110
|  | Finland | 232
|  | France | 233
|  | Germany | 253
|  | Greece | 148
|  | Hungary | 121
|  | Ireland | 286
|  | Italy | 200
|  | Netherlands | 275
|  | Poland | 131
|  | Portugal | 137
|  | Slovak Republic | 118
|  | Slovenia | 185
|  | Spain | 202
|  | Sweden | 236
|  | United Kingdom | 238
|  | Bulgaria | 80
|  | Croatia | 100
|  | Cyprus | 120
|  | Latvia | 104
|  | Lithuania | 100
|  | Luxemburg | 324
|  | Malta | 140
|  | Romania | 80
|  | ERDF | 75%
|  | ERDF | 85%
Note on I28: Tóth Gábor: FLC cost
Note on I37: Tóth Gábor: Translation and printing of the briefing brouchure
Note on I38: Tóth Gábor: Printing cost of the poster
Note on I55: Tóth Gábor: Printing cost
Note on I56: Tóth Gábor: Non-staff stakeholder travel (2 person)
Note on I58: Tóth Gábor: Design and printing cost
Note on I75: Tóth Gábor: Organisation cost
Note on I76: Tóth Gábor: Cost for organisieng the meeting (incuding networking activities)
Note on I84: Tóth Gábor: Organisation cost for hosting the visit
Note on I91: Tóth Gábor: Non-staff stakeholder travel (3 person): 4800 EUR Organisation of 1 Transnational exchange session: 4000 EUR

## PP1_x (hidden)
PPx - Acronym |  |  |  | Country --> | [5 empty] | Ireland
DAILY FEE |  | 286 |  |  | Travel cost 1 person 2 nights |  |  | 600 | ERDF | 0.75
[5 empty] | Travel cost 1 person 3 nights |  |  | 800
Action | ACTIVITIES | Partner in charge | Participating
|  |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL
|  |  |  | days | total
| PREPARATION | LP
| Project proposal preparation |  |  |  | 0 | 0 |  |  |  | 0 | OK
| TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | OK
| PROJECT MANAGEMENT AND COORDINATION | LP | [8 empty] | OK
| Contractualisation and start-up | [9 empty] | OK
| Subsidy Contract | LP | All |  | 0 | 0 |  |  |  | 0 | OK
| Partnership Agreement | LP | All | 1 | 286 | 42.9 |  |  |  | 328.9 | OK
| Appointment FLC | LP | All | 2 | 572 | 85.8 |  |  |  | 657.8 | OK
| Management and financial handbook | LP | All | 1 | 286 | 42.9 |  |  |  | 328.9 | OK
| Rules of Procedures for the PR | LP | All |  | 0 | 0 |  |  |  | 0 | OK
| Rules of Procedures for the SG | LP | All |  | 0 | 0 |  |  |  | 0 | OK
| Kick-off meeting | LP | All | 8 | 2288 | 343.2 | 1200 |  |  | 3831.2 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
| Project Management and coordination | [9 empty] | OK
| Daily project management | LP | All | 30 | 8580 | 1287 |  |  |  | 9867 | OK
| Steering Group meeting linked with thematic meeting | LP | All | 15 | 4290 | 643.5 | 3000 |  |  | 7933.5 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
| Reporting | [9 empty] | OK
| Internal financial monitoring/budget revision | LP | All | 8 | 2288 | 343.2 |  |  |  | 2631.2 | OK
| Preparation of partner level progress report | LP | All | 35 | 10010 | 1501.5 |  |  |  | 11511.5 | OK
| Delivery of progress report to JTS | LP | All | 7 | 2002 | 300.3 |  |  |  | 2302.3 | OK
| Delivery of final report to JTS | LP | All | 2 | 572 | 85.8 |  |  |  | 657.8 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
| TOTAL |  |  |  | 31174 | 4676.1 | 4200 | 0 | 0 | 40050.1 | OK
| COMMUNICATION | [9 empty] | OK
| Planning and start-up | [9 empty] | OK
| Communication and knowledge sharing strategy | PP4-VPR | All | 1 | 286 | 42.9 |  |  |  | 328.9 | OK
| Launching event | LP | All | 3 | 858 | 128.7 | 600 |  |  | 1586.7 | OK
| Briefing brochure linked to the Launching event about the project and the topic adressed | PP4-VPR | All | 4 | 1144 | 171.6 |  | 2000 |  | 3315.6 | OK
| Poster (obligatory) | PP4-VPR | All | 2 | 572 | 85.8 |  | 300 |  | 957.8 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
| Website and social media | [9 empty] | OK
| Launching of website and regular update of the website | PP4-VPR | All | 7 | 2002 | 300.3 |  |  |  | 2302.3 | OK
| Social media presence | PP4-VPR | All | 3 | 858 | 128.7 |  |  |  | 986.7 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
| Paticipation in other events | [9 empty] | OK
| INTERREG Europe events | PP4-VPR, LP- VRW | n.a. |  | 0 | 0 |  |  |  | 0 | OK
| Dissemination at transnational events (presenter or exhibitioner) | PP4-VPR | All | 3 | 858 | 128.7 | 600 |  |  | 1586.7 | OK
| Dissemination at national events (presenter or exhibitioner) | PP4-VPR | All | 4 | 1144 | 171.6 | 600 |  |  | 1915.6 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
| Communication materials/tools | [9 empty] | OK
| Press releases | PP4-VPR | TWG meeting/event organisers | 4 | 1144 | 171.6 |  |  |  | 1315.6 | OK
| Newsletters on project level | PP4-VPR | All | 5 | 1430 | 214.5 |  |  |  | 1644.5 | OK
| Project video | PP4-VPR | All | 3 | 858 | 128.7 |  |  |  | 986.7 | OK
| Policy learning Synthesis report | LP- VRW, PP4-VPR | All | 1 | 286 | 42.9 |  |  |  | 328.9 | OK
| Dissemination materials on exchanged experience targeting regions outside the partnership | PP4-VPR | All | 6 | 1716 | 257.4 |  | 3000 |  | 4973.4 | OK
| Mid term event | PP4-VPR | All partners | 3 | 858 | 128.7 | 600 | 1200 |  | 2786.7 | OK
| Final event | PP1- TCC | All partners | 3 | 858 | 128.7 | 600 |  |  | 1586.7 | OK
| Visualisation materials for institutional, stakeholder meetings | PP4- VPR | LP, PP1, PP2, PP3, PP4 | 10 | 2860 | 429 |  | 2000 |  | 5289 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
| TOTAL |  |  |  | 17732 | 2659.8 | 3000 | 8500 | 0 | 31891.8 | OK
| INTERREGIONAL POLICY LEARNING | [9 empty] | OK
| Interregional thematic organisation | [9 empty] | OK
| Setting up Thematic Working Group (TWG) | LP | All partners | 2 | 572 | 85.8 |  |  |  | 657.8 | OK
| TWG Rules of procedure | LP | All partners |  | 0 | 0 |  |  |  | 0 | OK
| TWG meetings linked to thematic implementation | LP | All partners | 15 | 4290 | 643.5 | 3000 |  |  | 7933.5 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
| Stakeholder involvement and organisational learning | [9 empty] | OK
| Setting up stakeholder & institutional learning groups | PP1- TCC | LP + PP5,PP1,PP2,PP3,PP4 | 5 | 1430 | 214.5 |  |  |  | 1644.5 | OK
| Interactive training on stakeholder involvement/institutional learning for the Regional Managers | PP1- TCC | LP + PP5,PP1,PP2,PP3,PP4 | 4 | 1144 | 171.6 |  |  |  | 1315.6 | OK
| Methodology for regional Roadmaps | PP1- TCC | All partners | 1 | 286 | 42.9 |  |  |  | 328.9 | OK
| regional Roadmaps (on the institutional/stakeholder involvement process) elaborated and quality controled | PP1- TCC | LP + PP5,PP1,PP2,PP3,PP4 | 20 | 5720 | 858 |  |  |  | 6578 | OK
| Regional Opening meeting for stakeholders (including some networking lunch, evening reception, regional seminar) | PP1- TCC | LP + PP5,PP1,PP2,PP3,PP4 | 15 | 4290 | 643.5 |  | 2000 |  | 6933.5 | OK
| Meetings with stakeholder groups and Institutional learning groups / involvement in action plan implementation + Synergy Sessions with Institutional departments | PP1- TCC | LP + PP5,PP1,PP2,PP3,PP4 | 30 | 8580 | 1287 |  | 1800 |  | 11667 | OK
| Phase 1 closing stakeholder session (including some networking lunch, evening reception, regional seminar) | PP1- TCC | LP + PP5,PP1,PP2,PP3,PP4 | 15 | 4290 | 643.5 |  | 2000 |  | 6933.5 | OK
| Synergy session for personnel of partner organisations | PP1- TCC | LP + PP5,PP1,PP2,PP3,PP4 | 18 | 5148 | 772.2 |  |  |  | 5920.2 | OK
| Thematic coordination of stakeholder involvement | PP1- TCC | LP- VRW |  | 0 | 0 |  |  |  | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
| Analysis | [9 empty] | OK
| Joint methodology for regional State of Arts | PP3 | All partners | 1 | 286 | 42.9 |  |  |  | 328.9 | OK
| Regional State of Arts (including good practice inventory + list of ingredients for change) | PP3 | LP + PP5,PP1,PP2,PP3,PP4 | 20 | 5720 | 858 |  |  |  | 6578 | OK
| Transnational audit visits to each region by experts delegated by 2 other partners | PP3 | LP + PP5,PP1,PP2,PP3,PP4 | 12 | 3432 | 514.8 | 1200 | 200 |  | 5346.8 | OK
| Project level menu of good practices | PP3 | LP + PP5,PP1,PP2,PP3,PP4 | 4 | 1144 | 171.6 |  |  |  | 1315.6 | OK
| Thematic coordination of analysis phase | PP3 | LP- VRW |  | 0 | 0 |  |  |  | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
| Knowledge exchange (good practice transfer) | [9 empty] | OK
| Guidelines (including matching learning needs with good practices)/methodology and templates for knowledge sharing | LP- VRW | All partners | 2 | 572 | 85.8 |  |  |  | 657.8 | OK
| 3 Transnational Exchange Session meetings of 3 days length (for individual staff members of partners + appr. 3 stakeholders per partner region) | LP- VRW | All partners | 30 | 8580 | 1287 | 4800 | 7200 |  | 21867 | OK
| Summary reports on the Exchange Sessions | LP- VRW | All partners | 5 | 1430 | 214.5 |  |  |  | 1644.5 | OK
| Thematic coordination of knowledge exchange | LP- VRW | n.a. |  | 0 | 0 |  |  |  | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
| Action plan drafting | [9 empty] | OK
| Project level Guideline and joint training on action plan development | PP2 | All partners | 3 | 858 | 128.7 |  |  |  | 986.7 | OK
| Detailed Action Plan methodology on regional level/workplan | PP2 | LP + PP5,PP1,PP2,PP3,PP4 | 5 | 1430 | 214.5 |  |  |  | 1644.5 | OK
| Elaboration of Action Plans / policy instrument | PP2 | LP + PP5,PP1,PP2,PP3,PP4 | 20 | 5720 | 858 |  | 5000 |  | 11578 | OK
| Cross- reading exercise | PP2 | LP + PP5,PP1,PP2,PP3,PP4 | 5 | 1430 | 214.5 |  |  |  | 1644.5 | OK
| Final quality control of Action Plans | PP2 | n.a. | 2 | 572 | 85.8 |  |  |  | 657.8 | OK
| Consistency check of Action Plans on regional level | PP2 | LP + PP5,PP1,PP2,PP3,PP4 | 3 | 858 | 128.7 |  |  |  | 986.7 | OK
| Thematic coordination of action planning | PP2 | LP- VRW |  | 0 | 0 |  |  |  | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
| Action plan implementation follow-up(24 months) |  |  |  |  | 0 |  |  |  |  | OK
| Monitoring of the implementation of the action plans | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 12 | 3432 | 514.8 |  |  |  | 3946.8 | OK
| Summary on the level of achievements / policy instrument | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 4 | 1144 | 171.6 |  |  |  | 1315.6 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
[5 empty] | 0 | 0 |  |  |  | 0 | OK
| TOTAL |  |  |  | 72358 | 10853.7 | 9000 | 18200 | 0 | 110411.7 | OK
| TOTAL |  |  |  | 121264 | 18189.6 | 16200 | 26700 | 0 | 182353.6 | OK
[5 empty] | OK | OK | OK | OK | OK | OK | OK
| Application Form budget |  |  |  | Staff | Overhead | T & A | External expertise | Equip. | TOTAL |  | ERDF | 136765.2
|  |  | PPx - Acronym |  | 121264 | 18189.6 | 16200 | 26700 | 0 | 182353.6 |  | Co-finance | 45588.4
[12 empty] | TOTAL | 182353.6
| Application Form budget - Spending Forecast |  | Period |  | Budget |  | Application Form budget - External expertise | Type of cost |  | Budget |  |  | OK
|  |  | Preparation |  |  |  |  | FLC cost
|  |  | Semester 1 |  |  |  |  | Project/financial/comm. management
|  |  | Semester 2 |  |  |  |  | Meetings: steering group
|  |  | Semester 3 |  |  |  |  | Meetings: dissemination event
|  |  | Semester 4 |  |  |  |  | Meetings: exchange of exp. events
|  |  | Semester 5 |  |  |  |  | Meetings: stakeholder group
|  |  | Semester 6 |  |  |  |  | Travel & acc. cost: non staff
|  |  | Semester 7 |  |  |  |  | Publication and dissemination costs
External support for the exc. of experience
Other
[8 empty] | TOTAL |  | 0
|  |  | TOTAL |  | 0 |  |  |  |  | ERROR
ERROR
| % check tables | Budget lines | % |  |  |  | Application Form budget - Equipment | Type of cost |  | Budget
|  | Staff | 66.5% |  |  |  |  | Office eqiupment
|  | Overhead | 9.975% |  |  |  |  | Other
|  | T & A | 8.884% |  |  |  |  | TOTAL |  | 0
|  | Ext. expertise | 14.64% | [6 empty] | OK
|  | Eqipment | 0%
|  | TOTAL | 100%
|  | CP | %
|  | Management CP | 21.96%
|  | Communication CP | 17.49%
|  | Thematic CP | 60.55%
|  | TOTAL | 100%
|  | Austria | 262
|  | Belgium | 278
|  | Czech Republic | 118
|  | Denmark | 280
|  | Estonia | 110
|  | Finland | 232
|  | France | 233
|  | Germany | 253
|  | Greece | 148
|  | Hungary | 121
|  | Ireland | 286
|  | Italy | 200
|  | Netherlands | 275
|  | Poland | 131
|  | Portugal | 137
|  | Slovak Republic | 118
|  | Slovenia | 185
|  | Spain | 202
|  | Sweden | 236
|  | United Kingdom | 238
|  | Bulgaria | 80
|  | Croatia | 100
|  | Cyprus | 120
|  | Latvia | 104
|  | Lithuania | 100
|  | Luxemburg | 324
|  | Malta | 140
|  | Romania | 80
|  | ERDF | 75%
|  | ERDF | 85%
Note on I28: Tóth Gábor: FLC cost
Note on I37: Tóth Gábor: Translation and printing of the briefing brouchure
Note on I38: Tóth Gábor: Printing cost of the poster
Note on I55: Tóth Gábor: Design and printing cost
Note on I56: Tóth Gábor: Non-staff stakeholder travel (2 person)
Note on I58: Tóth Gábor: Design and printing cost
Note on I74: Tóth Gábor: Cost for organisieng the meeting (incuding networking activities)
Note on I75: Tóth Gábor: Organisation cost
Note on I76: Tóth Gábor: Cost for organisieng the meeting (incuding networking activities)
Note on I84: Tóth Gábor: Organisation cost for hosting the visit
Note on I91: Tóth Gábor: Non-staff stakeholder travel (2 person)
Note on I99: Tóth Gábor: External support for the preparation of the Action Plan

## Task_matrix (hidden)
Action | ACTIVITIES | Partner in charge (coordinator) | Output
|  |  |  | LP -VRW | PP1 - TCC | PP2 - MMC | PP3 - Pons Danubii | PP4 - VPR | PP5 - Province of South Holland
| Policy Instrument |  |  | Shared Policy Intrument with | 1 Policy Intrument | 1 Policy Intrument | 1 Policy Intrument | 1 Policy Intrument | Shared Policy Intrument with
| Shared Policy Instrument with |  |  | PP5 - Province of South Holland |  |  |  |  | LP -VRW
| PROJECT MANAGEMENT AND COORDINATION | LP - ACRONYM
| Contractualisation and start-up | LP - ACRONYM
| Subsidy Contract | LP - ACRONYM | 1 SC signed | x
| Partnership Agreement | LP - ACRONYM | 1 PA signed | x | x | x | x | x | x
| Appointment FLC | LP - ACRONYM |  | x | x | x | x | x | x
| Management and financial handbook | LP - ACRONYM | 1 handbook | x
| Rules of Procedures for the PR | LP - ACRONYM | 1 RoP adopted | x
| Rules of Procedures for the SG | LP - ACRONYM | 1 RoP adopted | x
| Kick-off meeting | LP - ACRONYM | 1 meeting | x | x | x | x | x | x
| Project Management and coordination | LP - ACRONYM
| Daily project management | LP - ACRONYM |  | x | x | x | x | x | x
| Steering Group meeting linked with thematic meeting | LP - ACRONYM | 8 meetings | x | x | x | x | x | x
| Reporting | LP - ACRONYM
| Delivery of internal financial report to LP | LP - ACRONYM |  | x | x | x | x | x | x
| Preparation of partner level progress report | LP - ACRONYM | 8 partner reports / partner | x | x | x | x | x | x
| Delivery of progress report to JTS | LP - ACRONYM | 8 progress report | x
| Delivery of final report to JTS | LP - ACRONYM | 1 final report | x
| Component 2 -COMMUNICATION | PP4 - VPR
Planning and start-up
| Communication and knowledge sharing strategy | PP4 - VPR | 1 project level stategy |  |  |  |  | x
| Launching event | LP | 1 event | x
| Briefing brochure linked to the Launching event about the project and the topic adressed | PP4-VPR | 1 brochure (English and local editions) |  |  |  |  | x
| Poster (obligatory) | PP4-VPR | poster prepared for each partner |  |  |  |  | x
Website and social media
| Launching of website and regular update of the website | PP4-VPR | 1 website regularly updated |  |  |  |  | x
| Social media presence | PP4-VPR | regular update |  |  |  |  | x
Paticipation in other events
| INTERREG Europe events (annual programme events + Policy learning platform events) | PP4-VPR, LP- VRW | 1 event / semester | x |  |  |  | x
| Dissemnation at transnational events (presenter or exhibitioner) | PP4-VPR | 2 events / semester | x | x | x | x | x
| Dissemnation at national events (presenter or exhibitioner) | PP4-VPR | 2 events / partner region | x | x | x | x | x
Communication materials/tools
| Press releases | PP4-VPR | 7 press releases linked to the project meetings/events |  |  |  |  | x
| Newsletters on project level | PP4-VPR | 5 newsletters (English) | x | x | x | x | x
| Project video (+ national language subtitles by partners) | PP4-VPR | 1 English project video |  |  |  |  | x
| Policy learning Synthesis report | LP- VRW, PP4-VPR | 1 Synthesis for dissemination | x |  |  |  | x
| Dissemination materials on exchanged experience targeting regions outside the partnership | PP4-VPR | 3 materials |  |  |  |  | x
| Mid term event | PP4 - VPR | 1 event |  |  |  |  | x
| Final event | PP1 - TCC | 1 event |  | x
| Visualisation materials for institutional, stakeholder meetings | PP4-VPR | 3 materials per region |  |  |  |  | x
Component 3 -INTERREGIONAL POLICY LEARNING
Interregional thematic organisation
| Setting up Thematic Working Group (TWG) (1 expert + 1 project manager + 1 regional manager) | LP | 1 TWG established | x
| TWG Rules of procedure | LP | 1 Rules of Procedures | x
| TWG meetings linked to thematic implementation | LP | 7 meetings (5+2) | x | x | x | x | x | x
Stakeholder involvement and organisational learning
| Setting up stakeholder groups & institutional learning groups | PP1- TCC | 1 group /policy instrument | x | x | x | x | x | x
| Interactive training on stakeholder involvement/institutional learning for the Regional Managers | PP1- TCC | 1 training |  | x
| Methodology for regional Roadmaps | PP1- TCC | 1 methodology |  | x
| regional Roadmaps (on the institutional/stakeholder involvement process) elaborated and quality controled | PP1- TCC | 1 regional roadmap/policy instrument | x | x | x | x | x | x
| Regional Opening meeting for stakeholders (including some networking lunch, evening reception, regional seminar) | PP1- TCC | 1 meeting / stakeholder group | x | x | x | x | x
| Meetings with stakeholder groups and Institutional learning groups / involvement in action plan implementation | PP1- TCC | average 3 meetings / policy intrument / year in Phase1 and 2 meetings / policy instrument + average 1 Synergy Session per year | x | x | x | x | x
| Phase 1 closing stakeholder session (including some networking lunch, evening reception, regional seminar) | PP1- TCC | 1 meeting / stakeholder group | x | x | x | x | x
| Synergy sessions for personnel of partner organisations | PP1 - TCC | 3 sessions / per partner | x | x | x | x | x | x
| Thematic coordination of stakeholder involvement | PP1- TCC | n.a. |  | x
Analysis
| Joint methodology for regional State of Arts | PP3 | 1 methodology |  |  |  | x
| Regional State of Arts | PP3 | 1 analysis-desk research / policy instrument | x | x | x | x | x | x
| Transnational audit visits to each region by experts delegated by 2 other partners | PP3 | 5 visits | x | x | x | x | x | x
| Project level menu of good practices | PP3 | 1 good practice collection |  |  |  | x
| Thematic coordination of analysis phase | PP3 | n.a. |  |  |  | x
Knowledge exchange (good practice transfer)
| Guidelines (including matching learning needs with good practices)/methodology and templates for knowledge sharing | LP- VRW | 1 guide | x
| 3 Transnational Exchange Session meetings of 3 days length (for individual staff members of partners + appr. 3 stakeholders per partner region) | LP- VRW | 3 good practice transfer meetings | x | x | x | x | x | x
| Summary reports on the Exchange Sessions | LP- VRW | 1 report/policy instrument | x
| Thematic coordination of knowledge exchange | LP- VRW | n.a. | x
Action plan drafting
| Project level Guideline and joint training on action plan development | PP2 | 1 guide, 1 training |  |  | x
| Detailed Action Plan methodology on regional level/workplan | PP2 | 1 Action plan methodology / policy instrument (5) | x | x | x | x | x | x
| Elaboration of Action Plans / policy instrument | PP2 | 1 action plan / policy instrument (5) | x | x | x | x | x | x
| Cross- reading exercise | PP2 | 1 procedure | x | x | x | x | x | x
| Final quality control of Action Plans | PP2 | 1 quality control process / action plan |  |  | x
| Consistency check of Action Plans on regional level | PP2 | 1 procedure / action plan | x | x | x | x | x | x
| Thematic coordination of action planning | PP2 | n.a. |  |  | x
Action plan implementation follow-up(24 months)
| Monitoring of the implementation of the action plans | LP- VRW | 1 monitoring procedure / policy instrument | x | x | x | x | x | x
| Summary on the level of achievements / policy instrument | LP- VRW | 1 report / policy instrument | x | x | x | x | x | x
No Policy intrument
1 Policy Intrument
2 Policy Intruments
Shared Policy Intrument with

## Meetings_table
| Color codes: | Management CP |  |  | Travel lump sums | Travel cost 1 person 2 nights |  |  | 600
|  | Communication CP |  |  |  | Travel cost 1 person 3 nights |  |  | 800
Thematic CP
[8 empty] | NL | IE | IT | SK | LT | NL
When | Organiser | Venue (city, country) | Meeting/event | Budgeted under | Purpose / description | Participants | Organisational details | LP -VRW | PP1 - TCC | PP2 - MMC | PP3 - Pons Danubii | PP4 - VPR | PP5 - Province of South Holland
m2 | LP -VRW | NL | Internal kick-off | CP1 | - 1 teambuilding session - content session (detailed work plan, division of tasks) - admininstrative session (general & financial management) | All PPs: 2 participants (project manager, financial or thematic manager) | 1,5-2 day workshop (2 nights) cc. 30 participants |  | 1200 | 1200 | 1200 | 1200
m6 | LP -VRW | NL | Launching conference | WP2 | Dissemination (objectives, planned results) | All PPs: 3 participants (project manager, thematic expert, communication manager or additional thematic expert) | 1.5 day event (2 nights) 0,5 day public event with cc. 100 participants, 1 day partner meeting |  | 600 | 600 | 600 | 600
|  |  | Steering Group 1 | WP1/Act.3 | Process management |  |  |  | 600 | 600 | 600 | 600
|  |  | Thematic Working Group 1 | WP3/Act.1 | Content management |  |  |  | 600 | 600 | 600 | 600
TOTAL TRAVEL BUDGET FOR THE MEETING | [7 empty] | 0 | 1800 | 1800 | 1800 | 1800 | 0
m11 | PP1 - TCC | Ireland | Steering Group 2 | WP1/Act.3 | Process management | All PPs: 2 participants (project manager, thematic expert) | Partner meeting (2 nights) with 1 working dinner cc. 30 participant | 600 |  | 600 | 600 | 600 | 600
|  |  | Thematic Working Group 2 | WP4/Act.5 | Content management |  |  | 600 |  | 600 | 600 | 600 | 600
TOTAL TRAVEL BUDGET FOR THE MEETING | [7 empty] | 1200 | 0 | 1200 | 1200 | 1200 | 1200
m20 | PP2 - MMC | Italy | Steering Group 3 | WP1/Act.3 | Process management | All PPs: 2 participants (project manager, thematic expert) | Partner meeting (2 nights) with 1 working dinner cc. 30 participants | 600 | 600 |  | 600 | 600 | 600
|  |  | Thematic Working Group 3 | WP4/Act.5 | Content management |  |  | 600 | 600 |  | 600 | 600 | 600
TOTAL TRAVEL BUDGET FOR THE MEETING | [7 empty] | 1200 | 1200 | 0 | 1200 | 1200 | 1200
m26 | PP3 - Pons Danubii | SK | Steering Group 4 | WP1/Act.3 | Process management | All PPs: 2 participants (project manager, thematic expert) | Partner meeting (2 nights) with 1 working dinner cc. 30 participants | 600 | 600 | 600 |  | 600 | 600
|  |  | Thematic Working Group 4 | WP3/Act.1 | Content management |  |  | 600 | 600 | 600 |  | 600 | 600
TOTAL TRAVEL BUDGET FOR THE MEETING | [7 empty] | 1200 | 1200 | 1200 | 0 | 1200 | 1200
m30 | PP4 - VPR | Latvia |  |  |  | All PPs: 2 participants (project manager, thematic expert) + 2 stakeholders budgeted under external expertise | Partner meeting (2 nights) with 1 working dinner cc. 30 participants
|  |  | Steering Group 5 | WP1/Act.3 | Process management |  |  | 600 | 600 | 600 | 600 |  | 600
|  |  | Thematic Working Group 5 | WP3/Act.1 | Content management |  |  | 600 | 600 | 600 | 600 |  | 600
TOTAL TRAVEL BUDGET FOR THE MEETING | [7 empty] | 1200 | 1200 | 1200 | 1200 | 0 | 1200
m38 | PP2 - MMC | Italy | Steering Group 6 | WP1/Act.3 | Process management | All PPs: 2 participants (project manager, thematic expert) | Partner meeting (2 nights) with 1 working dinner cc. 30 participants | 600 | 600 |  | 600 | 600 | 600
|  |  | Thematic Working Group 6 | WP3/Act.1 | Content management / montoring |  |  | 600 | 600 |  | 600 | 600 | 600
TOTAL TRAVEL BUDGET FOR THE MEETING | [7 empty] | 1200 | 1200 | 0 | 1200 | 1200 | 1200
m44 | PP1 - TCC | Ireland | Final conference | WP2 | Dissemination (monitoring results) | All PPs: 3 participants (project manager, thematic expert, communication manager or additional thematic expert) | 1.5 day event (2 nights) 0,5 day public event with cc. 100 participants, 1 day partner meeting | 600 |  | 600 | 600 | 600 | 600
|  |  | Steering Group 7 | WP1/Act.3 | Process management |  |  | 600 |  | 600 | 600 | 600 | 600
|  |  | Thematic Working Group 7 | WP3/Act.1 | Content management / montoring |  |  | 600 |  | 600 | 600 | 600 | 600
TOTAL TRAVEL BUDGET FOR THE MEETING | [7 empty] | 1800 | 0 | 1800 | 1800 | 1800 | 1800
TBD |  |  | Participation at INTERREG Europe events | CP1 | PP attends the compulsory INTERREG events | PPs: 1 participants (project/communication manager) | 2 nights | 3000 |  |  |  | 1800
TBD |  |  | Dissemnation at transnational events (presenter or exhibitioner) | CP1 | Each PP visits 1 transational event to disseminate the project | All PPs: 1 participants (project manager) | 2 nights | 1800 | 600 | 600 | 600 | 1800
TBD |  |  | Dissemnation at national events (presenter or exhibitioner) | CP1 | Each PP visits 2 national events to disseminate the project | All PPs: 1 participants (project manager) | 2 nights, local travel | 600 | 600 | 600 | 600 | 600
TBD | PP1 - TCC PP3 - Pons Danubii PP5 - PSH | Ireland Slovakia Netherlands | 3 Transnational knowledge sharing (individual + stakeholder) - Peer review / site visits / staff exchange | CP1 | tbd | All PPs: 2 participants (project manager, thematic expert) + 3 stakeholders budgeted under external expertise | cc. 30 participants | 3200 | 3200 | 4800 | 3200 | 4800 | 3200
TOTAL | [7 empty] | 16400 | 12200 | 14400 | 14000 | 18600 | 11000 | 86600

## Imp_plan_old (hidden)
Action | ACTIVITIES | Partner in charge | Participating partners | Output | Phase 1 – Focus on the interregional learning process | [29 empty] | Phase 2 – monitoring of the action plan implementation
[5 empty] | 1st reporting period | [5 empty] | 2nd reporting period | [5 empty] | 3rd reporting period | [5 empty] | 4th reporting period | [5 empty] | 5th reporting period | [5 empty] | 6th reporting period | [11 empty] | 7th reporting period
[5 empty] | 2016 | [5 empty] | 2016 |  |  | 2017 |  |  | 2017 | [5 empty] | 2017 |  |  | 2018 |  |  | 2018 | [5 empty] | 2018 |  |  | 2019 | [8 empty] | 2019 |  |  | 2020
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
[5 empty] | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Febr | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Febr | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Febr | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Febr | Mar | Apr | May | June | July | Aug | Sept
| Component 1 -PROJECT MANAGEMENT AND COORDINATION | LP
Contractualisation and start-up
| Subsidy Contract | LP | All | 1 SC signed | bar: 2016 1 Apr
| Partnership Agreement | LP | All | 1 PA signed | bar: 2016 1 Apr to 2016 2 May
| Setting up PMTs (Project Management Teams) | LP | All | x PMT set up | bar: 2016 1 Apr
| Appointment FLC | LP | All | x FLC appointed | bar: 2016 1 Apr to 2016 3 June
| Financial and Project Management Guide (FPMG) | LP | All | 1 guide | bar: 2016 1 Apr to 2016 2 May
| Rules of Procedures for the SG | LP | All | 1 RoP adopted | bar: 2016 1 Apr to 2016 2 May
| Kick-off meeting | LP | All | 1 meeting | bar: 2016 2 May
Project Management and coordination
| Daily project management | LP | All | n.a.
| Steering Group meeting linked with TWG meeting | LP | All | 8 meetings | bar: 2016 6 Sept; 2017 11 Febr; 2017 20 Nov; 2018 26 May; 2018 30 Sept; 2019 38 May; 2020 51 June
Reporting
| Internal financial monitoring/budget revision | LP | All | 3 revisions | bar: 2016 9 Dec to 2017 10 Jan; 2017 21 Dec to 2018 22 Jan
| Preparation of partner level progress report | LP | All | 8 partner reports / partner | bar: 2016 6 Sept to 2016 9 Dec; 2017 12 Mar to 2017 15 June; 2017 18 Sept to 2017 21 Dec; 2018 24 Mar to 2018 27 June; 2018 30 Sept to 2018 33 Dec; 2019 42 Sept to 2019 45 Dec; 2020 52 July to 2020 54 Sept
| Delivery of progress report to JTS | LP | All | 8 progress report | bar: 2017 10 Jan; 2017 16 July; 2018 22 Jan; 2018 28 July; 2019 34 Jan; 2020 46 Jan; 2020 54 Sept
| Delivery of final report to JTS | LP | All | 1 final report | bar: 2020 54 Sept
| Component 2 -COMMUNICATION | PP4-VPR
Planning and start-up
| Communication and knowledge sharing strategy | PP4-VPR | All | 1 project level stategy | bar: 2016 2 May to 2016 4 July
| Launching event | LP | All | 1 event | bar: 2016 6 Sept
| Briefing brochure linked to the Launching event about the project and the topic adressed | PP4-VPR | All | 1 brochure (English and local editions) | bar: 2016 5 Aug to 2016 6 Sept
| Poster (obligatory) | PP4-VPR | All | poster prepared for each partner | bar: 2016 5 Aug to 2016 6 Sept
Website and social media
| Launching of website and regular update of the website | PP4-VPR | All | 1 website regularly updated
| Social media presence | PP4-VPR | All | regular update
Paticipation in other events
| INTERREG Europe events (annual programme events + Policy learning platform events) | PP4-VPR, LP- VRW | n.a. | 1 event / semester | bar: 2016 6 Sept; 2017 11 Febr; 2017 17 Aug; 2018 23 Febr; 2018 29 Aug
| Dissemnation at transnational events (presenter or exhibitioner) | PP4-VPR | All | 2 events / semester | bar: 2016 6 Sept; 2017 10 Jan; 2018 22 Jan; 2018 28 July
| Dissemnation at national events (presenter or exhibitioner) | PP4-VPR | All | 2 events / partner region | bar: 2016 3 June; 2016 8 Nov; 2017 15 June; 2017 20 Nov; 2018 27 June
Communication materials/tools
| Press releases | PP4-VPR | TWG meeting/event organisers | 7 press releases linked to the project meetings/events | bar: 2016 6 Sept; 2017 11 Febr; 2017 20 Nov; 2018 26 May; 2018 30 Sept; 2019 38 May; 2020 51 June
| Newsletters on project level | PP4-VPR | All | 5 newsletters (English) | bar: 2016 6 Sept; 2017 11 Febr; 2017 20 Nov; 2018 26 May; 2018 30 Sept
| Project video | PP4-VPR | All | 1 English project video | bar: 2018 29 Aug to 2018 30 Sept
| Policy learning Synthesis report | LP- VRW, PP4-VPR | All | 1 Synthesis for dissemination | bar: 2018 29 Aug to 2018 30 Sept
| Dissemination materials on exchanged experience targeting regions outside the partnership | PP4-VPR | All | 3 materials | bar: 2018 29 Aug to 2018 30 Sept
| Mid term event | PP4-VPR | All partners | 1 event | bar: 2018 30 Sept
| Final event | PP1- TCC | All partners | 1 event | bar: 2020 51 June
| Visualisation materials for institutional, stakeholder meetings | PP4- VPR | LP, PP1, PP2, PP3, PP4 | 3 materials per region | bar: 2016 5 Aug to 2018 30 Sept
Component 3 -INTERREGIONAL POLICY LEARNING
Interregional thematic organisation
| Setting up Thematic Working Group (TWG) | LP | All partners | 1 TWG established | bar: 2016 2 May
| TWG Rules of procedure | LP | All partners | 1 Rules of Procedures | bar: 2016 2 May
| TWG meetings linked to thematic implementation | LP | All partners | 7 meetings (5+2) | bar: 2016 6 Sept; 2017 11 Febr; 2017 20 Nov; 2018 26 May; 2018 30 Sept; 2019 38 May; 2020 51 June
Stakeholder involvement and organisational learning
| Setting up stakeholder & institutional learning groups | PP1- TCC | LP + PP5,PP1,PP2,PP3,PP4 | 1 group /policy instrument | bar: 2016 5 Aug to 2016 6 Sept
| Interactive training on stakeholder involvement/institutional learning for the Regional Managers | PP1- TCC | LP + PP5,PP1,PP2,PP3,PP4 | 1 training | bar: 2016 6 Sept
| Methodology for regional Roadmaps | PP1- TCC | All partners | 1 methodology | bar: 2016 6 Sept
| regional Roadmaps (on the institutional/stakeholder involvement process) elaborated and quality controled | PP1- TCC | LP + PP5,PP1,PP2,PP3,PP4 | 1 regional roadmap/policy instrument | bar: 2016 7 Oct
| Regional Opening meeting for stakeholders (including some networking lunch, evening reception, regional seminar) | PP1- TCC | LP + PP5,PP1,PP2,PP3,PP4 | 1 meeting / stakeholder group | bar: 2016 6 Sept
| Meetings with stakeholder groups and Institutional learning groups / involvement in action plan implementation + Synergy Sessions with Institutional departments | PP1- TCC | LP + PP5,PP1,PP2,PP3,PP4 | average 3 meetings / policy intrument / year in Phase1 and 2 meetings / policy instrument + average 1 Synergy Session per year | bar: 2016 6 Sept to 2018 30 Sept; 2020 54 Sept
| Phase 1 closing stakeholder session (including some networking lunch, evening reception, regional seminar) | PP1- TCC | LP + PP5,PP1,PP2,PP3,PP4 | 1 meeting / stakeholder group | bar: 2018 30 Sept
| Synergy session for personnel of partner organisations | PP1- TCC | LP + PP5,PP1,PP2,PP3,PP4 | 3 sessions / per partner | bar: 2016 8 Nov; 2017 18 Sept; 2018 25 Apr; 2018 30 Sept
| Thematic coordination of stakeholder involvement | PP1- TCC | LP- VRW | n.a.
Analysis
| Joint methodology for regional State of Arts | PP3 | All partners | 1 methodology | bar: 2016 5 Aug to 2016 6 Sept
| Regional State of Arts (including good practice inventory + list of ingredients for change) | PP3 | LP + PP5,PP1,PP2,PP3,PP4 | 1 analysis-desk research / policy instrument | bar: 2016 6 Sept to 2016 9 Dec
| Transnational audit visits to each region by experts delegated by 2 other partners | PP3 | LP + PP5,PP1,PP2,PP3,PP4 | 5 visits | bar: 2016 7 Oct to 2016 9 Dec
| Project level menu of good practices | PP3 | LP + PP5,PP1,PP2,PP3,PP4 | 1 good practice collection | bar: 2016 8 Nov to 2017 10 Jan
| Thematic coordination of analysis phase | PP3 | LP- VRW | n.a. | bar: 2016 2 May to 2016 9 Dec
Knowledge exchange (good practice transfer)
| Guidelines (including matching learning needs with good practices)/methodology and templates for knowledge sharing | LP- VRW | All partners | 1 guide | bar: 2017 10 Jan to 2017 12 Mar
| 3 Transnational Exchange Session meetings of 3 days length (for individual staff members of partners + appr. 3 stakeholders per partner region) | LP- VRW | All partners | 3 good practice transfer meetings | bar: 2017 12 Mar to 2017 18 Sept
| Summary reports on the Exchange Sessions | LP- VRW | All partners | 1 report/policy instrument | bar: 2017 13 Apr to 2017 19 Oct
| Thematic coordination of knowledge exchange | LP- VRW | n.a. | n.a. | bar: 2016 9 Dec to 2017 20 Nov
Action plan drafting
| Project level Guideline and joint training on action plan development | PP2 | All partners | 1 guide, 1 training | bar: 2017 20 Nov to 2017 21 Dec
| Detailed Action Plan methodology on regional level/workplan | PP2 | LP + PP5,PP1,PP2,PP3,PP4 | 1 Action plan methodology / policy instrument (5) | bar: 2018 22 Jan
| Elaboration of Action Plans / policy instrument | PP2 | LP + PP5,PP1,PP2,PP3,PP4 | 1 action plan / policy instrument (5) | bar: 2018 23 Febr to 2018 28 July
| Cross- reading exercise | PP2 | LP + PP5,PP1,PP2,PP3,PP4 | 1 procedure | bar: 2018 27 June to 2018 28 July
| Final quality control of Action Plans | PP2 | n.a. | 1 quality control process / action plan | bar: 2018 28 July to 2018 29 Aug
| Consistency check of Action Plans on regional level | PP2 | LP + PP5,PP1,PP2,PP3,PP4 | 1 procedure / action plan | bar: 2018 28 July to 2018 29 Aug
| Thematic coordination of action planning | PP2 | LP- VRW | n.a. | bar: 2017 19 Oct to 2018 30 Sept
Action plan implementation follow-up(24 months)
| Monitoring of the implementation of the action plans | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 1 monitoring procedure / policy instrument | bar: 2018 31 Oct to 2020 54 Sept
| Summary on the level of achievements / policy instrument | LP- VRW | LP + PP5,PP1,PP2,PP3,PP4 | 1 report / policy instrument | bar: 2020 50 May to 2020 52 July

## PPx_template (hidden)
PPx - Acronym |  |  |  | Country -->
DAILY FEE |  | 0 |  |  | Travel cost 1 person 2 nights |  |  | 650 |  |  | Austria | 294 | 294.2558
[5 empty] | Travel cost 2 person 2 nights |  |  | 1300 |  |  | Belgium | 313 | 313.0248
[11 empty] | Czech Republic | 132 | 132.405
Action | ACTIVITIES | Partner in charge | Participating | [7 empty] | Denmark | 315 | 314.75
|  |  |  | Staff |  | Overhead | Travel and accommodation | External expertise | EQUIP | TOTAL | Estonia | 123 | 123.3298
|  |  |  | days | total | [5 empty] | Finland | 261 | 260.7997
[11 empty] | France | 262 | 261.9846
| PROJECT MANAGEMENT AND COORDINATION | LP | [8 empty] | Germany | 284 | 284.3798
| Contractualisation and start-up | [9 empty] | Greece | 166 | 166.0304
| Subsidy Contract | LP | All |  | 0 | 0 |  |  |  | 0 | Hungary | 136 | 136.3763
| Partnership Agreement | LP | All |  | 0 | 0 |  |  |  | 0 | Ireland | 322 | 322.2954
| Appointment FLC | LP | All |  | 0 | 0 |  |  |  | 0 | Italy | 225 | 225
| Management and financial handbook | LP | All |  | 0 | 0 |  |  |  | 0 | Netherlands | 310 | 309.8218
| Rules of Procedures for the PR | LP | All |  | 0 | 0 |  |  |  | 0 | Poland | 147 | 147.4892
| Rules of Procedures for the SG | LP | All |  | 0 | 0 |  |  |  | 0 | Portugal | 154 | 154.2143
| Kick-off meeting | LP | All |  | 0 | 0 |  |  |  | 0 | Slovak Republic | 132 | 132.2032
[5 empty] | 0 | 0 |  |  |  | 0 | Slovenia | 209 | 208.5682
| Project Management and coordination | [9 empty] | Spain | 227 | 226.7122
| Daily project management | LP | All |  | 0 | 0 |  |  |  | 0 | Sweden | 266 | 265.7345
| Steering Group meeting linked with thematic meeting | LP | All |  | 0 | 0 |  |  |  | 0 | United Kingdom | 268 | 268.1693
[5 empty] | 0 | 0 |  |  |  | 0 | Bulgaria | 90 | 90
| Reporting | [9 empty] | Croatia | 113 | 112.5
| Delivery of internal financial report to LP | LP | All |  | 0 | 0 |  |  |  | 0 | Cyprus | 135 | 135
| Preparation of partner level progress report | LP | All |  | 0 | 0 |  |  |  | 0 | Latvia | 117 | 117
| Delivery of progress report to JTS | LP | All |  | 0 | 0 |  |  |  | 0 | Lithuania | 113 | 112.5
| Delivery of final report to JTS | LP | All |  | 0 | 0 |  |  |  | 0 | Luxemburg | 365 | 364.5
[5 empty] | 0 | 0 |  |  |  | 0
| TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | Malta | 158 | 157.5
| COMMUNICATION | [9 empty] | Romania | 90 | 90
Planning and start-up
| Communication plan and knowledge sharing strategy |  |  |  | 0 | 0 |  |  |  | 0
| List of stakeholders to reach |  |  |  | 0 | 0 |  |  |  | 0
| Launching event |  |  |  | 0 | 0 |  |  |  | 0
| Briefing brochure linked to the Launching event about the project and the topic adressed |  |  |  | 0 | 0 |  |  |  | 0
| Poster |  |  |  | 0 | 0 |  |  |  | 0
Website and social media
| Regular update of the website |  |  |  | 0 | 0 |  |  |  | 0
| Social media presence |  |  |  | 0 | 0 |  |  |  | 0
| Press releases |  |  |  | 0 | 0 |  |  |  | 0
[5 empty] | 0 | 0 |  |  |  | 0
Paticipation in other events
| INTERREG Europe events |  |  |  | 0 | 0 |  |  |  | 0
| Dissemnation at transnational events (presenter or exhibitioner) |  |  |  | 0 | 0 |  |  |  | 0
| Dissemnation at national events (presenter or exhibitioner) |  |  |  | 0 | 0 |  |  |  | 0
[5 empty] | 0 | 0 |  |  |  | 0
Communication materials/tools
| Briefing brochures/leaflets on the implementation |  |  |  | 0 | 0 |  |  |  | 0
| Newsletters |  |  |  | 0 | 0 |  |  |  | 0
| Awereness raising project video |  |  |  | 0 | 0 |  |  |  | 0
| Dissemination type stakeholder meeting (networking lunch, evening reception, regional seminar) |  |  |  | 0 | 0 |  |  |  | 0
| Mid term event |  |  |  | 0 | 0 |  |  |  | 0
| Final event |  |  |  | 0 | 0 |  |  |  | 0
0
| TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
INTERREGIONAL POLICY LEARNING
Stakeholder involvement (36 months + 24 months)
| Setting up stakeholder groups / policy instrument |  |  |  | 0 | 0 |  |  |  | 0
| Meetings with stakeholder groups / involvement in action plan implementation |  |  |  | 0 | 0
| Final regional stakeholder event |  |  |  | 0 | 0
| Thematic coordination of stakeholder involvement |  |  |  | 0 | 0
Analysis (6-8 months)
| Joint methodology for regional analysis |  |  |  | 0 | 0
| Regional anaylsis - desk research, own need and gift (N&G) analysis |  |  |  | 0 | 0
| Synthesis and knowledge exchange match- making matrix |  |  |  | 0 | 0
| Thematic coordination of analysis |  |  |  | 0 | 0
Knowledge exchange (12-14 months)
| Complex methodology for knowledge sharing (defining level of knowledge sharing) |  |  |  | 0 | 0
| Transnational knowledge sharing (individual + stakeholder) - Peer review / site visits / staff exchange |  |  |  | 0 | 0
| Organisational knowledge sharing (organisational) |  |  |  | 0 | 0
| EU level knowledge sharing (Brussels briefing; networking; Policy Learning Platform, etc.) |  |  |  | 0 | 0
| Regional summary reports on knowledge sharing |  |  |  | 0 | 0
| Synthesis on knowledge sharing |  |  |  | 0 | 0
| Thematic coordnation of knowledge exchange |  |  |  | 0 | 0
Action planning (6-8 months)
| Guidance on action plan development |  |  |  | 0 | 0
| Elaboration of action plans / policy instrument |  |  |  | 0 | 0
| Endorsement procedure / policy instrument |  |  |  | 0 | 0
| Thematic coordination of action planning |  |  |  | 0 | 0
| Action plan implementation follow-up(24 months) |  |  |  |  | 0 |  |  |  | 0
| Monitoring of the implementation of the action plans |  |  |  | 0 | 0 |  |  |  | 0
| Summary on the level of achievements / policy instrument |  |  |  | 0 | 0 |  |  |  | 0
| Transnational thematic meetings |  |  |  |  | 0 |  |  |  | 0
| Thematic meetings linked to thematic implementation |  |  |  | 0 | 0 |  |  |  | 0
[5 empty] | 0 | 0 |  |  |  | 0
| TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0